## Cover_Control
ROK SPORTS PRECINCT — STAGE 1 ¦ TCS COST MODEL V2
Entity | TriCore Civil Services Pty Ltd (TCS) — civil stormwater
ABN | 89 195 291 365
Tender | TEN16699 — Rockhampton Sports Precinct Stage 1A ('A Home for Netball') & Stage 1B ('Recreational Park and Public Amenities')
Site | 554-700 Yaamba Rd, Norman Gardens QLD
Quote reference | TCS #2372-V2
Date | 26-07-2026
GST | ALL SUMS EX-GST throughout this workbook
Architecture | CQU/Hyd pattern per COST_MODEL_REBUILD_DECISION.md: Cover_Control / TCS $ Sched / work-area sheets / 5 masters / Prelim_OH / EBC / Sched3_Extract
KEY TOTALS (live)
Stage 1A lump sum (excl PC) |  | 2761814.9757
Stage 1A WSUD PC sum |  | 111787.7395
Stage 1A total incl PC |  | 2873602.7152
Stage 1B lump sum |  | 113131.2626
TCS GRAND TOTAL ex GST |  | 2986733.9777
Old Civil workbook total (materials-only, superseded) |  | 890849.95
REVISION / CHANGE LOG
V1 | 16-07-2026 — MasterCostSheet_Civ.V1 — original TCS Quote #2372. Part A $890,849.95 ex GST = materials/subbies-only marked up: labour $0, plant $0, no accommodation, GT drains excluded (orphaned $164,860 column), Prelim_OH check empty, profit compounded on (cost+prelims+OH) = 45.73% effective vs 41.5% label, external link to unrelated Loganlea 2018-era file.
V2 | 26-07-2026 — FULL REBUILD on CQU/Hyd architecture (this workbook). Adopted quantities (Phase 4), re-sourced rates (Phase 5), FIFO labour x1.08 + crew-days/plant-days/accommodation (Phase 7), markup re-based to directed 41.5% each-on-cost (old effective 45.73% — both shown), GST removed, all external links severed (values frozen from dumps then re-sourced), GT reinstated, WSUD re-based to Reece PC line, kerb chutes carried both ways (D6-F1), basin/spillway $0 allocation-RFI flag. LH supervision priced as DIRECT LABOUR per TriCore methodology (correction recorded at change-log S9). See TCS_CHANGE_LOG.md + MIGRATION_RECONCILIATION.xlsx.
ASSUMPTIONS & BASIS
1. | Quantities: ADOPTED column of QUANTITY_RECONCILIATION.xlsx (TCS_Civil + NewItems) is the sole pricing basis; Denis's figures retained there — variances reasoned in MIGRATION_RECONCILIATION.xlsx.
2. | Labour: FIFO Roster Example #3 (6-day week, 10-hr days, 21 work-days / 210 hrs per month); ROK monthly bases x1.08 -> LH $132.9634/hr, Trades $101.6458/hr, T/A $82.9510/hr; crews of 3 (2 Trades + 1 T/A) = $2,862.43/crew-day.
3. | Crew-days and plant-days: PROGRAMME_LABOUR_PLANT.xlsx TCS_Activities/TCS_Programme (233 base cd = 222 1A + 11 1B; B-07 spillway 10 cd held at $0 pending allocation RFI; B-09 kerb chutes 9 cd EBC).
4. | Leading Hand supervision (120 days) is DIRECT LABOUR in the Stage 1A/1B labour blocks (row A-14 each), allocated pro-rata to crew-days — per TriCore's existing methodology, which prices TRADESMAN_LEADING HAND as a Day line inside the work-area labour block (old Civ 'SW Zone Sumry' B13/C13/E13 feeding H11; the Hyd master follows the same pattern). It is NOT a preliminary. Establishment non-labour, temp services incl. temp water cartage, EDQ remob and ADAC/CCTV/as-cons are funded from the 5.5% prelims allowance; Prelim_OH builds those bottom-up and carries the variance cross-check (LH row retained there at $0 for traceability).
5. | Markup: Prelims 5.5% + OH 18% + Profit 18% EACH ON TOTAL COST (= 41.5%); cost = escalated-contingent materials + labour + plant + subbies + accommodation. Corrects old compounding (45.73% effective).
6. | Material contingency x1.18 on materials only (incl freight); never on labour/plant/PC/provisional; no quote on file embeds contingency (Register S3).
7. | Escalation to 2027 commencement applied ONCE via factors x1.38 PE/PVC (incl PP Stormpro + Hauraton Recyfix PE-PP), x1.15 subbies, x1.20 delivery — only where KeyRates safe-to-multiply flag is Y; concrete/precast/quarry carry no directed factor (escalation risk inside x1.18 + re-quote condition). Per-rate decision recorded on Materials_Master.
8. | Supplier selection: cheaper compliant rate per item — Humes (RCP, RCBC, BCC headwalls, twin 375), Reece (winged 375 headwall, PP Stormpro, Hauraton, 100 PVC), Tradelink (225/150 PVC, 600 pits), Jaybro (small headwalls + freight adder). RCP375 take-off discrepancy (Humes 299 vs Reece 262 lengths) noted — adopted 714.9 m governs.
9. | PP lines priced as PP (StormPRO o.e.) per drawings — Atlan HDPE cheaper but day-of-issue validity and spec acceptance unconfirmed (Opens #5).
10. | WSUD: supply+delivery PC Sum $97,206.73 + 15% (Reece Q-459014431; Ocean Protect direct re-quote required — MUSIC model); installation in base lump sum (locked 5.3).
11. | Trench drains REINSTATED (Hauraton package $162,349 quote basis; old model's $164,860 orphan superseded) incl excavation & quarry; GT6 grate substitution verify (Gap #7); Reece $198/m Fibretec anomaly to confirm (delta $19,217).
12. | Kerb chutes: base EXCLUDED per Denis 24-Jul; add-price 9 chutes + rock/mat on EBC — 'Director decision D6-F1', both positions carried.
13. | Rock: base allows geotech-anticipated band only (NQL2024-0320 refusal 25/36; A-08 allowance 10 cd); extra-over soft/hard rates for trenches AND pits tendered separately (H002 n.24) on TCS $ Sched.
14. | Rising main ($ and 110 m allowance) and $20k provisional connection fees are TPS-side — NOT in this model. Pump station excluded (Add 2).
15. | Detention basin earthworks/spillway NOT priced — $0 flagged rows, allocation RFI pending (Opens #26 + Director); spillway build-up held on EBC.
16. | Accommodation Option A (apartments house 3, LH individual nightly) ADOPTED; Option B shown. FIFO flights $200 ex GST/leg, 2 returns/person-month. Allocated 1A/1B pro-rata crew-days.
17. | Stage split: VOL 20 SE_12306_SKT_CMP Rev B hatches (RFI to confirm): GT5+GT6+lines 60/61/83 = 1B; all else incl WSUD + detention outlet = 1A.
18. | All external links severed: [SBSERVER Loganlea 60 Richards St V2.xls] inherited link NOT carried; Hyd-master monthly labour bases and accommodation rates frozen as stated inputs (source noted per cell).
19. | Crane (50t), franna, trench shields carried as ALLOWANCES — absent from all hire registers (flagged on Equip_Master); PE welder flagged not required for TCS scope.
20. | Validity cliff: every quote expires Aug-2026 vs 2027 start — escalation carried once as above; re-quote at award (Register S5).

## TCS $ Sched
TCS $ SCHED — SUMMARY
TriCore Civil Services Pty Ltd — ABN 89 195 291 365
TEN16699 ROK Sports Precinct Stage 1A & 1B — Civil Stormwater ¦ 554-700 Yaamba Rd, Norman Gardens QLD
TCS Quote #: 2372-V2 ¦ Date: 26-07-2026 ¦ Rev: V2 (rebuild on CQU/Hyd architecture)
ALL SUMS EX-GST
MARKUP BASIS (Directive 5.4): Prelims + OH + Profit EACH calculated ON TOTAL COST — NOT compounded.
Prelims % | 5.5% |  |  |  |  | CHANGE LOG: old model compounded profit on (cost+prelims+OH) giving 45.73% effective while labelled 41.5%; this model applies the directed 41.5% (each % on cost). Movement recorded in TCS_CHANGE_LOG.md.
Overheads % | 18%
Profit % | 18%
Total effective markup on cost | 41.5%
STAGE 1A — 'A HOME FOR NETBALL' (Sch 3 items 2.3-a drainage component / 2.5 Drainage / 3.5 Grated trench drains)
Materials (escalated + x1.18 contingency) |  | 880272.9489
Labour incl. LH supervision (crew-days x FIFO rates) |  | 758545.605
Plant |  | 165146.73
Subbies & services |  | 41975
Accommodation & FIFO travel share |  | 105872.4197
STAGE 1A TOTAL COST |  | 1951812.7036
Prelims (5.5% on cost) |  | 107349.6987
Overheads (18% on cost) |  | 351326.2867
Profit (18% on cost) |  | 351326.2867
STAGE 1A LUMP SUM (EX-GST, excl PC sums) |  | 2761814.9757
STAGE 1A — PC SUMS (SEPARATED; not in lump sum above)
WSUD StormFilter — 22x Tall (690) PSorb cartridges in DN3300 manhole — SUPPLY + DELIVERY |  | 90064.63 |  |  |  | Reece Q-459014431 line (only project-specific price; verify vs direct Ocean Protect quote — Register Gap #1 / Opens #10). Superseded Atlan $88,838 basis removed.
Freight — StormFilter manhole |  | 7142.1
PC base (supply + delivery) |  | 97206.73
PC markup % | 15%
WSUD PC SUM TOTAL (supply + delivery + 15%) |  | 111787.7395 |  |  |  | INSTALLATION (excavation, bedding, cranage, placement, connection, backfill — Phase 7 activity C-05) is priced in the BASE lump sum, not in this PC (locked 5.3).
STAGE 1A TOTAL INCL PC SUMS (EX-GST) |  | 2873602.7152
STAGE 1B — 'RECREATIONAL PARK AND PUBLIC AMENITIES' (Sch 3 item 2.3 Drainage)
Materials (escalated + x1.18 contingency) |  | 29185.1927
Labour incl. LH supervision |  | 39331.5294
Plant |  | 2942.12
Subbies & services |  | 2999.2
Accommodation & FIFO travel share |  | 5493.3803
STAGE 1B TOTAL COST |  | 79951.4223
Prelims (5.5% on cost) |  | 4397.3282
Overheads (18% on cost) |  | 14391.256
Profit (18% on cost) |  | 14391.256
STAGE 1B LUMP SUM (EX-GST; no PC sums in 1B) |  | 113131.2626 |  |  |  | Sch 1B 2.3-b 'Retention basin': no separate 1B basin is documented — carried unpriced with qualification + RFI (CL A4). The single detention basin outlet works are in 1A.
TCS GRAND TOTAL — STAGE 1A + 1B INCL PC SUMS (EX-GST) |  | 2986733.9777
SCHEDULE OF RATES — Sch 1A 7.0 / 1B 5.0 (extra-over rates, each stage, TCS trenches AND pits; H002 n.24: soft AND hard rock separately). Payable per ITT S18 written-direction regime.
Build-up: (crew day + excavator + breaker) / production m3/day = cost rate; sell = cost x (1+41.5%).
Rate item | Prod (m3/day) | Unit | Cost rate | SELL RATE | Note
Rock extra-over — SOFT rock, TRENCHES | 20 | m3 | 168.9858 | 239.1149 | Breaker + 20-24T + crew; XW/soft rippable band
Rock extra-over — HARD rock, TRENCHES | 10 | m3 | 337.9716 | 478.2298 | Hammer production halved
Rock extra-over — SOFT rock, PITS | 15 | m3 | 225.3144 | 318.8199 | Confined pit excavation penalty
Rock extra-over — HARD rock, PITS | 8 | m3 | 422.4645 | 597.7873
Unsuitable ground — removal & reinstatement | 30 | m3 | 275.8905 | 390.3851 | Excavate + cart + imported backfill; Superintendent written direction only
Base lump sums allow the geotech-anticipated rock band only (NQL2024-0320: refusal 25/36 locations, XW rock 0.2-2.2 m at 6 pits; ~15% of trench metres at reduced production — labour A-08). Rock beyond that band is claimable at these rates on written direction.

## Stage1A_Drainage
STAGE 1A — CIVIL STORMWATER WORK AREA (TCS)
Quantities = ADOPTED per QUANTITY_RECONCILIATION.xlsx TCS_Civil (pricing basis). Rates ref Materials_Master adopted (escalated) rates. ALL SUMS EX-GST.
ID | Description | Qty | Unit | Rate | Total | Source / note
A — MATERIALS (adopted qty x source-tagged escalated rate)
P1 | RCP 375 CL3+CL4 mainline incl C09 twin barrels (adopted 702.9 m CL3 + 12.0 m CL4) | 714.9 | m | 105 | 75064.5 | Adopted 714.9 m governs (Humes 299-len vs Reece 262-len take-off discrepancy noted). CL4 12.0 m re-split per Opens #2.
P2 | 375 rubber rings (1 per 2.44 m length) | 293 | ea | 4.8 | 1406.4 | Qty = lengths of P1.
P3 | RCP 600 CL3 (line 26 stub, 1:500 grade) | 3.31 | m | 183.5656 | 607.602
P4 | 600 rubber rings (allowance) | 2 | ea | 24 | 48
P5 | 225 PP collector (lines 26-29) | 137.67 | m | 49.786 | 6854.0354
P6 | 300 PP (tank line 25 — deepest pipework 1.57-1.67 m) | 58.56 | m | 82.8 | 4848.768
P7 | 375 PP collectors (17 m court bays) | 210.43 | m | 126.974 | 26719.131
P8 | 450 PP (line 26) | 41.47 | m | 186.3 | 7725.861
P9 | 600 PP (line 26) | 38.47 | m | 311.9272 | 11999.8386
P10 | Jointing lubricant | 10 | ea | 17 | 170
P11 | 225 PVC DWV SN8 — building drainage collector line 81 (adopted printed chainage 115.45 m; Denis 180.93 m over-measure removed) | 115.45 | m | 178.595 | 20618.7927 | Rule 2 — printed design data governs (Opens #1).
P12 | 150 PVC DWV SN8 — trash box laterals lines 30-53/87 (1A share; 29.6 m to 1B) | 33.25 | m | 50.623 | 1683.2147
P13 | 100 PVC DWV — subsoil outlets / building DP laterals | 283.71 | m | 9.9061 | 2810.4596 | Subsoil SYSTEM excluded by others; outlets/connections at TCS pits only (matrix 2.3-x2/2.5-x3).
F1 | 100 PVC 90 deg bends | 17 | ea | 4.83 | 82.11
F2 | 100 PVC 45 deg bends | 9 | ea | 4.83 | 43.47
F3 | 225 PVC 90 deg bend | 1 | ea | 32.43 | 32.43
F4 | 100 PVC 45 deg junctions | 26 | ea | 13.8 | 358.8
F5 | 225 PVC 45 deg junction | 1 | ea | 82.938 | 82.938
F6 | 225x100 PVC 45 deg junctions | 11 | ea | 53.199 | 585.189
F7 | Inspection openings c/w galv cover flush | 3 | ea | 207 | 621
F8 | Pipe-to-pipe / pipe-to-culvert connections (20 P2P per F1310) | 20 | ea | 310 | 6200
C1 | RCBC 600x300 crowns (C05-C08, 33.39 m @ 2.4 m/unit) | 14 | ea | 1095 | 15330 | Zero/negative cover at headwalls — extra-over excav/bedding at Q2 (NewItems #2).
C2 | RCBC 750x300 crowns (WSUD high-flow bypass, 5.17 m) | 3 | ea | 1171.2 | 3513.6
C3 | RCBC 900x450 crowns (C01/C02, 27.86 m) | 12 | ea | 1404.8 | 16857.6
C4 | RCBC 1200x600 crowns (C03, 17.77 m) | 8 | ea | 1718.4 | 13747.2
C5 | LBC 1500x600 crowns (C04, 29.04 m) | 13 | ea | 3065.72 | 39854.36
C6 | LBC 2700x1200 crowns (C10 basin outlet, 17.53 m — heavy lift) | 8 | ea | 5891.95 | 47135.6
H1 | Headwalls to suit 375 RCP | 5 | ea | 317.05 | 1585.25
H2 | Headwalls to suit 2x375 RCP (C09A/B — details missing, RFI Opens #8) | 2 | ea | 588.8 | 1177.6
H3 | Headwall to suit 150 PVC (87-01) | 1 | ea | 158 | 158
H4 | Headwall to suit 225 PVC (81-01; adopted 1 vs Denis 2 per F1310) | 1 | ea | 280 | 280
H5 | Headwall to suit 300 PP (25-01) | 1 | ea | 352 | 352
H6 | BCC headwalls 600x300 (C05A/B-C08A/B) | 8 | ea | 1800.63 | 14405.04
H7 | BCC headwall 750x300 (26-01) | 1 | ea | 2162.6 | 2162.6
H8 | BCC headwalls 900x450 (C01A/B, C02A/B) | 4 | ea | 2425.63 | 9702.52
H9 | BCC headwalls 1200x600 (C03A/B) | 2 | ea | 3322.45 | 6644.9
H10 | BCC headwalls 1500x600 (C04A/B, skew 22 deg) | 2 | ea | 4222.78 | 8445.56
H11 | BCC headwalls 2700x1200 (C10A/B) | 2 | ea | 5241.45 | 10482.9
S1 | RGU inlets on-grade 2.4 m (CMDG-D-020) | 28 | ea | 1350 | 37800
S2 | RGU inlets sag 2.4 m | 5 | ea | 1350 | 6750
S3 | 1050 access chamber shafts (CMDG-D-030) | 13 | ea | 364 | 4732
S4 | Aspro cover slabs 1050x1350 | 13 | ea | 400 | 5200
S5 | 1200x900 chamber shafts (25-03, 26-03, 26-05) | 3 | ea | 1101 | 3303 | Adopted 4 total 1200 chambers (Denis 3) — Opens #4.
S6 | 1200x1200 chamber shaft (26-02 c/w 0.467 m internal upstand) | 1 | ea | 1403 | 1403 | Upstand formwork in labour B-03.
S7 | Aspro cover slabs 1200x1650 | 4 | ea | 400 | 1600
S8 | Grate & frame 600x900 Class D (chamber covers) | 17 | ea | 298 | 5066
S9 | 600x600 field inlet pits Type 2 (81-02, 81-07, 87-02) | 3 | ea | 229.5 | 688.5
S10 | 600x600 Class D grates & frames | 3 | ea | 365.2 | 1095.6
G1 | Grated trench GT1-GT4 Recyfix PRO200 Fibretec B125 (F1320 schedule 125.2+141.2x3) | 548.8 | m | 321.4572 | 176415.7114 | Sch 1A 3.5 — TCS despite 'Hydraulic' heading (locked 5.1). REINSTATED (Denis excluded). GT2 '4 pits' RFI Opens #7.
G2 | Grated trench GT7-GT9 Recyfix PRO100 SS heelguard (3.6+6.0+3.5) | 13.1 | m | 508.1712 | 6657.0427 | REINSTATED.
G3 | Hauraton trash boxes TB200 | 25 | ea | 738.7002 | 18467.505
G4 | End caps PRO200 | 8 | ea | 32.4714 | 259.7712
G5 | End caps PRO100 | 10 | ea | 12.9858 | 129.858
R1 | Rock beaching D50=200 x 360 deep — culvert headwalls (70.4 m2) | 25.344 | m3 | 110 | 2787.84 | Geotech-anticipated erosion protection band — base scope.
R2 | Rock beaching d50=100 x 180 thick (179.56 m2) | 32.3208 | m3 | 120 | 3878.496
R3 | Basin rock D50=500 x 900 deep — C10 inlet/outlet (263.33 m2) | 236.997 | m3 | 110 | 26069.67
Q1 | Bedding stone 5-7 mm — pipe trenches (0.203 T/m x trench metres) | 332 | T | 62 | 20584
Q2 | Bedding stone — culvert extra-over (0.4 T/m x 130.76 m RCBC; zero/negative cover regime) | 52 | T | 62 | 3224 | NewItems #2 priced from long-section cover data.
Q3 | Sundry consumables | 1 | lot | 2500 | 2500
X1 | DETENTION BASIN EARTHWORKS / CONCRETE SPILLWAY — NOT PRICED | 0 | item |  | 0 | ALLOCATION RFI PENDING (Opens #26 + Director; matrix 2.5-x4 assigns basin bulk shaping to earthworks trade). $0 carried. Full spillway build-up + labour/plant held on EBC sheet for reinstatement.
D1 | Freight — Humes (RCP + RCBC + BCC headwalls), est loads | 35 | load | 852 | 29820 | Load count per Humes P04 basis (186 t); confirm at order.
D2 | Freight — Reece (Hauraton + PP + winged headwalls), est loads | 11 | load | 1133.16 | 12464.76 | Re-based from Reece's 25 loads (RCP moved to Humes).
D3 | Freight — Tradelink (PVC/pits) lot | 1 | lot | 4500 | 4500
D4 | Freight — Jaybro headwalls lot | 1 | lot | 1500 | 1500
D5 | Freight — rock cartage | 1 | lot | 5700 | 5700
D6 | Freight — remaining materials | 1 | lot | 3000 | 3000
| Materials subtotal (escalated rates) |  |  |  | 745994.0245
| x1.18 material contingency (Directive 5.4 — materials only; no quote on file embeds contingency) |  |  |  | 134278.9244
| A — MATERIALS TOTAL (escalated + contingent) |  |  |  | 880272.9489
B — LABOUR (crew-days from PROGRAMME_LABOUR_PLANT Phase 7 x FIFO crew day rate; crew = 2 Trades + 1 T/A)
A-01 | Site establishment — TCS own compound, temp services | 3 | crew-day | 2862.4261 | 8587.2783
A-02 | Set-out survey + DBYD / service location | 3 | crew-day | 2862.4261 | 8587.2783
A-03 | RCP375 CL3 mainline incl C09 twin barrels (45 m/day, flat-grade laser penalty) | 16 | crew-day | 2862.4261 | 45798.8176
A-04 | RCP375 CL4 + RCP600 short runs | 1 | crew-day | 2862.4261 | 2862.4261
A-05 | PP collector mains 225/300/375/450/600 — 17 m court bays | 10 | crew-day | 2862.4261 | 28624.261
A-06 | 225 PVC DWV line 81 | 2 | crew-day | 2862.4261 | 5724.8522
A-07 | 100 PVC DWV subsoil outlets / DP laterals | 4 | crew-day | 2862.4261 | 11449.7044
A-08 | Rock extra-over trenching allowance (geotech refusal band; rates tendered separately 7.0-a) | 10 | crew-day | 2862.4261 | 28624.261
A-09 | Testing + CCTV attendance (crew attendance; CCTV subbie in Prelim_OH) | 4 | crew-day | 2862.4261 | 11449.7044
A-10 | As-constructed survey + ADAC XML attendance | 3 | crew-day | 2862.4261 | 8587.2783
A-11 | EDQ-gate remobilisation allowance (Conditions 16/17) | 4 | crew-day | 2862.4261 | 11449.7044
B-01 | RGU inlets x33 install | 22 | crew-day | 2862.4261 | 62973.3742
B-02 | 1050 access chambers x13 | 13 | crew-day | 2862.4261 | 37211.5393
B-03 | 1200 access chambers x4 incl 26-02 upstand formwork | 6 | crew-day | 2862.4261 | 17174.5566
B-04 | 600x600 field inlets x3 | 2 | crew-day | 2862.4261 | 5724.8522
B-05 | Pipe-to-pipe connections x20 | 7 | crew-day | 2862.4261 | 20036.9827
B-06 | Pipe headwalls x10 | 10 | crew-day | 2862.4261 | 28624.261
B-07 | Concrete spillway weir 50 m — HELD AT 0 (allocation RFI pending; 10 cd on EBC sheet) | 0 | crew-day | 2862.4261 | 0
B-08 | Rock pads / beaching 513 m2 | 9 | crew-day | 2862.4261 | 25761.8349
C-01 | C10 RCBC 2700x1200 basin outlet (crane set, shields) | 6 | crew-day | 2862.4261 | 17174.5566
C-02 | Small culverts 600x300/750x300/900x450 (66.4 m) | 9 | crew-day | 2862.4261 | 25761.8349
C-03 | RCBC 1200x600 + 1500x600 (46.8 m) | 8 | crew-day | 2862.4261 | 22899.4088
C-04 | Culvert headwalls x20 incl wingwalls + beaching interface | 16 | crew-day | 2862.4261 | 45798.8176
C-05 | WSUD DN3300 manhole install + 22 StormFilter cartridges (supply = PC Sum) | 8 | crew-day | 2862.4261 | 22899.4088
C-06 | Grated trench drains GT1-GT4 + GT7-GT9 (561.9 m) — REINSTATED incl excavation & quarry | 23 | crew-day | 2862.4261 | 65835.8003
C-07 | Trash Box 200 x25 + 150 DWV laterals (grades to 29.2%) | 13 | crew-day | 2862.4261 | 37211.5393
| B1 — Crew labour subtotal (crew-days / $) | 212 |  |  | 606834.333
A-14 | Leading Hand supervision — site-wide (DIRECT LABOUR per TriCore methodology: old Civ 'SW Zone Sumry' B13/C13/E13 prices TRADESMAN_LEADING HAND as a Day line inside the work-area labour block feeding H11; Hyd master follows the same pattern). 120 LH-days allocated pro-rata to crew-days. | 114.1 | LH-day | 1329.6343 | 151711.272
| B — LABOUR TOTAL (crew labour + LH supervision) |  |  |  | 758545.605 | LH supervision is DIRECT COST here (not a preliminary) — see TCS_CHANGE_LOG.md S9. Prelim_OH retains a $0 traceability row.
C — PLANT (days from Phase 7 roll-up; dry hire unless noted)
| 13-16T excavator | 43 | day | 317.2 | 13639.6
| 8T excavator | 64 | day | 261.17 | 16714.88
| 20-24T excavator | 66 | day | 314.29 | 20743.14
| 3-5T excavator | 56 | day | 238.67 | 13365.52 | 68 total less 5 d (B-07 spillway, on EBC) less 7 d (Stage 1B).
| Hydraulic breaker 13-15T | 10 | day | 203 | 2030
| Trench roller dbl drum remote | 60 | day | 165 | 9900
| Upright rammer / wacker | 70 | day | 34.29 | 2400.3
| <6T tipper truck | 69 | day | 171.43 | 11828.67 | 70 total less 1 d (Stage 1B).
| 50t mobile crane (wet) | 8 | day | 3800 | 30400 | ALLOWANCE — not in hire registers; quote at award.
| Franna / pick-and-carry (wet) | 17 | day | 2200 | 37400 | ALLOWANCE — not in hire registers.
| Trench shields | 14 | day | 120 | 1680 | ALLOWANCE — not in hire registers.
| Vacuum excavator (TPZ/services) | 6 | day | 295.77 | 1774.62
| Water truck (test/flush cartage) | 2 | day | 1100 | 2200 | 3 total less 1 d (Stage 1B).
| Sump pumps / dewatering set | 10 | day | 57 | 570
| Quick-cut / demo saw | 5 | day | 100 | 500
| C — PLANT TOTAL |  |  |  | 165146.73
D — SUBBIES & SERVICES (rates incl x1.15 subbie escalation via Materials_Master)
| Surveyor — set-out (2 d) + as-con pickup (3 d) | 5 | day | 2070 | 10350
| Services locator (live irrigation under ex-fields, geotech S2.0) | 1 | day | 1495 | 1495
| Compaction testing (lots per ITP regime) | 40 | test | 140.3 | 5612
| Geotech entry inspections >1.5 m (WSUD, C10) | 4 | visit | 977.5 | 3910
| Spoil haulage & dump (0.21 m3/m trench + 0.8 m3/m culvert) | 448 | m3 | 46 | 20608 | Formula-driven from trench metres.
| D — SUBBIES TOTAL |  |  |  | 41975
E — ACCOMMODATION & FIFO TRAVEL share (Option A adopted; pro-rata crew-days 1A/(1A+1B))
| Accommodation + flights share — Stage 1A (pro-rata CREW-days, excl. LH supervision days) |  |  |  | 105872.4197
| STAGE 1A — TOTAL COST (materials + labour + plant + subbies + accommodation) |  |  |  | 1951812.7036

## Stage1B_Drainage
STAGE 1B — CIVIL STORMWATER WORK AREA (TCS)
Stage 1B per adopted stage-split basis (VOL 20 SE_12306_SKT_CMP Rev B hatch; RFI to confirm): GT5 + GT6 + lines 60/61/83. 1B priced standalone-viable per Directive 5.2. ALL SUMS EX-GST.
ID | Description | Qty | Unit | Rate | Total | Source / note
A — MATERIALS (adopted qty x source-tagged escalated rate)
P1 | 150 PVC DWV SN8 — lines 60/61/83 (district park / PAM) | 29.6 | m | 50.623 | 1498.4408
G1 | Grated trench GT5 Recyfix PRO100 SS heelguard — multi-use court (Sch 1B 4.2-a interface) | 15.2 | m | 508.1712 | 7724.2022 | Stage split per VOL 20 hatch (RFI).
G2 | Grated trench GT6 Recyfix PRO200 G-tec D400 ductile — amenities bldg (Class D outlier) | 31.4 | m | 387.6282 | 12171.5255 | GT6 spec is PRO100 D400 code 47245; Reece offered PRO200 G-tec — substitution verify (Register Gap #7).
G3 | Hauraton trash boxes TB100 (60-01, 60-03, 61-01, 83-01) | 4 | ea | 295.4856 | 1181.9424
G4 | End caps PRO100 | 4 | ea | 12.9858 | 51.9432
Q1 | Bedding stone 5-7 mm (0.203 T/m) | 6 | T | 62 | 372
D1 | Freight — Reece (GT5/GT6/TB100), est loads | 1 | load | 1133.16 | 1133.16
D2 | Freight — 1B misc deliveries | 1 | lot | 600 | 600
| Materials subtotal (escalated rates) |  |  |  | 24733.2141
| x1.18 material contingency (Directive 5.4 — materials only) |  |  |  | 4451.9785
| A — MATERIALS TOTAL (escalated + contingent) |  |  |  | 29185.1927
B — LABOUR (crew-days from Phase 7)
A-12 | Stage 1B establishment / remobilisation (standalone per 5.2) | 2 | crew-day | 2862.4261 | 5724.8522
A-13 | 1B testing / CCTV attendance / ADAC share | 2 | crew-day | 2862.4261 | 5724.8522
C-08 | GT5 + GT6 trench drains 46.6 m | 3 | crew-day | 2862.4261 | 8587.2783
C-09 | 1B lines 60/61/83 + TB100 x4 + connections | 4 | crew-day | 2862.4261 | 11449.7044
| B1 — Crew labour subtotal (crew-days / $) | 11 |  |  | 31486.6871
A-14 | Leading Hand supervision — 1B share (DIRECT LABOUR per TriCore methodology: old Civ 'SW Zone Sumry' B13). 120 LH-days allocated pro-rata to crew-days. | 5.9 | LH-day | 1329.6343 | 7844.8423
| B — LABOUR TOTAL (crew labour + LH supervision) |  |  |  | 39331.5294
C — PLANT
| 3-5T excavator | 7 | day | 238.67 | 1670.69
| <6T tipper truck | 1 | day | 171.43 | 171.43
| Water truck (test/flush cartage) | 1 | day | 1100 | 1100
| C — PLANT TOTAL |  |  |  | 2942.12
D — SUBBIES & SERVICES (x1.15 via Materials_Master)
| Surveyor — 1B set-out / as-con | 1 | day | 2070 | 2070
| Compaction testing | 4 | test | 140.3 | 561.2
| Spoil haulage & dump | 8 | m3 | 46 | 368
| D — SUBBIES TOTAL |  |  |  | 2999.2
E — ACCOMMODATION & FIFO TRAVEL share (pro-rata CREW-days, excl. LH supervision days)
| Accommodation + flights share — Stage 1B |  |  |  | 5493.3803
| STAGE 1B — TOTAL COST (materials + labour + plant + subbies + accommodation) |  |  |  | 79951.4223

## LabourRates_Master
LABOUR RATES MASTER — FIFO ROSTER (TCS)
Work ROSTER Example #3 - 6-Day Week, 10Hr Days, Stay @ Rocky for W/E, Return Every 2nd W/E. (FLY)
Source: MasterCostSheet_Hyd.V1 'LabourProject Rates_Master' (monthly bases frozen from severed external link [2] CQU ROK_Staff Costing.V1_Steph.xlsx) x 1.08 ROK uplift per Directive 5.4. All ex GST.
Working Days / Month | 21
Avrg Hours / Day | 10
Avrg Hours / Month | 210
ROK uplift factor (Directive 5.4) | 1.08
Classification | Unit basis | Monthly base ($) | Uplifted monthly ($) | Hourly ($/hr) | Day ($/10-hr day) | Week ($/wk) | Source / check
TRADESMAN_LEADING HAND | per month | 25854 | 27922.32 | 132.9634 | 1329.6343 | 6980.58 | Hyd master E17 (was $123.1143/hr) -> x1.08 target $132.9634/hr
TRADESMAN_PLUMBER_OPERATOR (Trades) | per month | 19764.4593 | 21345.616 | 101.6458 | 1016.4579 | 5336.404 | Hyd master E24 (was $94.1165/hr) -> x1.08 target $101.6458/hr
T/A & APPRENTICE | per month | 16129.3667 | 17419.716 | 82.951 | 829.5103 | 4354.929 | Hyd master E31 (was $76.8065/hr) -> x1.08 target $82.9510/hr
CIVIL CREW (2 x Trades + 1 x T/A) — Phase 7 crew convention | per 10-hr day |  |  | 286.2426 | 2862.4261 | 15027.737 | Crew day rate check vs Phase 7 indicative $2,862.43/crew-day
Uplifted hourly rates carried: LH $132.9634 / Trades $101.6458 / T/A $82.9510 (Directive 5.4). Cascade is fully formula-driven: month -> x1.08 -> hour(/210) / day(/21) / week(/4).

## Materials_Master
MATERIALS MASTER — TCS (adopted rates, ex GST)
Every rate carries its source and a per-rate escalation decision. Escalation factors are the CQU-architecture 'april 2026 direct impact Increase % (not contingency)' set, applied ONLY where MATERIAL_QUOTE_REGISTER KeyRates safe-to-multiply flag confirms the rate is not already loaded. All quotes on file are current-price offers with no embedded escalation (Register S3).
Escalation factors (Directive / CQU block J14:M19):
| PE / PVC pipe & fittings |  | 1.38
| Subby rates |  | 1.15
| Delivery / freight |  | 1.2
| Material contingency (Directive 5.4 — materials only, applied on work-area subtotals; never on labour/plant/PC/provisional) |  | 1.18
Code | Item | Unit | Base rate | Source | Factor | Adopted rate | Escalation decision / note
M01 | RCP 375 CL3/CL4 RRJ (priced at Humes Class 4 rate; no CL3 quote on file — conservative) | m | 105 | Humes Q21642316 REV2 ($256.20/2.44 m eff.) | 1 | 105 | Concrete/precast: no directed category factor (not PE/PVC/subbie/delivery); 2027 escalation risk carried inside x1.18 material contingency + re-quote condition at award. Humes 299 vs Reece 262 take-off discrepancy noted — our adopted 714.9 m governs.
M02 | 375 rubber ring | ea | 4.8 | Humes Q21642316 REV2 | 1 | 4.8 | Concrete/precast: no directed category factor (not PE/PVC/subbie/delivery); 2027 escalation risk carried inside x1.18 material contingency + re-quote condition at award.
M03 | RCP 600 CL3 RRJ | m | 183.5656 | Humes Q21642316 REV2 ($447.90/2.44 m) | 1 | 183.5656 | Concrete/precast: no directed category factor (not PE/PVC/subbie/delivery); 2027 escalation risk carried inside x1.18 material contingency + re-quote condition at award.
M04 | 600 rubber ring (allowance) | ea | 24 | Old Civ workbook rate (benchmark) | 1 | 24 | Benchmark-derived; minor value.
M05 | 225 PP Stormpro SN8 (or equal) | m | 36.0768 | Reece Q-459014445 ($216.10/5.99 m) | 1.38 | 49.786 | PP priced (drawings label PP; 'HDPE PN100' not a real class — Opens #5). Atlan HDPE cheaper but day-of-issue validity + spec acceptance unconfirmed — NOT adopted. KeyRates safe-flag Y -> x1.38 PE family.
M06 | 300 PP Stormpro SN8 | m | 60 | DERIVED — interpolated Reece Stormpro curve (225=$36.08/m, 375=$92.01/m) | 1.38 | 82.8 | Benchmark-derived (no 300 rate quoted); re-quote at award. x1.38 PE family.
M07 | 375 PP Stormpro SN8 | m | 92.0101 | Reece Q-459014445 ($545.62/5.93 m) | 1.38 | 126.974 | KeyRates safe-flag Y -> x1.38 PE family.
M08 | 450 PP Stormpro SN8 | m | 135 | DERIVED — interpolated Reece Stormpro curve (375=$92.01/m, 600=$226.03/m) | 1.38 | 186.3 | Benchmark-derived (no 450 rate quoted); re-quote at award. x1.38 PE family.
M09 | 600 PP Stormpro SN8 | m | 226.0342 | Reece Q-459014445 ($1,322.30/5.85 m) | 1.38 | 311.9272 | KeyRates safe-flag Y -> x1.38 PE family.
M10 | 225 PVC DWV SN8 SWJ | m | 129.4167 | Tradelink 1065005 R1 ($776.50/6 m) | 1.38 | 178.595 | KeyRates safe-flag Y -> x1.38 PVC. Tradelink freight is a separate lot line (M56) — rate not freight-loaded.
M11 | 150 PVC DWV SN8 SWJ | m | 36.6833 | Tradelink 1065005 R1 ($220.10/6 m) | 1.38 | 50.623 | As M10.
M12 | 100 PVC DWV SN6 SWJ | m | 7.1783 | Reece Q-459014445 ($43.07/6 m) | 1.38 | 9.9061 | KeyRates safe-flag Y -> x1.38 PVC.
M13 | 100 PVC 90 deg bend | ea | 3.5 | Old Civ workbook rate (benchmark — no current quote) | 1.38 | 4.83 | Benchmark-derived; x1.38 PVC; re-quote at award.
M14 | 100 PVC 45 deg bend | ea | 3.5 | Old Civ workbook rate (benchmark) | 1.38 | 4.83 | As M13.
M15 | 225 PVC 90 deg bend | ea | 23.5 | Old Civ workbook rate (benchmark) | 1.38 | 32.43 | As M13.
M16 | 100 PVC 45 deg junction | ea | 10 | Old Civ workbook rate (benchmark) | 1.38 | 13.8 | As M13.
M17 | 225 PVC 45 deg junction | ea | 60.1 | Old Civ workbook rate (benchmark) | 1.38 | 82.938 | As M13.
M18 | 225x100 PVC 45 deg junction | ea | 38.55 | Old Civ workbook rate (benchmark) | 1.38 | 53.199 | As M13.
M19 | Inspection opening c/w galvanised cover flush with surface | ea | 150 | Old Civ workbook rate (benchmark) | 1.38 | 207 | PVC assembly — x1.38; re-quote at award.
M20 | Pipe-to-pipe / pipe-to-culvert connection materials (couplers, epoxy, mortar) | ea | 310 | Old Civ workbook rates $150-600 (benchmark allowance) | 1 | 310 | Connection allowance, not a supplier rate — factor 1.00; escalation risk inside x1.18 contingency.
M21 | Jointing lubricant 1L | ea | 17 | Old Civ workbook rate (benchmark) | 1 | 17 | Minor consumable.
M22 | RCBC 600x300 crown unit (2.4 m) | ea | 1095 | Humes Q21642316 REV2 (vs Reece $1,136.36 — Humes adopted) | 1 | 1095 | Concrete/precast: no directed category factor (not PE/PVC/subbie/delivery); 2027 escalation risk carried inside x1.18 material contingency + re-quote condition at award.
M23 | RCBC 750x300 crown unit (2.4 m) | ea | 1171.2 | Humes Q21642316 REV2 (vs Reece $1,330.91) | 1 | 1171.2 | Concrete/precast: no directed category factor (not PE/PVC/subbie/delivery); 2027 escalation risk carried inside x1.18 material contingency + re-quote condition at award.
M24 | RCBC 900x450 crown unit (2.4 m) | ea | 1404.8 | Humes Q21642316 REV2 (vs Reece $1,599.77) | 1 | 1404.8 | Concrete/precast: no directed category factor (not PE/PVC/subbie/delivery); 2027 escalation risk carried inside x1.18 material contingency + re-quote condition at award.
M25 | RCBC 1200x600 crown unit (2.4 m) | ea | 1718.4 | Humes Q21642316 REV2 | 1 | 1718.4 | Concrete/precast: no directed category factor (not PE/PVC/subbie/delivery); 2027 escalation risk carried inside x1.18 material contingency + re-quote condition at award.
M26 | Large box culvert 1500x600 (2.4 m) AS1597.2 | ea | 3065.72 | Humes Q21642316 REV2 (vs Reece $3,483.77; Humes qty 13 vs Reece 8 — our 29.04 m governs) | 1 | 3065.72 | Concrete/precast: no directed category factor (not PE/PVC/subbie/delivery); 2027 escalation risk carried inside x1.18 material contingency + re-quote condition at award.
M27 | Large box culvert 2700x1200 (2.4 m) AS1597.2 | ea | 5891.95 | Humes Q21642316 REV2 (vs Reece $6,797.67) | 1 | 5891.95 | Concrete/precast: no directed category factor (not PE/PVC/subbie/delivery); 2027 escalation risk carried inside x1.18 material contingency + re-quote condition at award.
M28 | Headwall to suit 375 RCP (winged) | ea | 317.05 | Reece Q-459014445 (vs Humes $380.80 / Jaybro $372+freight — Reece adopted) | 1 | 317.05 | Concrete/precast: no directed category factor (not PE/PVC/subbie/delivery); 2027 escalation risk carried inside x1.18 material contingency + re-quote condition at award.
M29 | Headwall to suit 2x375 RCP twin cell | ea | 588.8 | Humes Q21642316 REV2 (vs Jaybro $1,670 — Humes adopted) | 1 | 588.8 | Concrete/precast: no directed category factor (not PE/PVC/subbie/delivery); 2027 escalation risk carried inside x1.18 material contingency + re-quote condition at award.
M30 | Headwall to suit 150 PVC | ea | 158 | Jaybro email 16/07/26 (freight excluded — carried at M57) | 1 | 158 | Concrete/precast: no directed category factor (not PE/PVC/subbie/delivery); 2027 escalation risk carried inside x1.18 material contingency + re-quote condition at award.
M31 | Headwall to suit 225 PVC | ea | 280 | Jaybro email 16/07/26 (freight excluded — M57) | 1 | 280 | Concrete/precast: no directed category factor (not PE/PVC/subbie/delivery); 2027 escalation risk carried inside x1.18 material contingency + re-quote condition at award.
M32 | Headwall to suit 300 PP/HDPE | ea | 352 | Jaybro email 16/07/26 (freight excluded — M57) | 1 | 352 | Concrete/precast: no directed category factor (not PE/PVC/subbie/delivery); 2027 escalation risk carried inside x1.18 material contingency + re-quote condition at award.
M33 | BCC headwall 600x300 | ea | 1800.63 | Humes Q21642316 REV2 (Jaybro declined all RCBC headwalls) | 1 | 1800.63 | Concrete/precast: no directed category factor (not PE/PVC/subbie/delivery); 2027 escalation risk carried inside x1.18 material contingency + re-quote condition at award.
M34 | BCC headwall 750x300 | ea | 2162.6 | Humes Q21642316 REV2 | 1 | 2162.6 | Concrete/precast: no directed category factor (not PE/PVC/subbie/delivery); 2027 escalation risk carried inside x1.18 material contingency + re-quote condition at award.
M35 | BCC headwall 900x450 | ea | 2425.63 | Humes Q21642316 REV2 | 1 | 2425.63 | Concrete/precast: no directed category factor (not PE/PVC/subbie/delivery); 2027 escalation risk carried inside x1.18 material contingency + re-quote condition at award.
M36 | BCC headwall 1200x600 | ea | 3322.45 | Humes Q21642316 REV2 | 1 | 3322.45 | Concrete/precast: no directed category factor (not PE/PVC/subbie/delivery); 2027 escalation risk carried inside x1.18 material contingency + re-quote condition at award.
M37 | BCC headwall 1500x600 | ea | 4222.78 | Humes Q21642316 REV2 | 1 | 4222.78 | Concrete/precast: no directed category factor (not PE/PVC/subbie/delivery); 2027 escalation risk carried inside x1.18 material contingency + re-quote condition at award.
M38 | BCC headwall 2700x1200 | ea | 5241.45 | Humes Q21642316 REV2 | 1 | 5241.45 | Concrete/precast: no directed category factor (not PE/PVC/subbie/delivery); 2027 escalation risk carried inside x1.18 material contingency + re-quote condition at award.
M39 | RGU inlet unit 2.4 m lintel (CMDG-D-020) supply set | ea | 1350 | Old Civ workbook allowance (benchmark — NO current RGU quote: sourcing gap) | 1 | 1350 | Benchmark-derived; RGU/lintel package to be quoted at award. Escalation inside contingency.
M40 | 1050 dia precast chamber shaft x900 (CMDG-D-030) | ea | 364 | Old Civ workbook rate (Humes-era benchmark) | 1 | 364 | Concrete/precast: no directed category factor (not PE/PVC/subbie/delivery); 2027 escalation risk carried inside x1.18 material contingency + re-quote condition at award.
M41 | Aspro cover slab 1050x1350 (600x900 hole) | ea | 400 | Old Civ workbook rate (benchmark) | 1 | 400 | Concrete/precast: no directed category factor (not PE/PVC/subbie/delivery); 2027 escalation risk carried inside x1.18 material contingency + re-quote condition at award.
M42 | 1200x900 precast chamber shaft | ea | 1101 | Old Civ workbook rate (benchmark) | 1 | 1101 | Concrete/precast: no directed category factor (not PE/PVC/subbie/delivery); 2027 escalation risk carried inside x1.18 material contingency + re-quote condition at award.
M43 | 1200x1200 precast chamber shaft | ea | 1403 | Old Civ workbook rate (benchmark) | 1 | 1403 | Concrete/precast: no directed category factor (not PE/PVC/subbie/delivery); 2027 escalation risk carried inside x1.18 material contingency + re-quote condition at award.
M44 | Aspro cover slab 1200x1650 (600x900 hole) | ea | 400 | Old Civ workbook rate (benchmark) | 1 | 400 | Concrete/precast: no directed category factor (not PE/PVC/subbie/delivery); 2027 escalation risk carried inside x1.18 material contingency + re-quote condition at award.
M45 | Grate & frame 600x900 Class D galv | ea | 298 | Old Civ workbook rate (benchmark; cf Tradelink 600 sq $365.20) | 1 | 298 | Concrete/precast: no directed category factor (not PE/PVC/subbie/delivery); 2027 escalation risk carried inside x1.18 material contingency + re-quote condition at award.
M46 | 600x600x600 HD concrete pit (80 wall) | ea | 229.5 | Tradelink 1065005 R1 (re-sourced from old $168 allowance) | 1 | 229.5 | Concrete/precast: no directed category factor (not PE/PVC/subbie/delivery); 2027 escalation risk carried inside x1.18 material contingency + re-quote condition at award.
M47 | 600x600 Class D grate & frame (HD) | ea | 365.2 | Tradelink 1065005 R1 (re-sourced from old $195) | 1 | 365.2 | Concrete/precast: no directed category factor (not PE/PVC/subbie/delivery); 2027 escalation risk carried inside x1.18 material contingency + re-quote condition at award.
M48 | Hauraton Recyfix PRO200 T010 + Fibretec slotted grate B125 (47246) | m | 232.94 | Reece Q-459014445 lines 21-28 (embedded '$198.00' negotiated-rate anomaly — confirm with Reece; delta $19,217) | 1.38 | 321.4572 | Recyfix = recycled PE-PP channel; KeyRates x1.38 safe-flag Y -> PE family factor applied.
M49 | Hauraton Recyfix PRO100 T010 + SS304 heelguard grate, 200 deep | m | 368.24 | Reece Q-459014445 | 1.38 | 508.1712 | As M48.
M50 | Hauraton Recyfix PRO200 T010 + G-tec ductile iron grate Cl D400 | m | 280.89 | Reece Q-459014445 (GT6 spec is PRO100 D400 G-tec code 47245 — substitution to be verified, Register Gap #7) | 1.38 | 387.6282 | As M48; GT6 substitution flag carried.
M51 | Hauraton trash box PRO200 c/w galv mud bucket + Fibretec grate | ea | 535.29 | Reece Q-459014445 | 1.38 | 738.7002 | As M48.
M52 | Hauraton trash box PRO100 c/w PE mud bucket + Fibretec grate | ea | 214.12 | Reece Q-459014445 | 1.38 | 295.4856 | As M48.
M53 | End cap PRO/NC200 T010 c/w DN100 PVC outlet | ea | 23.53 | Reece Q-459014445 | 1.38 | 32.4714 | As M48.
M54 | End cap closed PRO100 T010 200 deep | ea | 9.41 | Reece Q-459014445 | 1.38 | 12.9858 | As M48.
M55 | Freight — Humes concrete to site FOT <24 km (customer to unload) | load | 710 | Humes Q21642316 REV2 (35 loads inside their total; unload/cranage by others — crane carried in plant) | 1.2 | 852 | Delivery x1.20 (KeyRates: escalation needed once; freight not already in item rates).
M56 | Freight — Reece concrete/Hauraton (customer to unload) | load | 944.3 | Reece Q-459014445 | 1.2 | 1133.16 | As M55. Load count re-based to our split-supplier scope (RCP moved to Humes).
M57 | Freight — Tradelink supplier freight/handling | lot | 3750 | Tradelink 1065005 R1 (SF line inside their total) | 1.2 | 4500 | Applied once — do not add again on Tradelink items.
M58 | Freight — Jaybro regional lot to Rockhampton | lot | 1250 | Jaybro 20043160 benchmark ('No allowance for freight' on email rates) | 1.2 | 1500 | Adder required once for Jaybro headwalls.
M59 | Freight — rock cartage (kerb/headwall/basin rock) | lot | 4750 | Old Civ workbook freight rows $500+$4,250 (benchmark) | 1.2 | 5700 | Benchmark-derived.
M60 | Freight — remaining materials / smalls | lot | 2500 | Old Civ workbook allowance (benchmark) | 1.2 | 3000 | Benchmark-derived.
M61 | Freight — Stage 1B misc deliveries | lot | 500 | Estimator allowance (1B standalone viability per 5.2) | 1.2 | 600 | Benchmark-derived.
M62 | Bedding stone 5-7 mm | T | 62 | Old Civ TCS quarry rate table (benchmark; re-quote at award) | 1 | 62 | Quarry supply — no directed factor; escalation inside contingency. Cartage in M59/M60.
M63 | Rock beaching D50=200-500 (headwall/basin pads) | m3 | 110 | Old Civ workbook rate (benchmark) | 1 | 110 | Concrete/precast: no directed category factor (not PE/PVC/subbie/delivery); 2027 escalation risk carried inside x1.18 material contingency + re-quote condition at award.
M64 | Rock beaching d50=100, 180 thick | m3 | 120 | Old Civ workbook rate (benchmark) | 1 | 120 | Concrete/precast: no directed category factor (not PE/PVC/subbie/delivery); 2027 escalation risk carried inside x1.18 material contingency + re-quote condition at award.
M65 | Concrete 32 MPa (spillway/surrounds) | m3 | 400 | Old Civ workbook rate table E362 (benchmark) | 1 | 400 | Concrete/precast: no directed category factor (not PE/PVC/subbie/delivery); 2027 escalation risk carried inside x1.18 material contingency + re-quote condition at award.
M66 | SL72 mesh sheet | sheet | 85 | Estimator benchmark | 1 | 85 | Benchmark-derived.
M67 | Type 2.3 sub-base | T | 48 | Old Civ CBR15 rate (benchmark) | 1 | 48 | Benchmark-derived.
M68 | Sundry consumables (marker tape, glue, primer, couplers, concrete bags, geofabric) | lot | 2500 | Old Civ workbook consumable rows (benchmark roll-up) | 1 | 2500 | Benchmark-derived.
M69 | Kerb chute structure materials (concrete invert, kerb returns, R1000) per chute | ea | 850 | Estimator build-up from F1325 detail (benchmark) | 1 | 850 | EBC item — Director decision D6-F1.
M70 | Erosion control matting | m2 | 7 | Old Civ workbook rate (benchmark) | 1 | 7 | EBC item (kerb chutes).
M71 | Kerb chute rock DIA 100, 180 thick | m3 | 150 | Old Civ workbook rate (benchmark) | 1 | 150 | EBC item (kerb chutes).
M72 | CCTV of drainage (independent approved firm) per metre | m | 5 | Benchmark-derived (VOL38 3.56 obligation; old Civ $1,680/zone) | 1.15 | 5.75 | Subbie x1.15.
M73 | Surveyor (set-out / as-con pickup) | day | 1800 | Phase 7 rate $180/hr x 10 hr | 1.15 | 2070 | Subbie x1.15.
M74 | Services locator | day | 1300 | Phase 7 rate $130/hr x 10 hr | 1.15 | 1495 | Subbie x1.15.
M75 | Compaction testing per test | test | 122 | Old Civ register rate (benchmark) | 1.15 | 140.3 | Subbie x1.15.
M76 | Geotech entry inspection (>1.5 m excavations) per visit | visit | 850 | Estimator benchmark (NQL2024-0320 5.3.3 obligation) | 1.15 | 977.5 | Subbie x1.15.
M77 | Spoil haulage & dump | m3 | 40 | Old Civ workbook rate L330 (benchmark) | 1.15 | 46 | Cartage service x1.15 (not a material — excluded from x1.18 contingency by placement in Subbies block).

## Equip_Master
EQUIPMENT / HIRE MASTER — TCS
Adopted plant day rates (dry hire unless noted). Source register header says WEEKLY (5-day) but unit column says Day — treated as $/day (conservative), flagged for confirmation (Phase 7 flag carried).
Item | Unit | Rate ex GST | Source | In hire register? | Note
13-16T excavator | day | 317.2 | Hyd Equip&HIRE_Master | Y | Mainline / PP / DWV trenching
8T excavator | day | 261.17 | Hyd Equip&HIRE_Master | Y | Crew B pits / structures
20-24T excavator | day | 314.29 | Hyd Equip&HIRE_Master | Y | Culverts, WSUD, rock band
3-5T excavator | day | 238.67 | Hyd Equip&HIRE_Master | Y | GT drains, trash boxes, laterals, rock pads
Hydraulic breaker 13-15T | day | 203 | Hyd Equip&HIRE_Master | Y | Rock extra-over band only
Trench roller dbl drum remote | day | 165 | Hyd Equip&HIRE_Master | Y
Upright rammer / wacker | day | 34.29 | Hyd Equip&HIRE_Master | Y
<6T tipper truck | day | 171.43 | Hyd Equip&HIRE_Master | Y
Vacuum excavator (TPZ/services) | day | 295.77 | Hyd Equip&HIRE_Master | Y | VFMP water excavation in NRZs (arborist supervised)
Sump pumps / dewatering set | day | 57 | Hyd Equip&HIRE_Master (flexdrive set) | Y | Wet-season seepage per geotech S4.2
Water truck (test/flush cartage) | day | 1100 | Misc Subbie Rates $110/hr wet x 10 hr | Y | No site water — ITT S17.3
50t mobile crane (wet) | day | 3800 | ALLOWANCE — quote at award | N — FLAG: NOT IN HIRE REGISTERS | C10 RCBC 2700x1200 + WSUD DN3300 sets
Franna / pick-and-carry (wet) | day | 2200 | ALLOWANCE — quote at award | N — FLAG: NOT IN HIRE REGISTERS | Culvert crown units
Trench shields | day | 120 | ALLOWANCE — quote at award | N — FLAG: NOT IN HIRE REGISTERS | WSUD + C10 + entered runs >1.5 m per geotech 5.3.3
Quick-cut / demo saw | day | 100 | Benchmark (Civ register $100/wk Coates line — treated /day) | Y (weekly basis) | GT drain cutting
PE butt/electrofusion welder | day | 0 | NOT REQUIRED — TCS scope has no PE pressure welding (rising main = TPS) | N — FLAG: ABSENT FROM ALL REGISTERS | Flagged per rebuild direction; if scope changes, quote at award
REFERENCE — MIGRATED FROM MasterCostSheet_Civ.V1 'Equip&HIRE' (weekly 5-day rates, all qty=0 in old model; retained for comparison only — NOT used in pricing)
Description |  | TCS wkly | CAT (ROK) wkly | COATES wkly | ONSITE wkly
Skid Steer Loader_Tracked |  | 0 | 0 | 0 | 262
Skid Steer Loader_Wheeled |  | 300 | 250 | 192 | 0
4.5-6Ton_Excavator |  | 200 | 0 | 0 | 0
8Ton_Excavator |  | 250 | 0 | 0 | 0
10-12Ton_Excavator |  | 310 | 310 | 301 | 300
14-16Ton_Excavator |  | 440 | 370 | 375 | 295
20-24Ton_Excavator |  | 450 | 480 | 417 | 444
Ripper_10-12T |  | 26 | 0 | 25.7 | 0
Ripper_14-16T |  | 26 | 0 | 25.7 | 21
Ripper_20-24T |  | 30 | 0 | 30.1 | 23
Auger Drive_10-12T |  | 115 | 0 | 0 | 0
300Dia Auger Drill |  | 50 | 0 | 0 | 0
2-4T_Tipper Truck |  | 180 | 0 | 180 | 130
6-12T_Tipper Truck |  | 400 | 0 | 238 | 0
<10T_Articulated Site Tipper |  | 341 | 0 | 243 | 0
Upright Rammer_Wacker |  | 50 | 0 | 48 | 46
Trench Roller_Dbl Drum_Remote |  | 180 | 0 | 121 | 98
<26Ft_Scissor Lift - Diesel |  | 150 | 0 | 89 | 112
<34Ft_Boom Lift - Diesel |  | 150 | 0 | 96 | 140
Porta Loo_No Tank |  | 5 | 0 | 5 | 7.5
3.6*3m Demountable Office |  | 0 | 0 | 15 | 13
20Ft Shipping Container |  | 5 | 0 | 4 | 0
Quick Cut Demo Saw |  | 0 | 0 | 100 | 50
Sngl Ph_6KVA Genset |  | 50 | 0 | 45 | 35
Diesel Air Compressor_Trailer |  | 0 | 0 | 73 | 68
Air Breaker - Heavy |  | 0 | 0 | 34 | 0
Air Hose <10m |  | 0 | 0 | 9 | 1.2
Elec Breaker/Jackhammer |  | 0 | 0 | 45 | 0
Flexdrive Motor Unit |  | 0 | 0 | 25 | 27
Flexdrive_Pump Shaft |  | 0 | 0 | 30 | 22
Temporary Power Board |  | 25 | 0 | 30 | 17
Dual CabUte |  | 125 | 0 | 0 | 0
10m3_Skip Bin |  | 40 | 0 | 0 | 0
Vac Truck / HR |  | 200 | 0 | 0 | 0
TRANSPORT_Ex ROK - Return (22T) |  | 0 | 0 | 480 | 0

## Accommodation
ACCOMMODATION & FIFO TRAVEL — TCS
Basis: Roster Example #3 — 6-day week, 10-hr days, stay Rockhampton weekends, fly home every 2nd weekend. 21 work-days / 210 hrs per month. Rates ex GST from Accomodation_Master (Hyd). No shared accommodation between entities (Directive 5.2).
Full apartment/townhouse via agent (houses crew of 3), per month | 4606.06 | Accomodation_Master E308 ex GST
Individual private unit, nightly | 103.2468 | Accomodation_Master F364 ex GST
Nights per person-month (approx 5 nights home / month on 2nd-weekend fly-back) | 25
Flight one-way (Qantas, no checked luggage) ex GST | 200 | Misc Subbie Rates_Master: $220 incl GST -> $200 ex GST
Return flights per person-month (fly home every 2nd weekend) | 2
Month | Persons on site (incl LH) | Apartments (3/apt) | Apartment cost | Individual nights | Individual cost
M1 (A+B+C+LH) | 10 | 3 | 13818.18 | 250 | 25811.7
M2 (A+B+C+LH) | 10 | 3 | 13818.18 | 250 | 25811.7
M3 (B+C+LH) | 7 | 2 | 9212.12 | 175 | 18068.19
M4 (B+LH) | 4 | 1 | 4606.06 | 100 | 10324.68
M5 (B+C+LH) | 7 | 2 | 9212.12 | 175 | 18068.19
M6 (A+C+LH) | 7 | 2 | 9212.12 | 175 | 18068.19
TOTAL (6 months) | 45 | 13 | 59878.78 | 1125 | 116152.65
LH individual nights (Option A: LH on nightly individual, 6 months x 25 nights) | 150 |  | 15487.02
OPTION A — apartments (crews) + LH individual [ADOPTED] |  |  | 75365.8
OPTION B — all individual nightly (shown for comparison; NOT adopted) |  |  | 116152.65
Option B premium vs Option A |  |  | 40786.85
FIFO return flights (person-months x returns/month x 2 legs x one-way rate) |  |  | 36000
TOTAL ACCOMMODATION + FIFO TRAVEL (Option A, adopted) — carried to work-area cost pro-rata crew-days |  |  | 111365.8

## Prelim_OH
PRELIMINARIES & OVERHEAD — BOTTOM-UP CROSS-CHECK (TCS)
The sell carries Prelims 5.5% + OH 18% + Profit 18%, EACH calculated ON TOTAL COST per Directive 5.4 (no compounding). This sheet builds TRUE PRELIMINARIES bottom-up and cross-checks the 5.5% allowance. Items here are NOT added to the sell — they are funded from the 5.5% pool. Leading Hand supervision is NOT a preliminary: per TriCore methodology it is DIRECT LABOUR and is priced in the Stage 1A/1B labour blocks (row retained below at $0 for traceability). All ex GST.
Item | Qty | Unit | Rate | Total | Basis / note
LH SUPERVISION
Leading Hand supervision (site-wide, both stages) — REALLOCATED TO DIRECT LABOUR | 0 | day | 1329.6343 | 0 | REALLOCATED to direct labour per TriCore methodology (old Civ 'SW Zone Sumry' B13 prices TRADESMAN_LEADING HAND as a Day line inside the work-area labour block) — see TCS_CHANGE_LOG.md S9. Row retained at ZERO for traceability; the 120 LH-days are priced at Stage1A_Drainage A-14 and Stage1B_Drainage A-14. Rate shown for reference.
ESTABLISHMENT (non-labour; establishment crew-days are in Stage1A/1B labour A-01/A-12)
Compound set-up: fencing, gates, signage, rumble grid/washdown (VFMP) | 1 | lot | 4500 | 4500 | Estimator allowance — VFMP washdown compliance.
20 ft container / site storage | 6 | month | 150 | 900 | Benchmark (register weekly rates implausibly low — flagged).
Site admin, stationery, Greenstar admin | 6 | month | 1600 | 9600 | Old Civ Prelim rate $1,600/mo.
Site PPE | 6 | month | 400 | 2400 | Old Civ Prelim rate.
Site consumables — paint, tapes etc | 6 | month | 180 | 1080 | Old Civ Prelim rate.
Site management — bollards, pickets, barrier mesh | 6 | month | 400 | 2400 | Old Civ Prelim rate.
Dual cab ute | 6 | month | 541 | 3246 | Civ Equip&HIRE $125/wk x 4.33.
10 m3 skip bin + waste | 6 | month | 600 | 3600 | Benchmark incl exchanges (spoil stays on site per Add 2 — general waste only).
TEMPORARY SERVICES — TCS OWN SHARE (locked Split; nothing shared, ITT S17.3: no site power or water)
Portable toilets + wash station (2 no.) | 26 | week | 120 | 3120 | Benchmark 2 x $60/wk.
6 KVA genset + fuel | 26 | week | 130 | 3380 | Civ register $50/wk + fuel allowance.
Temporary potable water storage + CARTAGE (no site water) | 1 | lot | 6000 | 6000 | Estimator allowance — ITT S17.3; incl temp water cartage for amenities/testing top-up.
Temporary power boards / leads | 26 | week | 25 | 650 | Civ register rate.
EDQ GATE
EDQ-gate remobilisation — plant float 2 loads | 2 | load | 800 | 1600 | RPT006_B S3.1 Conditions 16/17; $200/hr x 4 hr/load. Crew remobilisation 4 crew-days carried in Stage1A labour A-11 (not here — no double count).
QA DELIVERABLES — ADAC / CCTV / AS-CONSTRUCTED
CCTV of all TCS in-ground drainage (independent approved firm, Superintendent present) | 1667 | m | 5.75 | 9585.25 | VOL38 3.56; qty = 1A + 1B pipe metres (formula); rate x1.15 subbie.
ADAC XML preparation + validation (TCS stormwater assets) | 1 | lot | 4500 | 4500 | ITT S19 / CMDG ADAC deliverable — estimator allowance.
RPEQ certification + as-constructed drawing preparation | 1 | lot | 3500 | 3500 | Estimator allowance; surveyor pickup attendance already in Stage subbies.
Drainage clean / pre-PC de-silt (S24) | 1 | lot | 2500 | 2500 | Estimator allowance.
BOTTOM-UP PRELIMS TOTAL |  |  |  | 62561.25
5.5% PRELIMS ALLOWANCE (as carried in the sell = 5.5% x total cost 1A+1B) |  |  |  | 111747.0269
CROSS-CHECK — variance (allowance less bottom-up; negative = allowance shortfall) |  |  |  | 49185.7769
Variance % (bottom-up vs allowance) |  |  |  | -44.02%
OVERHEAD CROSS-CHECK
OH 18% x total cost (as carried in the sell) |  |  |  | 365717.5427
TriCore overheads benchmark — $20,000/month x 6 months (old Civ Prelim_OH-Check rate) | 6 | month | 20000 | 120000
OH margin vs benchmark |  |  |  | 245717.5427

## EBC
EBC — EXCLUDED-BUT-COSTED / DIRECTOR-PENDING REGISTER (TCS)
Add-prices computed at the same commercial basis as the base model (escalated rates, x1.18 on materials, 41.5% on cost). Reinstatement cell references given per item. ALL EX-GST.
Item | Qty | Unit | Rate | Total | Note
E1 — KERB CHUTES x9 — 'Director decision D6-F1' (BOTH POSITIONS CARRIED — do not close either way)
Position 1 (BASE, as modelled): kerb chutes EXCLUDED entirely per Denis 24-Jul email — base lump sums carry $0.
Position 2 (ADD-PRICE): 9 chutes (03-02, 03-03, 04-02, 13-02 to 18-02 per F1310/F1325) + rock + erosion matting:
Kerb chute structure materials (concrete invert, kerb returns, R1000) | 9 | ea | 850 | 7650
Kerb chute rock DIA 100 x 180 thick (55.67 m2 x 0.18) | 10.0206 | m3 | 150 | 1503.09
Erosion control matting | 56 | m2 | 7 | 392
Materials subtotal x1.18 contingency |  |  |  | 11263.2062
Labour B-09 — 9 crew-days (Phase 7 EBC) | 9 | crew-day | 2862.4261 | 25761.8349
Plant — 3-5T excavator 9 days | 9 | day | 238.67 | 2148.03
KERB CHUTES ADD-PRICE (cost x 1.415) |  |  |  | 55429.8956 | Reinstatement: add labour row B-09 (9 crew-days) to Stage1A_Drainage labour block; add the three material rows above to the Stage 1A materials block; add 9 plant-days to the 3-5T excavator line.
E2 — DETENTION BASIN EARTHWORKS + CONCRETE SPILLWAY — ALLOCATION RFI PENDING (Opens #26; Director)
Base carries $0 (Stage1A_Drainage row X1 and labour B-07 held at 0). Spillway build-up below for reinstatement if allocated to TCS; basin bulk earthworks NOT QUANTIFIED anywhere (F1305 annotation only) — cannot be priced, RFI.
Spillway concrete 25 MPa, 125 thk x 50 m weir + 1.5 m aprons (F1323 build-up) | 10.3 | m3 | 400 | 4120
SL72 mesh central | 12 | sheet | 85 | 1020
Type 2.3 sub-base 75 mm | 13 | T | 48 | 624
Materials subtotal x1.18 contingency |  |  |  | 6801.52
Labour B-07 — 10 crew-days (5 m/day, L-confidence) | 10 | crew-day | 2862.4261 | 28624.261
Plant — 3-5T excavator 5 days + concrete gear allowance | 5 | day | 338.67 | 1693.35
SPILLWAY ADD-PRICE IF ALLOCATED TO TCS (cost x 1.415) |  |  |  | 52523.5704 | Reinstatement: set Stage1A_Drainage labour B-07 = 10 cd; enter spillway material rows at X1; add 5 plant-days 3-5T.
E3 — RECORDS (excluded / relocated items — nothing lost silently)
Grated trench drains (GT1-9, trash boxes, excavation & quarry) — REINSTATED into base (1A 3.5 / 1B 2.3-a). Old workbook computed $164,860.30 in an orphaned column (K258) that never reached the old total. |  |  |  | REINSTATED — in base
100 mm subsoil / type 2 strip-filter drainage, 2,172.4 m — EXCLUDED 'by others' (locked 5.3; matrix 2.3-x2/2.5-x3). Old workbook carried $10,865 in orphaned cells J269 (never in total). Interface: strip-filter connections at TCS collector pits only. |  |  |  | EXCLUDED — E+Q
Sewer rising main Ø100/DN110 (110 m allowance) — TPS scope (matrix 2.1-x2 EBC in TPS model), NOT in TCS. |  |  |  | NOT TCS
Sewer pump station QMax Fortis — EXCLUDED per Addendum 2 (Council installs); TPS interface ledger item, NOT TCS. |  |  |  | NOT TCS
$20,000 provisional connection fees (Sch 1A 5.0 / 1B 4.6) — TPS side, carried as directed in TPS model, NOT in TCS. |  |  |  | NOT TCS
WSUD supply basis — old Atlan $88,838 'high level estimate' (day-of-issue validity) SUPERSEDED by Reece Q-459014431 line $90,064.63 + $7,142.10 freight as PC Sum +15% (RPT006_B 7.4 nomination). |  |  |  | SUPERSEDED — PC

## Sched3_Extract
SCHED3_EXTRACT — PAYNTERS TENDER SCHEDULE 3 LINE STRUCTURE WITH TCS PRICES (D5)
Exact Schedule 3 1A/1B structure (schedule3_transcript.md rows cited) for direct transfer. Only TCS lines carry prices; other-trade lines shown as headers only. ALL EX-GST.
1A | R5 | 1.0 | Preliminaries & Documentation (1.1-1.7) |  |  |  | TCS's own establishment/TC/ESC/plans/set-out/QA-ADAC/PM are inside the lump sum rates below (Split per matrix 1.1-1.7); enter at section level only if Paynters direct.
1A | R15 | 2.0 | Site Works
1A | R33 | 2.3 | Road and Carpark — Drainage, retaining structures and protective treatments |  |  |  | TCS prices the DRAINAGE COMPONENT ONLY; mapped into 2.5 Stormwater drainage below under the single-pricing control (each F13xx line ID priced once — matrix 2.3-a). Retaining/protective treatments NOT TCS.
1A | R49 | 2.5 | Drainage
1A | R50 |  | Stormwater drainage | Item | 1 | 2204088.4794 | 1A lump sum less GT component (GT carried at 3.5). Includes 2.3-a drainage component, culverts, headwalls, pits, WSUD INSTALLATION, rock protection.
1A | R51 |  | Retention Basin |  |  |  | Outlet structures (C10, spillway interface, rock pads) included in Stormwater drainage line. Detention basin bulk earthworks + concrete spillway NOT PRICED — allocation RFI pending (Opens #26; drawings say DETENTION basin).
1A | R52 |  | WSUD Basin? (question mark in document) | Item | 1 | 111787.7395 | PC SUM — supply + delivery of 22x Ocean Protect Tall (690) PSorb StormFilter cartridges O.A.E. in DN3300 manhole + 15% (locked 5.3). Installation in the Stormwater drainage lump sum. RFI CL A4.
1A | R59 | 3.0 | Netball Courts
1A | R81-82 | 3.5 | Hydraulic — Grated trench drains and pits | Item | 1 | 557726.4963 | TCS despite 'Hydraulic' heading (locked 5.1; drawn on civil sheets). GT1-GT4 + GT7-GT9 = 561.9 m Hauraton Recyfix + trash boxes + connection pits incl excavation & quarry — REINSTATED in full. GT5/GT6 in Stage 1B.
1A | R138 |  | LUMP SUM TOTAL (EXC. GST) — TCS lines |  |  | 2873602.7152 | Sum of: Stormwater drainage + 3.5 GT + WSUD PC.
1A | R140 | 7.0 | Schedule of Rates - Provisions
1A | R141 |  | Rock — removal of rock as defined in tender specification — SOFT ROCK, TRENCHES | m3 |  | 239.1149 | 4 rates per H002 n.24 (soft/hard x trench/pit); TCS rates apply to stormwater excavations only.
1A | R141 |  | Rock — HARD ROCK, TRENCHES | m3 |  | 478.2298
1A | R141 |  | Rock — SOFT ROCK, PITS | m3 |  | 318.8199
1A | R141 |  | Rock — HARD ROCK, PITS | m3 |  | 597.7873
1A | R142 |  | Unsuitable ground — removal and reinstatement | m3 |  | 390.3851 | Superintendent written direction only (ITT S18.1).
1B | R15 | 2.0 | Site Works
1B | R28 | 2.3 | Drainage
1B | R29 |  | Stormwater drainage | Item | 1 | 113131.2626 | 1B lump sum: GT5 + GT6 (46.6 m) + lines 60/61/83 + TB100 x4, standalone-viable (5.2).
1B | R30 |  | Retention Basin |  |  |  | NO separate 1B basin documented anywhere in the civil set — carried UNPRICED with qualification + RFI (CL A4); the single detention basin sits in the 1A hatch.
1B | R113 |  | LUMP SUM TOTAL (EXC. GST) — TCS lines |  |  | 113131.2626
1B | R115 | 5.0 | Schedule of Rates - Provisions
1B | R116 |  | Rock — SOFT ROCK, TRENCHES | m3 |  | 239.1149 | Same tendered rates as 1A (each stage's own excavations).
1B | R116 |  | Rock — HARD ROCK, TRENCHES | m3 |  | 478.2298
1B | R116 |  | Rock — SOFT ROCK, PITS | m3 |  | 318.8199
1B | R116 |  | Rock — HARD ROCK, PITS | m3 |  | 597.7873
1B | R117 |  | Unsuitable ground — removal and reinstatement | m3 |  | 390.3851
HELPER — GT (grated trench) component build-out for Sch 1A 3.5 split
|  |  | GT materials (G1-G5) escalated + x1.18 |  | 238277.2682
|  |  | GT labour C-06 + C-07 |  | 103047.3396
|  |  | GT plant (36 d 3-5T + quick-cut 5 d) |  | 9092.12
|  |  | GT accommodation share (36 cd pro-rata) |  | 17978.3354
|  |  | GT LH supervision share (36 cd pro-rata) |  | 25757.9377
|  |  | GT component cost |  | 394153.0009
|  |  | GT component SELL (x 1.415 on cost) |  | 557726.4963