## Forward_Test
ID | Exact proposal sentence (para ref) | Entity & stage | Location/system | Tender Schedule line | Source drawing/spec/addendum + rev | Quantity basis | Material/subcontract rate basis | Labour allowance | Plant & access allowance | Preliminaries treatment | Workbook sheet/row/cost code | External treatment | Confidence | VERDICT | FINDING
FT-01 | §6 / §8: “Stage 1A and Stage 1B are priced as standalone tenders; each remains viable and capable of award alone.” | TPS · 1A & 1B | Whole package | N/A — basis statement | N/A | 1A/1B split by crew-day ratio (146/166 vs 20/166) on TCS $ Sched R81/R84 | Combined base cost split proportionally, not independently re-estimated per stage | Combined labour split by crew-day share, not a stand-alone 1B labour build | Combined plant split by crew-day share | 5.5%/18%/18% applied ONCE to the COMBINED base (TCS $ Sched R42-51), then the combined sell is apportioned into 1A/1B by crew-day ratio — NOT independently costed prelim/OH per stage | TCS $ Sched R81, R84, R87-88; 00_ TCS Prelim & OH (whole-project mobilisation, 3 mobs, one genset/toilet/container run) | Stated as standalone-viable in Tender Value section and cover letter | Medium | PARTIAL | The standalone-viability claim is asserted twice but the cost model computes ONE combined prelim/OH/mobilisation cost for the whole 9.4-month, 3-mobilisation programme and then allocates a proportional share (20/166 crew-days) to Stage 1B. A truly independent 1B-only award would very plausibly need its own full mobilisation, genset, container and porta-loo run for its own duration — a smaller job does not shrink fixed establishment cost pro-rata, it usually increases the overhead percentage. No stand-alone-1B-only cost scenario exists in the model to test the claim. Recommend Director obtain/sight a stand-alone 1B cost run before repeating the claim unqualified.
FT-02 | §10: Alternate Pricing — copper substitution ALT-A, “addition of $1,169.23 ex GST” | TPS · 1A & 1B | NBC + PAM above-ground water >DN22 | Sch 4.11-c / 3.11-c | H-NBC-002 WS2; VOL 38 §10.1; T1 issue | 17.86 m + 112.72 m (NBC) + 9.56 m + 26.9 m (PAM) 316SS pipe less copper equivalent | EBC_Alternates ALT-2 build-up: copper pipe $3,657.30 vs base SS pipe $2,479.64 + fitting reversion -$439.89 = delta $737.77 | No separate labour delta modelled (assumed neutral install time copper vs press-fit) | N/A | Delta × 1.12 NBC contingency × 1.415 markup = $1,169.23 (EBC_Alternates R53) | EBC_Alternates R43-R53 | Alternate, excluded from tendered sum, offered on request | Medium | PASS | Ties exactly to the proposal figure ($1,169.23). Flagged internally (Gap #2) that SS press fitting rates are benchmark-derived (copper ×1.5) pending an actual RFQ — confidence is Medium, not High, but this is disclosed internally and doesn't need external disclosure.
FT-03 | §14: Measurement basis — site quantities “measured by scale from H003” | TPS · 1A | Site mains/reticulation/fire | Sch 2.1/2.4 | H003 (no printed pipe lengths); vector-verified per QUANTITY_RECONCILIATION TPS_Site | Vector-scaled lengths per QUANTITY_RECONCILIATION TPS_Site tab | All Siteworks pipe/fitting rows below | Crew 1 (23cd) + Crew 2 (35cd) day-rate blocks on Siteworks | All Siteworks plant rows (13-16T/8T/3-5T excavators, trench roller, hydro-ex truck) | 5.5% prelim on total cost | Siteworks R173,R349,R353,R360,R361,R705,R706 etc. | Stated as the measurement basis in Basis of Tender | High | PASS | Every scaled length checked against the Noted Inclusions numeric claims reconciles exactly (fire main 217.73 m, CW spine 236.88 m, branches 111.51 m, gravity sewer 207.53 m all tie to the cent/metre — see Reverse Test).
FT-04 | §17: Geotechnical basis — rock-rate regime “priced against the bore logs” | TPS · 1A & 1B | Site/NBC/PAM excavations | Sch 1A 7.0 / 1B 5.0 | NQL2024-0320 §5.3.3, Table 14 | Rock production rates (18/7/12/4.5 m3/day) vs normal (45 m3/day) per estimator judgement on refusal-depth data | Crew+plant combined day rate $3,289.48/day underlies the rate build-up (no separate material cost — this is an excavation rate, not a supplied material) | Crew 1 FIFO day rate embedded in the $3,289.48/day combined rate | 8T excavator + breaker embedded in the $3,289.48/day combined rate | N/A (schedule of rates, no quantity in the lump sum, so no prelim % applies until directed) | Sched3_Extract R42-R49 | Schedule of rates, contributes nothing to tendered sum unless directed | Medium | PASS | Rate build-up traceable to a stated formula and named inputs. Rock production rates are estimator judgement (disclosed as such), not a supplier/quarry quote — acceptable under Rule 1 as a transparent estimator calculation.
FT-05 | §19: “escalation to the anticipated 2027 commencement has been carried within the tendered sums” | TPS · 1A & 1B | All material | N/A | N/A | N/A | PE/PVC pipe & fittings ×1.38, subcontractor rates ×1.15, delivery ×1.20 (April 2026 direct-impact factors) applied at Material Rates_Master; separate ×1.12/1.18 site contingency layered on top per work area | N/A | N/A | N/A | NBC/PAM/Siteworks header cells (column J “april 2026 direct impact” factors); TCS $ Sched R51 (41.5% chain) | Stated in Basis of Tender and Conditions | Medium | PASS | Escalation factors are carried and traceable to named columns. Fixture PC Sum carries its own separate quotation-validity risk (13/08/26), correctly flagged in §19 rather than folded silently into the escalation factor — no double-count identified.
FT-06 | §23-29: Description of Proposed Services — 7 work-area bullets (site mains, site hydraulic, site fire, NBC, 1B connections, PAM, park units) | TPS · 1A & 1B | Whole package | Sch 2.1/2.2/2.4/3.5(excl)/4.11/4.12 (1A); 2.2/3.11/3.12/4.5 (1B) | H001-H003, H300 series, H-NBC-000/301, H-PAM-000/301 T1 | See individual Noted Inclusions rows below | See individual rows | See individual rows | See individual rows | 5.5%/18%/18% chain | Sched3_Extract full mapping (every Sch 3 line appears once) | Base lump sum per stage, PC Sum for fixtures/equipment, provisional for connection fees | High | PASS | Every work area named here is traced individually below under Noted Inclusions; no work area is asserted here that isn't priced somewhere in the model.
FT-07 | §30: “The proposal includes the supply, installation, testing, commissioning, certification, handover and defects liability obligations necessary to deliver the included hydraulic scope only” | TPS · 1A & 1B | Whole package | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Closing scope statement, correctly qualified “only” and “subject to the PC Sum supply regime” | High | PASS | This is the closest the draft comes to a broad statement (§2 Rule 4 concern). It is properly hedged — scoped to “only” the included scope and expressly subject to the PC Sum carve-out. Not prohibited wording.
FT-08 | §52: HDPE main — “The copper tapping-cluster fittings remain in the base as documented.” | TPS · 1A | Site water main | Sch 2.1-c | H003; VOL 38 §10.1 | 134.63 m HDPE pipe run + tapping-cluster fittings (tees/bends/stubs/valves) at adopted counts | Siteworks R349 (HDPE main, benchmark-derived rate PENDING RFQ — Gap #5) + R350-352, R657-664 (copper cluster fittings, quoted rates) | Crew 2 in-ground water/fire day rate (Siteworks R19, 35 crew-days) | 13-16T excavator (Siteworks R81, part of the 35 crew-days) | 5.5%/18%/18% | Siteworks R349-R352, R657-R664 | Base lump sum, no alternate offered in-ground (locked §5.5) | Medium | PARTIAL | The HDPE pipe RATE ITSELF is benchmark-derived and flagged internally as “PENDING RFQ” (Gap #5) — there is no live project-specific HDPE PE100 SDR11 DN250 quote in the Material & Quote Register for this exact product. This is disclosed internally but is a genuine confidence gap behind a technical position the proposal states with total confidence (§52, one tight paragraph, no hedging). Recommend the Director close Gap #5 with an actual supplier quote before red-team; if the benchmark rate proves low, the HDPE main cost — the headline technical position of the whole submission — is exposed.
FT-09 | §53: Above-ground water — 316 SS press-fit tendered as base, priced both ways | TPS · 1A & 1B | NBC + PAM | Sch 4.11-c / 3.11-c | H-NBC-002 WS2; VOL 38 | 30.42 m (NBC) + 36.46 m (PAM) SS pipe at adopted lengths | NBC F420/F423, PAM F405/F407 (project quote Reece Q-459014431, 22/28/35 mm only — covers every size needed) + benchmark-derived fittings (copper ×1.5, PENDING RFQ per Gap #2) | In the crew day-rate blocks (Crew 4 above-ground water/fire) | Scissor lift/EWP (NBC R106, 13 days) | 5.5%/18%/18% | ClubHouse (NBC ) R420-443; PAM R405-425 | Base (conforming), copper as labelled ALT-2 | Medium | PASS | Pipe rate is a genuine project quote (High confidence); fitting rates are benchmark-derived and flagged Gap #2 (Medium confidence). Forward test satisfied — material+labour+plant+prelims all present — but confidence on the fittings sub-component should stay Medium until RFQ'd.
FT-10 | §54: Articulation — “priced accordingly at slab entries and exits, changes of direction, and pier/beam penetrations, for both buildings” | TPS · 1A & 1B | NBC + PAM | Sch 4.11-c / 3.11-c | NQL2024-0320 §5.1; Design Report §4.3; structural Vols 04/09 NOT ISSUED | NBC ~25 joints @ ~$100 avg allowance; PAM ~7 joints @ ~$100 avg allowance | NBC R782 $2,500 item allowance (Gap #4, pending Storm Plastics RFQ); PAM R748 $750 item allowance | T5-05 (NBC) / rough-in days (PAM) — labour for installation is in the crew-day blocks, not broken out separately | N/A additional (within crew days) | 5.5%/18%/18% | ClubHouse (NBC ) R782; PAM R748 | Base lump sum, basis stated in Hydraulic Basis paragraph | Low-Medium | PARTIAL | Priced as a round-number ALLOWANCE (not a supplier quote or a drawing-derived count) because the structural drawings that would fix the actual joint count were never issued — this is disclosed internally (Gap #4) but the proposal states the articulation position with the same one-tight-paragraph confidence as the fully-quoted items. The external qualification at §54 (“pending their receipt”) is honest and adequate — verdict is PARTIAL only because the underlying allowance is a round-number estimate, not because the wording oversells it.
FT-11 | §55: Seismic restraint — “priced for installation of seismic restraints to the specified system… including access equipment” | TPS · 1A & 1B | NBC + PAM | Sch 4.11-c / 3.11-c | VOL 38 §3.15; H002 n.9; NQL2024-0320 §5.2 | ~2.5% rough-in material allowance (NBC), minor allowance (PAM) | NBC R932 $3,500 (Gap #3, RFQ nVent/Unistrut/Hilti pending); PAM R853 $500 | T4-07 (NBC, 2 crew-days) / within PAM rough-in/fit-off days | Scissor lift/EWP costed at NBC R106 (13 days, shared with articulation/rough-in access) | 5.5%/18%/18% | ClubHouse (NBC ) R932; PAM R853 | Base lump sum, “layout drafting only—no design liability” stated | Medium | PASS | Material+labour+plant+prelims all present. Allowance basis disclosed as Gap #3 pending RFQ (Medium confidence) — acceptable, not oversold externally (one tight paragraph citing AS1170.4/EDC2/Ce, no overclaim of a finished design).
FT-12 | §56: Fire services — “Boost testing, hydrostatic testing and third-party Form 72 certification… are included” | TPS · 1A | Site fire | Sch 2.4-c | H003 (no printed lengths/hydrant symbols) | 217.73 m fire main (vector-verified) | Siteworks R173, R293-296 | Crew 2 (part of 35 crew-days, T2-08 specifically) | 8T excavator + crane truck (T2-08) | 5.5%/18%/18% | Siteworks R149(booster test $3,560)/R150(3×hydro test $1,945)/R151(Form 72 $350) | Base lump sum, extent qualified at Appendix B C3 | Medium | PASS | All three named tests (boost, hydro, Form 72) are individually costed and traceable. AS 2419.1 hydrant-coverage adequacy is correctly NOT asserted — it is queried (C3) rather than claimed, which is the compliant way to handle a documentation gap under Rule 4.
FT-13 | §59: Noted Inclusion — “Project-specific preliminaries… traffic control for our own works and deliveries, erosion and sediment control local to our own open trenches, and trade set-out from Principal-supplied survey control” | TPS · 1A & 1B | Whole package | Sch 1.1-1.7 | N/A | N/A | No material rate exists for traffic control, erosion/sediment control or trade set-out anywhere in the workbook (searched all 12 sheets) | No dedicated labour line for these three items (unlike genset/toilets/container which are itemised on the Prelim & OH tab) | N/A | Wholly implicit within the 5.5% prelim percentage — which the model's OWN cross-check already shows running ~31% short against the items it DOES itemise (00_ TCS Prelim & OH R89-91: bottom-up $83,425 vs 5.5% allowance $63,797, variance +$19,628 / +30.8%) | 00_ TCS Prelim & OH (no matching rows found for these three items) | Stated as included, Noted Inclusions list | Low | FAIL | Traffic control, erosion/sediment control and trade set-out are stated as included but carry ZERO itemised cost anywhere in the 12-sheet model — not even a round-number allowance line of the kind used for articulation/seismic. They are wholly dependent on an undifferentiated 5.5% prelim percentage that the model's own bottom-up cross-check already shows is short by $19,628 (cost) / ~$27,772 (sell) against the items that ARE itemised. Adding three more unpriced items to an already-short percentage pool is a genuine forward-test failure: these are not traceable to a complete material+labour+plant allowance, only to an aggregate percentage that is already stretched.
FT-14 | §60: Noted Inclusion — Temporary site services “in full— portable toilets and wash facilities, generator power and temporary potable water storage and distribution” | TPS · 1A & 1B | Whole package | Sch 2.2-b / 2.1-a | ITT §17.3 (no site power/water) | 285 site days; 2 pods over ~10 months | Genset $45/d ×285d=$12,825; potable water pods $5,000 item; porta loo $5.46/d ×285d=$1,556.10 | N/A (hire items) | N/A | Itemised bottom-up on 00_ TCS Prelim & OH R75-77, cross-checked (not directly summed) against the 5.5% allowance | 00_ TCS Prelim & OH R75, R76, R77 | Base lump sum, scoped “our own works only”, Stage 1B sized standalone | High | PASS | Genuinely itemised, quantity × rate × duration, each traceable. See FT-13 for the parallel prelim items that are NOT itemised.
FT-15 | §61: Gravity sewerage mains 207.53 m (29.29 m Ø150 + 178.24 m Ø100), 2 SMS, Ø150 property connection | TPS · 1A | Site sewer | Sch 2.1-b | H003 vector-verified | 207.53 m total, matches QUANTITY_RECONCILIATION TPS_Site exactly | Siteworks R705 (29.29m@$14.49) + R706 (178.24m@$9.55) + R765 ($900 property connection) + R766 (2×$5,250 SMS) | Crew 1 (23 crew-days, T1-01..T1-05,T1-11,T1-12) | 13-16T excavator + trench roller (Siteworks R81/R102) | 5.5%/18%/18% | Siteworks R705,R706,R765,R766 | Base lump sum, terminates at Council pump-station inlet | High | PASS | Exact metre-for-metre tie: 29.29+178.24=207.53. Full material+labour+plant+prelims chain present.
FT-16 | §62: Water mains — Ø200 tapping cluster, 100mm fire + 100mm CW meter assemblies, 4x2m slab+bollards, HDPE main | TPS · 1A | Site water | Sch 2.1-c | H003 (RRC/FRW requirement) | 134.63 m HDPE + 1 combined meter assembly (legend groups both as one item, corrected from Denis's 0.5) | Siteworks R349 (HDPE, PENDING RFQ Gap #5) + R657-664 (tapping cluster) + R689 ($5,500 meter assembly, corrected qty) | T2-01..T2-03 (Crew 2, part of the 35 crew-days) | 13-16T excavator + hydro-ex truck (T1-04/T2-02) + services locator (live O300 main) | 5.5%/18%/18% | Siteworks R349,R657-664,R689 | Base lump sum, credit if FRW supplies meter bodies | Medium | PASS | Meter-assembly quantity correction (0.5→1 EA) is a genuine repair, documented and traceable. HDPE main rate remains Gap #5 (see FT-08).
FT-17 | §63: Site water reticulation — 236.88 m CW spine, 6 take-off sets, 111.51 m branches, capped future services, capped irrigation take-off | TPS · 1A | Site water | Sch 2.4-b | H003 vector-verified | 236.88m spine + 111.51m branches (37.26+74.25) all tie exactly | Siteworks R353 (236.88m), R360 (37.26m), R361 (74.25m) + fittings R364-402 | Crew 2 (part of 35 crew-days) | 13-16T excavator + trench roller | 5.5%/18%/18% | Siteworks R353,R360,R361,R364-402 | Base lump sum | High | PASS | All three stated lengths tie to the metre against the cost model — no variance found.
FT-18 | §64: Site fire services — 217.73 m DN125, booster+cabinet, dual pillar hydrant, boost/hydro/Form72 | TPS · 1A | Site fire | Sch 2.4-c | H003 | 217.73m (vector-verified) + 1 booster + 1 hydrant | Siteworks R173 (fire main), R293-294 (booster+cabinet), R296 (hydrant) | T2-08 (3 crew-days) | 8T excavator + crane truck | 5.5%/18%/18% | Siteworks R173,R293,R294,R296,R149-151 | Base lump sum, coverage queried at C3 | High | PASS | Duplicate of FT-12 items from the schedule-line perspective — confirms consistency across both mentions in the proposal.
FT-19 | §65: Stage 1B connections — branch take-offs, PAM entries, DF/bubbler supplies+wastes, hose taps | TPS · 1B | Site/PAM interface | Sch 2.2-b | H003; PAM sheets | 4 crew-days T2-09 carried on the PAM sheet | PAM R405-425 (water), R653 (hose tap) | T2-09 (4 crew-days, Crew 2, carried on PAM sheet per interface L9) | Included in T2-09 crew-day plant allocation | 5.5%/18%/18% | PAM R18-22 (crew allocation notes), R653 | Base lump sum, branch fitting/valve is the boundary | High | PASS | The interface (branch fitting/valve as the 1A/1B boundary) is consistently applied — T2-09 is booked to the PAM/1B sheet exactly as ITT §6 requires.
FT-20 | §66: NBC building hydraulics — sanitary 268.4m, trade waste 54.78m + 1500L GIT, water, 2xHWU, pump, RPZD, TMVx10, ATPx2, DP stubs | TPS · 1A | NBC | Sch 4.11-c | H-NBC series T1 | 268.4m=230.07+12.68+25.61 (sanitary only, vents excluded correctly); 54.78m TW exact | NBC R724,R741,R742 (sanitary); R813 (TW); R420-443 (water); big-ticket GIT/HWU/pump block; R690/699/700/702/834/835 (RPZD); R712 (TMV); R717 (ATP); R844 (DP stubs) | Crew 1 (26 cd), Crew 4 (21 cd), Crew 5 (27 cd) per activity breakdown in H18/H21/H22 | 1.5-1.8T & 3-5T excavators, wacker, scissor lift, PE welder, crane truck/HIAB | 5.5%/18%/18% | ClubHouse (NBC) — see cited rows | Base lump sum; GIT on stated allowance basis (size RFI C7) | High (quantities) / Medium (GIT size) | PASS | Every numeric claim in this single sentence reconciles exactly to the cost model (see Reverse Test for the full quantity walk). GIT size uncertainty (1500/2000/550-5000L) is disclosed at query C7, consistent with the Equipment Test finding — correctly not overclaimed.
FT-21 | §67: NBC fire compliance — FHR + fire blanket, installed and connected | TPS · 1A | NBC | Sch 4.11-d | VOL 38; H-NBC drawings | 1 FHR, 1 blanket | NBC R307 ($125) + R308 ($60) | T4-04 (1 crew-day) | N/A (hand tools) | 5.5%/18%/18% | ClubHouse (NBC) R307,R308,R309(AS1851 $2,500) | Base lump sum; 8 extinguishers correctly EXCLUDED (EBC-3) and NOT described as included here | High | PASS | Exactly matches EQUIPMENT_TEST_TPS.md item 2.13 — extinguishers correctly kept out of this sentence.
FT-22 | §68: PAM building hydraulics — sanitary 68.09m@1:60, ORG+4xFWG, Rheem 50L HWU, TMV, Ø32 check-meter, water, articulation, DP stubs | TPS · 1B | PAM | Sch 3.11-c | H-PAM series T1 | 68.09m=61.16+6.93 exact; 4 FWG (adopted, higher than 3 drawn) | PAM R695,R711 (sanitary); R746(ORG),R750(FWG); big-ticket 50L HWU block; R682(TMV); R680(check-meter) | T1-09(4cd),T3-03(2cd),T4-05(4cd),T4-06(1cd) | 1.5-1.8T excavator, wacker (PAM plant rows) | 5.5%/18%/18% | Public Amenities (PAM) — see cited rows | Base lump sum | High | PASS | 68.09m ties exactly; FWG count correctly shows the adopted (higher, 4) count against 3 drawn — consistent with the H002 n.15 ‘adopt higher’ convention stated elsewhere in the submission.
FT-23 | §69/70: Articulation and seismic hardware for both buildings — “restraint layout drafting only” | TPS · 1A & 1B | NBC + PAM | Sch 4.11-c/3.11-c | AS 2870 H1/P; AS1170.4 EDC2 | See FT-10/FT-11 | See FT-10/FT-11 | See FT-10/FT-11 | Scissor lift/EWP shared allocation | 5.5%/18%/18% | NBC R782/R932; PAM R748/R853 | Base lump sum | Low-Medium | PARTIAL | Same finding as FT-10/FT-11 (round-number allowances, Gaps #3/#4). No distinct new finding; cross-referenced to avoid double-counting the same defect twice in the summary.
FT-24 | §71: “Installation and connection only of the five Principal-supplied Billi Quadra 4180…” | TPS · 1A | NBC canteen | Sch 4.12-c | FF&E VOL 25 | 5 units | Supply value -$38,261 deducted from fixture PC Sum at TCS $ Sched R73 — TPS carries NO supply cost, confirmed | T5-02 (3 crew-days, Crew 5) | N/A | 5.5%/18%/18% on install labour only | ClubHouse (NBC) T5-02 note; TCS $ Sched R73 | Correctly worded — exact Rule 4 trap avoided | High | PASS | This is the single wording the whole exercise exists to catch, and the draft gets it exactly right: never ‘Billi units included’, always ‘installation and connection only’ of Principal-supplied units. Matches EQUIPMENT_TEST_TPS.md §6 verbatim.
FT-25 | §72: “Installation, fit-off and connection of the sanitary fixtures and tapware supplied under the fixture PC Sums (93 fixtures NBC; 15 fixtures PAM)” | TPS · 1A & 1B | NBC + PAM | Sch 4.12-c / 3.12-a | FF&E VOL 25/28 (no quantities stated — query C6) | 93 NBC (adopted) + 15 PAM (adopted, PAM set never independently counted) | NBC R930 ($30/EA×93 fit-off consumable); PAM R851 ($30/EA×15); PC Sum supply at TCS $ Sched R71/R74 | Fit-off labour within Crew 5 day blocks (T5-01 etc.) | N/A (fit-off tools) | 5.5%/18%/18% on install; 15% margin only on the PC Sum supply | ClubHouse (NBC) R930; PAM R851; TCS $ Sched R71/R74 | PC Sum (supply) + Base (install) — correctly split | Medium | PASS | Counts tie to Table 8/Sched3_Extract exactly. Confidence Medium because FF&E schedules genuinely carry no stated quantities (RFI C6) — correctly disclosed, not silently assumed.
FT-26 | §73: “Installation and connection of the PC-Sum drinking fountains…and the four water bubbler stations; slabs…by others and…signage excluded” | TPS · 1A & 1B | NBC/PAM/park | Sch 4.12-e / 3.12-b / 4.5-c | H003; Tradelink 1066143 | 2 NBC + 2 PAM DF + 4 bubblers | PC Sums at TCS $ Sched R72,R75,R76; install labour T5-04a/T5-04b | T5-04a (1cd), T5-04b (1cd) | N/A | 5.5%/18%/18% on install; 15% on PC Sum supply | ClubHouse/PAM T5-04a/b; TCS $ Sched R72/R75/R76 | PC Sum (calculated) + Base (install) | Medium | PASS | Matches EQUIPMENT_TEST_TPS.md §2.10/2.11 exactly, including the signage exclusion and the slabs-by-others boundary. PAM non-chilled unit remains an unpriced SKU pending re-quote (Gap #6) — correctly flagged at query C10, not overclaimed.
FT-27 | §74: “Delivery, craneage, storage and double-handling of long-lead equipment (grease arrestor, hot water plant, booster assembly)” | TPS · 1A | NBC + Site | Sch 4.11-c / 2.4-c | N/A | N/A | Siteworks R153 ($1,200 long-lead storage/double-handling allowance, added in the Rule 4 repair) | Crane truck/HIAB (NBC R149, Siteworks R152) | N/A | 5.5%/18%/18% | Siteworks R153; NBC R149; Siteworks R152 | Base lump sum | Medium | PASS | This inclusion previously had NO cost home at all until the Rule 4 equipment test closed the gap (see EQUIPMENT_TEST_TPS.md §5/§6). Now traceable; confidence Medium because the allowance is a single lump ($1,200) covering four different long-lead items of differing scale (booster 10-12wk, 316SS 10-14wk, Rheem 4-6wk, Stoddart specials 8-12wk) rather than four individually quantified sub-lines.
FT-28 | §75: “Non-destructive (hydro/vacuum) excavation to the allowance carried for existing-service proving and the authority tapping connection” | TPS · 1A | Site | Sch 2.1-c | VFMP; ITT §17 | 20 hr @ 3000L hydro-ex truck | Siteworks R65 ($190/hr×20hr=$3,800) | T1-04(1d)/T2-02(1d) | 3000L hydro-ex truck | 5.5%/18%/18% | Siteworks R65 | Base lump sum, scoped to tree-protection-zone routes | High | PASS | Directly costed and traceable, correctly scoped to “the allowance carried” rather than an open-ended commitment.
FT-29 | §76: Testing and commissioning — hydrostatic testing/disinfection, TMV certs (11), RPZD field tests, HW commissioning, Form 72 | TPS · 1A & 1B | Whole package | Sch (multiple) | VOL 38 | 3 site full hydro tests; 11 TMV certs; HWU commissioning within T4-03/T4-06; Form 72 x2 (NBC+Site) | Siteworks R150($1,945×3); R148($1,500 flush/disinfect); NBC R150($450×2); NBC/Site Form72 R154/R151 | T5-06 (NBC/PAM, 4cd); T2-10 (Site) | Hydro/commissioning test gear ($450/d) | 5.5%/18%/18% | Siteworks R148,R150,R151; NBC R150,R154 | Base lump sum | High | PASS | TMV cert count (11) reconciles exactly to 10 NBC + 1 PAM (see Reverse Test / Equipment Test §2.6). Every named test type has its own costed line.
FT-30 | §77: “Compaction testing of our own trench backfill at the allowance carried” | TPS · 1A & 1B | Whole package (as worded) | N/A | H002 n.17/16 duplicate; VOL 38 §3.62 | 15 tests + 4 site-establishments (NBC ONLY) | NBC R147($115×15=$1,725) + R148($90×4=$360) | N/A | N/A | 5.5%/18%/18% | ClubHouse (NBC) R147-148; Public Amenities (PAM) R145-146 (rate present, QTY=0); Siteworks R145-146 (rate present, QTY=0) | Base lump sum, stated package-wide | High (NBC only) / Nil (PAM, Site) | FAIL | The rate LINE for compaction testing exists on all three sheets (NBC, PAM, Siteworks) but only NBC carries a non-zero quantity (15 tests). PAM and — critically — Siteworks (which carries the largest trench lengths on the whole package: 134.63 m Ø200 main, 236.88 m CW spine, 217.73 m fire main, 207.53 m gravity sewer, plus branches) both show QTY=0 against the same rate row. The proposal states this inclusion once, package-wide, with no NBC-only qualifier. This is a genuine forward-test FAIL: the majority of the trenching this sentence purports to cover has ZERO compaction-testing cost behind it. Estimated exposure at the NBC unit rate scaled to Siteworks' much longer trench run would very plausibly exceed $6,000-$8,000 cost (not calculated precisely here — Rule 2 applies: flagged, not invented). Director must add Siteworks/PAM compaction-testing quantities before red-team.
FT-31 | §78: “Twelve-month maintenance of the installed fire services including AS 1851 servicing and tagging” | TPS · 1A | NBC + Site fire | Sch 4.11-d | VOL 38 | 1 item, FHR/FB/booster/hydrant | NBC R309 ($2,500, incl 6-monthly visits piggybacked on FIFO attendance) | Piggybacked on attendance, no separate crew-days | N/A | 5.5%/18%/18% | ClubHouse (NBC) R309 | Base lump sum | Medium | PASS | Costed as a single allowance covering both buildings' and the site's fire assets — acceptable as a bundled service allowance, though it sits only on the NBC sheet rather than being split/cross-referenced from Siteworks; a minor presentation point, not a cost gap.
FT-32 | §79: “As-constructed documentation, RPEQ certification and ADAC-compliant XML deliverables…and CCTV of our own in-ground drainage” | TPS · 1A & 1B | Whole package | Sch 1.6; ITT §19; VOL 38 §3.56 | N/A | 1 item, package-wide | Siteworks R147 (CCTV $5,000, “~385m @ ~$10/m”); Siteworks R143 (surveyor $2,880, as-cons/ADAC attendance) | T5-07 (surveyor attendance) | N/A | 5.5%/18%/18% | Siteworks R143,R147 | Base lump sum | Low (RPEQ) / Medium (CCTV/ADAC) | FAIL | Split finding. (1) RPEQ CERTIFICATION: searched all 12 sheets for ‘RPEQ’ — no cost line, allowance, or consultant-fee row exists anywhere in the model, yet RPEQ certification is explicitly claimed as an included deliverable here and again in §145 (Construct-Only Basis). An RPEQ sign-off is normally an external consultant engagement with a real fee; this is UNTRACEABLE. (2) CCTV/ADAC: a single $5,000 allowance sits on the SITEWORKS sheet only, with a stated basis of ‘~385 m’ of drainage — but the package's total in-ground drainage across NBC (268.4m sanitary + 54.78m TW) + PAM (68.09m) + Site (207.53m gravity sewer + 16.28m TW stub) is materially more than 385 m, and NBC/PAM each show no dedicated CCTV/ADAC line of their own. Confidence Medium — plausible the $5,000 is meant to cover the whole package's CCTV, but the basis note doesn't reconcile cleanly and each entity's own in-ground assets (NBC, PAM) have no stand-alone attendance/establishment allowance, which VOL 38 §3.56 and the CCTV firm's mobilisation practice would normally require per building.
FT-33 | §83: “No fixture, tapware or equipment supply is included elsewhere, and no statement in this submission is to be read as including supply beyond the PC Sums stated” | TPS · 1A & 1B | Whole package | N/A | N/A | N/A | N/A | N/A | N/A | N/A | TCS $ Sched R70-78 (PC Sum build) | Explicit anti-overclaim wording | High | PASS | This is a model example of compliant Rule 4 wording — a defensive clause that narrows every other inclusion sentence in the document rather than broadening it. No finding.
FT-34 | §87: “Backflow prevention devices are supplied, installed, field-tested and certified. Device registration…rides with the plumbing approval lodgement, which is excluded” | TPS · 1A & 1B | NBC + Site | Sch 4.11-c/2.4-b | N/A | 4×20mm+2×50mm RPZD (NBC), check valves (NBC+Site) | NBC R690,R699,R700,R702,R834,R835; Siteworks R661 | T4-02 (NBC), T2-05 (site checks) | N/A | 5.5%/18%/18% | ClubHouse (NBC) R690 etc.; Siteworks R661 | Base (device) / Excluded (registration, see FT-38 finding) | High (device) / see FT-38 | PASS (device) — cross-ref FT-38 (registration add-price) | Device supply/install/test/cert is fully traced. The registration EXCLUSION is correctly worded, but see FT-38: the ‘add-price held’ language used elsewhere for the parent obligation (plumbing approval lodgement) is not backed by an actual costed EBC line — registration itself carries no separate claim of an add-price here, so no finding attaches to this specific sentence.
FT-35 | §89: “The grease arrestor is priced at the 1500 L unit as drawn on a stated allowance basis” | TPS · 1A | NBC | Sch 4.11-c | H-NBC-102 (1500L); Design Report §12.4 (2000L); VOL 38 §22.25-27 (550-5000L range) | 1 unit, 1500 L | Big-ticket block: purchase $8,523.28 + freight $250 (Installation_MH token correctly zeroed, see FT-36) + lids $2,413.28 | T1-08 (8 crew-days, Crew 1) + T5-02 (commissioning, 3cd) | 3-5T excavator (4d) + crane truck (1d) | 5.5%/18%/18%; big-ticket block markup is only ×1.15 not the 41.5% chain (see Reverse Test finding) | TCS $ Sched R11/R16/R17 (‘big ticket items’ block) | Base lump sum, size RFI’d at C7 | Medium | PASS | Fully traceable across supply/delivery/install/commissioning — matches EQUIPMENT_TEST_TPS.md §2.1 exactly. Sizing uncertainty correctly disclosed (not overclaimed).
FT-36 | Noted Inclusion equivalents — HWU/pump installation wording throughout §66/68 | TPS · 1A & 1B | NBC + PAM | Sch 4.11-c/3.11-c | H-NBC-301, H-PAM-301 | 2 NBC + 1 PAM HWU, 1 pump set | Big-ticket blocks; NBC R933/PAM R854 (SS plinth, added in repair) | T4-03(NBC,3cd)/T4-06(PAM,1cd) | Crane truck (0.5d within T4-03) | 41.5% chain on plinths; 1.15× only on the big-ticket blocks themselves | TCS $ Sched R11,R17-31; NBC R933; PAM R854 | Base lump sum | High | PASS | Confirms EQUIPMENT_TEST_TPS.md §2.2-2.4 findings exactly — the two genuine fixings gaps (SS plinths) were closed in the repair and the four duplicate Installation_MH tokens were correctly zeroed with an audit trail. No new finding; included here to demonstrate the concordance independently reproduces the equipment test's conclusion rather than merely citing it.
FT-37 | §112: Sewage pump station exclusion — “the rising main…an add-price for the rising main is held and available on request” | TPS · 1A | Site sewer | Sch 2.1-x1/x2 | Addendum 2; H003/VOL17 QMax Fortis 3200; VOL38 §24 Sulzer XFP | 110 m DN110 rising main allowance | EBC_Alternates EBC-1: pipe $3,656.90 + fittings $548.54 + labour $5,724.85 (2cd) + plant $1,177.33 = cost $11,107.62 | 2 crew-days Crew 1 (Phase 7 T1-06) | 5T excavator 2d + butt welder 2d | 41.5% chain applied to EBC-1 cost → add-price $15,717.29 | EBC_Alternates R6-R13 | Excluded, add-price HELD (not offered) — correct wording used | High | PASS | This is the model example of a correctly-costed EBC add-price: quantified, formula-ready, and the submission wording (‘held’, not ‘offered’) matches the commercial intent exactly. Contrast with FT-38/FT-39 below, where the same wording pattern is used but no costed line exists.
FT-38 | §114: “Plumbing approval lodgement…are excluded—a stated departure…with an add-price held (Appendix B query C8)” | TPS · 1A & 1B | Whole package | N/A — ITT Pt2 §16 | ITT Pt2 §16 | N/A | NONE FOUND — searched all 12 sheets and EBC_Alternates for ‘lodge/lodgement/approval application’: no match | N/A | N/A | N/A | NONE — EBC_Alternates carries EBC-2 (Trade Waste application specifically, a narrower and separately-named obligation) but no line for the general plumbing approval lodgement obligation | Claimed as ‘add-price held’ | N/A | FAIL | UNTRACEABLE. The proposal (§114) and the RFI Schedule (query C8: ‘an add-price applies (held internally)’) and the Assumption/Gap/Risk Register (D6-F6: ‘add-price held on EBC’) all assert that a costed reinstatement price exists for plumbing-approval lodgement — but no such line exists anywhere in EBC_Alternates or any other sheet. This is distinct from EBC-2 (Trade Waste application only, $4,147.67 add-price, correctly costed) — the general ITT §16 lodgement/documentation/attendance obligation has NO quantified reinstatement price despite three separate documents claiming one is ‘held’. Per Rule 5 (no silent zeros) this is a registered gap, not a resolved one. Director must add a costed EBC line (comparable order of magnitude to EBC-2, ~$4,000-5,000 sell, but NOT to be assumed — must be estimated fresh) before the claim in §114/C8 is true.
FT-39 | §116: “Shop drawing production is excluded—a stated departure from H002 note 2, with an add-price held and available on request” | TPS · 1A & 1B | Whole package | N/A — H002 note 2 | H002 note 2 | N/A | NONE FOUND — searched all 12 sheets and EBC_Alternates for ‘shop draw’: no match | N/A | N/A | N/A | NONE. Sched3_Extract R51 references ‘shop drawings (X1 - EBC in the tender control register)’ but no such register entry exists anywhere in _Tender_Control | Claimed as ‘add-price held’ | N/A | FAIL | UNTRACEABLE — identical defect to FT-38. The proposal states an add-price is ‘available on request’ for shop drawing production, and the workbook's own cross-reference note (Sched3_Extract R51) points to an EBC entry that was never actually created. This is a second, separate instance of the same governance gap: a wording pattern (‘add-price held’) copied from EBC-1/EBC-2/EBC-3 (which ARE correctly costed) onto two items (C8 lodgement, H002 n.2 shop drawings) that were never actually built out. Director must add a costed line for both before the tender is red-team ready, or remove the ‘add-price held’ language and replace with ‘quantifiable on request’ (i.e. not yet priced) if a genuine estimate cannot be produced in time.
FT-40 | Table 6 (Building-Specific Clarifications) — PAM: “No PRV is documented at the PAM entry against the NBC 500 kPa provision…any pressure-reduction requirement is unpriced pending direction” | TPS · 1B | PAM | Sch 3.11-c | H-PAM series vs H-NBC-301 (500 kPa provision) | N/A | No PRV material/labour costed for PAM (correctly, since none is documented) | N/A | N/A | N/A | N/A — correctly NOT costed, and NOT claimed as included | N/A | High | PASS | Textbook Rule 5 treatment — an unresolved technical question is disclosed and explicitly NOT priced or claimed, rather than silently included or silently dropped. No finding.
FT-41 | Appendix A / Table 8: NBC Downpipe count — Table 6 states “eleven Ø150 downpipes”; Table 8 states “19 (adopted)” for a combined “Site (1A/1B)” row; Query C11 states drawings show 11 (NBC) + 4 (PAM) | TPS · 1A & 1B | NBC + PAM | Sch 4.11-c/3.11-c | H-NBC-103 (11 drawn); H-PAM-101 (4 drawn) | NBC: 9 markers on drawing, 11 counted on review, 19 ADOPTED (conservative/higher, RFI Opens #23). PAM: 4 EA adopted separately. | NBC R844 (19 EA @ $40 = $760, NBC ONLY); PAM R767 (4 EA @ $40 = $160, PAM ONLY) — total priced = 23 EA, not 19, not 11, not 15 | N/A (allowance item, no separate labour beyond crew-day blocks) | N/A | 5.5%/18%/18% | ClubHouse (NBC) R844; PAM R767 | Base lump sum | Low | PARTIAL | Internal wording inconsistency, not a cost gap — the model actually prices MORE stubs (23 total: 19 NBC + 4 PAM) than any of the three counts stated in the proposal text (11 in Table 6, ~15 implied by Query C11's “as drawn”, or 19 in Table 8 if a reader assumes that figure is the whole-package total). Because the model over-covers rather than under-covers, there is no dollar exposure — but a red-team reader comparing Table 6 (11), Query C11 (11+4=15) and Table 8 (19) side by side will reasonably conclude the document contradicts itself on a simple count. Recommend the Director correct Table 8 to read ‘NBC 19 (adopted) + PAM 4 (adopted) = 23’ and align Table 6/Query C11 wording before red-team, purely for document-integrity reasons.

## Reverse_Test
ID | Workbook sheet & row/cost code | Cost description | Cost (pre-markup, ex GST) | Entity & stage | External home (proposal sentence / schedule line / PC Sum / EBC / internal-only) | Internal-only? (Y/N + reason) | VERDICT | FINDING
RT-01 | TCS $ Sched R94-95 | TriCore corporate overhead $40,000/mo ×9.4mo, less 45% concurrent-project allocation = $169,200 net | $169,200 net (after 45% concurrent-project allocation) | TPS · whole package | N/A — internal overhead structure | Y — TENDER_PROMPT §8 expressly bars external disclosure of overhead/margin structure | PASS | Correctly internal-only. The 18% O/H markup line the proposal's total price reflects is the external face of this cost; no external sentence needs to (or should) describe it.
RT-02 | 00_ TCS Prelim & OH R70-83 | Vehicles, genset, potable water, porta loo, lunchroom/office, container, skip bin, mobilisation float — bottom-up $83,425.22 | $83,425.22 bottom-up | TPS · whole package | §60 Noted Inclusion (temporary site services in full) | N — externally represented via the 5.5% prelim %, not itemised in the proposal (correctly, per §8 non-disclosure rule) | PARTIAL | The bottom-up total ($83,425) exceeds the 5.5% prelim allowance actually applied to the sell price ($63,797) by $19,628 (+30.8%) — disclosed by the model's own cross-check (R89-91) as ‘a real exposure’. This is the cost-model-side view of the FT-13 finding: the prelim percentage that stands behind §59/§60/§96 is short against its own itemised evidence.
RT-03 | 00_ TCS Prelim & OH R94-98 | Combined prelim+O/H bottom-up $252,625 vs combined 5.5%+18% allowance $272,588 (variance -$19,963, i.e. allowance EXCEEDS bottom-up when combined) | $252,625 combined bottom-up vs $272,588 combined allowance | TPS · whole package | N/A — internal cross-check | Y | PASS (net) / caution flagged | At the COMBINED level the O/H allowance ($208,791) comfortably exceeds bottom-up O/H ($169,200) by $39,591, which more than offsets the prelim shortfall (RT-02). Total price is NOT short. However, the labelling is misleading internally: what the model calls ‘O/H surplus’ is functionally subsidising a ‘prelim shortfall’ across two different named markup categories. This is a presentation/governance issue for TriCore's internal control, not a proposal-facing Rule 4 defect — flagged for completeness, not counted in the FAIL total.
RT-04 | TCS $ Sched R11 (big-ticket items block) | GIT/HWU/pump purchase totals $8,523.28+$6,775.83+$3,438.29×2+$2,016.08 = $24,191.77 (+freight/safe-tray) at ×1.15 markup, NOT the 41.5% chain | $24,191.77 purchase (+ freight/safe-tray) | TPS · 1A/1B | §66/68/89 Noted Inclusions (GIT, HWU, pump) | N — externally represented as part of the Base lump sum | PASS (traced) / Director decision pending | Fully traced to proposal wording (see FT-35/FT-36). BUT this is a live, quantified Director decision recorded in EQUIPMENT_TEST_TPS.md §5: the four big-ticket items earn 14.49% effective margin vs 41.50% everywhere else in the model, a $6,805.55 sell delta if normalised. Not a Rule 4 traceability defect (the cost home exists and is disclosed) but IS a commercial consistency question the Director has not yet closed — carried here as a cross-reference, not a new finding.
RT-05 | NBC R782, R932; PAM R748, R853 (articulation/seismic allowances) | $2,500+$3,500 (NBC) + $750+$500 (PAM) = $7,250 round-number allowances | $7,250 combined allowance | TPS · 1A/1B | §54/55/69/70 Hydraulic Basis and Noted Inclusions | N | PASS (has a home) / confidence Medium-Low | See FT-10/FT-11/FT-23. Traceable but estimator-judgement allowances pending RFQ (Gaps #3/#4) — legitimate Rule 1 treatment (disclosed as an allowance) but confidence should stay Medium, not High, in any internal Director briefing.
RT-06 | Siteworks R153 | Long-lead storage/double-handling allowance $1,200 | $1,200 | TPS · 1A | §74 Noted Inclusion | N | PASS | Closed a genuine Rule 4 gap in the repair (see EQUIPMENT_TEST_TPS.md §6). Traced.
RT-07 | EBC_Alternates EBC-1 ($15,717.29 add-price) | Sewer rising main reinstatement price | $15,717.29 (add-price) | TPS · 1A | §112 (rising main add-price held) | N — EXCLUDED from the tendered sum by design, correctly disclosed externally as held-not-offered | PASS | Model example of correct EBC treatment — see FT-37.
RT-08 | EBC_Alternates EBC-2 ($4,147.67 add-price) | Trade waste application reinstatement price | $4,147.67 (add-price) | TPS · 1A | §114 (‘The Trade Waste application is likewise excluded…queries C7 and C8’) | N | PASS | Correctly costed and correctly referenced externally.
RT-09 | EBC_Alternates EBC-3 ($2,540.78 add-price) | Fire extinguisher supply reinstatement price (9 units) | $2,540.78 (add-price) | TPS · 1A/1B | §86 / Table 6 / C10 (extinguishers excluded, add-price held) | N | PASS | Correctly costed and correctly referenced externally — confirms EQUIPMENT_TEST_TPS.md §2.13/6.
RT-10 | EBC_Alternates EBC-4 (evidence only, no price carried) | Sewer pump station supply+install evidence ($468,000-$545,700 range across 3 quotes) | $0 priced (evidence only: $468,000-$545,700 quote range) | TPS · 1A | §112 (pump station excluded, Council-installed) | N — explicitly NOT priced, evidence retained only in case an add-price is later requested | PASS | Correct treatment: the proposal does not claim an add-price is held for the pump station itself (only for the rising main, EBC-1) — consistent with EBC-4's explicit ‘NO PRICE CARRIED’ label. No overclaim.
RT-11 | EBC_Alternates ALT-1 / ALT-2 (copper alternates) | HDPE→copper main delta ($36,891.78 sell if adopted, not offered); building water copper delta ($1,169.23 sell, offered as ALT-A) | $36,891.78 (ALT-1, not offered) / $1,169.23 (ALT-2, offered) | TPS · 1A/1B | §10 (ALT-A offered), §52 (no in-ground copper alternate offered) | N | PASS | ALT-1 (in-ground) is correctly NOT offered externally (locked §5.5 — no buried copper alternate); ALT-2 (above-ground) IS offered and ties exactly to §10's stated $1,169.23. Both alternates handled per their differing locked-decision status — no confusion between the two.
RT-12 | MATERIAL_QUOTE_REGISTER — Tradelink 1066143 header | Quote addressed to ‘TriCore CIVIL Services Pty Ltd’ and site address shown as ‘544 Yaamba Rd, Parkhurst’ (wrong entity, wrong street number, wrong suburb) | $252,694.77 (quote total; header defect only) | TPS · 1A/1B | PC Sum fixture supply basis (§19, §83, Sched3_Extract R17) | N/A — administrative quote-integrity issue | PARTIAL | Not a Rule 4 proposal-wording defect (the proposal does not repeat the quote's header errors) but a genuine Rule 1 traceability/quote-integrity risk: the underlying $252,694.77 quote that the entire fixture PC Sum is built on is addressed to the wrong TriCore entity and the wrong site address. Recommend a corrected-header confirmation from Tradelink before order placement — low severity for the tender itself, but material before award.
RT-13 | Siteworks R143/R147 (CCTV $5,000, surveyor $2,880) | See FT-32 | $7,880 ($5,000 CCTV + $2,880 surveyor) | TPS · whole package | §79/§145 | N | See FT-32 | Cross-referenced — not double-counted in the findings ranking.
RT-14 | All 12 sheets — search for 'RPEQ' | No match anywhere in the workbook | $0 (no RPEQ line found) | N/A | §79/§145 claim RPEQ certification as included | N/A — this IS the absence being tested | FAIL | Cross-referenced to FT-32 — the reverse-test route (hunting for the cost) independently confirms the forward-test finding (hunting for the proposal claim's cost home): RPEQ certification has no cost anywhere in the model.
RT-15 | Sched3_Extract R43-47 (rock schedule of rates) | 4 rock rates + 1 unsuitable-ground rate, all $/m³, zero quantity in the lump sum | $0 (rate only, no quantity in lump sum) | TPS · 1A/1B | §49/50 Schedule of Rates section, §119 Exclusions | N | PASS | Correctly disclosed as contributing nothing to the tendered sum unless directed — not padding, a genuine schedule-of-rates line per ITT §18.
RT-16 | Accommodation/Flights (TCS $ Sched R32-33) | $124,117.25 accommodation (Option A, 14 apt-months + 225 LH nights) + $63,505.20 flights | $187,622.45 ($124,117.25 accommodation + $63,505.20 flights) | TPS · whole package, split 1A/1B by crew-day ratio | N/A — internal FIFO cost basis; externally represented only via ‘Rockhampton and CQ-based crews…supported by our Brisbane office’ (About TriCore paragraph) | Y — correctly not itemised externally per §8 non-disclosure rule | PASS | No Rule 4 issue — FIFO/accommodation cost basis is internal by design and the proposal does not make any claim inconsistent with it existing. Cross-referenced to FT-01 for the standalone-viability question this cost's stage-split method raises.

## Equipment_Test_Reconciliation
# | Item | EQUIPMENT_TEST_TPS.md determination (summary) | Draft submission wording (verbatim/paraphrase, §ref) | Match? | Notes
1 | 1500 L Viking GIT grease arrestor | Complete — supply/delivery/storage/install/connect/commission all priced; token $250 correctly zeroed as duplicate of T1-08 | §66/89: “1500 L in-ground grease arrestor on a stated allowance basis”; Table 6 discloses the 3-way size conflict (1500/2000/550-5000 L) | YES | Wording never claims a resolved size — correctly hedged as ‘allowance basis’ and RFI'd at C7.
2 | Rheem 315 L HWU ×2 (NBC) | Complete — fixings gap (SS plinth) closed in the repair (NBC R933, +$520); token $600 zeroed as duplicate of T4-03 | §66: “two Rheem 315 L hot water units with safe trays, 316 stainless mounting plinths and seismic strapping” | YES | Wording now explicitly lists the plinth — matches the repair exactly, i.e. the draft was updated AFTER the equipment test, as intended.
3 | Rheem 50 L HWU ×1 (PAM) | Complete — fixings gap closed (PAM R854, +$260); token $200 zeroed as duplicate of T4-06 | §68: “one Rheem 50 L hot water unit with safe tray, 316 stainless plinth and seismic restraint” | YES | Matches exactly.
4 | HW circulating pump set | Complete — token $200 was a duplicate of T4-03; controls correctly excluded (electrical trade) | §66/88: “the hot water circulating pump set with flow/return loop”; §88: “Electrical isolators, power supplies, control panels and control cabling to hot water units, the circulating pump set…are by the electrical trade” | YES | Controls-exclusion wording present and correctly scoped — matches the equipment test's Rule 4 wording control exactly.
5 | RPZDs / check valves | Complete — registration correctly excluded (rides with plumbing approval lodgement, X2) | §87: “Backflow prevention devices are supplied, installed, field-tested and certified. Device registration…is excluded (refer Exclusions)” | YES | Matches the equipment test's wording control verbatim. NOTE: see FT-38 — the parent exclusion (plumbing approval lodgement) itself has no costed add-price despite claiming one is held; this does not change the correctness of THIS sentence, which only excludes registration, not the devices.
6 | TMVs ×11 (NBC 10 + PAM 1) | Complete — commissioning count ties exactly (10+1=11) | §66/68/76: “ten TMVs in lockable stainless boxes” (NBC), “one TMV in a lockable stainless cabinet” (PAM), “TMV certifications (eleven)” | YES | Exact match, count reconciles across three separate sentences.
7 | Water meters (site + PAM) | Complete — site 1 EA covering both assemblies (corrected from Denis's 0.5); PAM Ø32 check-meter separate | §62: “the 100 mm fire and 100 mm cold water meter assemblies…the 4 m × 2 m meter slab with bollards”; §68: “the Ø32 check-meter assembly at the building entry” | YES | Matches. Credit-if-FRW-supplies-meter-bodies caveat also correctly carried (§128).
8 | Fire booster assembly and cabinet | Complete — 10-12 week lead time flagged | §25/56/64: booster assembly and cabinet priced and included; §19 flags the 10-12 week lead time | YES | Matches, including the long-lead flag.
9 | Dual pillar hydrant | Complete | §25/56/64: “one 100 mm dual pillar hydrant” | YES | Matches; AS2419.1 coverage correctly queried (C3), not claimed as verified.
10 | Drinking fountains (2 chilled NBC + 2 non-chilled PAM) | Complete — signage excluded and stated; non-chilled SKU unpriced by anyone (Gap #6), re-quote pending | §73/85: PC Sum, install/connect by TriCore, slabs by others, signage excluded; Table 6/C10 discloses the non-chilled SKU uncertainty | YES | Matches exactly, including the disclosed pricing gap on the non-chilled unit — correctly NOT overclaimed as a firm price.
11 | Water bubbler stations ×4 | Complete — slabs/surrounds by others correctly excluded | §73/85/29: PC Sum, install/connect by TriCore, ‘slabs and surrounds to the site units are by others’ | YES | Matches exactly.
12 | Billi Quadra 4180 ×5 — PRINCIPAL-SUPPLIED | Complete — THE Rule 4 trap: must say ‘installation and connection’, never ‘Billi units included’ | §71/84: “Installation and connection only of the five Principal-supplied Billi Quadra 4180 boiling/chilled units” | YES | Exact match — the draft passes the single highest-stakes wording test in the whole equipment register.
13 | FHR / fire blanket / AS1851 maintenance | Complete — extinguishers correctly EBC, not ‘included’ | §67/78/86: FHR and blanket ‘included’; AS1851 maintenance included; §86: extinguishers ‘excluded…an add-price is held’ | YES | Matches. Extinguisher add-price IS correctly costed (EBC-3, $2,540.78) — unlike the two UNTRACEABLE add-price claims at FT-38/FT-39, this one is genuine.
14 | Automatic trap primers ×2 | Complete | §66: “two automatic trap primers” | YES | Matches.

## Findings_Summary
Rank | Severity | Ref(s) | Area | Finding | Dollar exposure (if quantifiable) | Recommendation before red-team
1 | HIGH | FT-30 | Compaction testing coverage | Compaction-testing rate line exists on all three work-area sheets but only NBC carries a non-zero quantity; Siteworks (the longest trench runs on the whole package — water main, fire main, gravity sewer, CW spine) and PAM both show ZERO compaction-testing cost, while the proposal's Noted Inclusion (§77) claims this package-wide with no NBC-only qualifier. | Not currently quantified in the model (≈$0 priced for Siteworks/PAM); NBC comparator = $2,085 for a much shorter trench run — true exposure for Siteworks/PAM trenching is plausibly several times that, but must be estimated fresh, not assumed. | Add Siteworks and PAM compaction-testing quantities (tests + establishment) before the proposal's §77 claim is true package-wide, or narrow the wording to NBC only.
2 | HIGH | FT-38, FT-39 | Add-price governance (EBC register) | Two exclusions — plumbing approval lodgement (§114/C8, ITT Pt2 §16) and shop drawing production (§116, H002 n.2) — are each stated as having ‘an add-price held’, and the RFI Schedule / Assumption-Gap-Risk Register repeat the same claim, but NO costed line exists anywhere in EBC_Alternates or any other sheet for either item. This is a clean two-for-two failure of Rule 5 (no silent zeros): the register entry that should exist was never built, only referenced. | Unquantified. For scale only (not to be used as the actual figure): EBC-2, the nearest comparable administrative exclusion, sits at $4,147.67 sell. | Build EBC-5 (plumbing approval lodgement) and EBC-6 (shop drawings) in EBC_Alternates with a genuine cost build-up, or amend §114/§116 to remove the ‘add-price held’ language until one exists.
3 | HIGH | FT-32, RT-14 | RPEQ certification | RPEQ certification is claimed as an included deliverable twice (§79, §145) but there is no cost line, allowance, or consultant-fee row anywhere in the 12-sheet model for engaging an RPEQ engineer. This is a genuine external-consultant cost with no internal home at all — not even a round-number allowance of the kind used for articulation/seismic. | Unquantified — no comparator exists in the model. RPEQ hydraulic/fire sign-off fees for a project of this scale are commonly several thousand dollars; Director should obtain an actual quote or set a disclosed allowance. | Add an RPEQ certification cost line (labour/consultant fee) before repeating the claim, or qualify §79/§145 to state RPEQ certification is provided by a named/TBC sub-consultant at cost.
4 | HIGH | FT-01 | Standalone-viability claim (Stage 1B) | §6 and §8 both assert Stage 1B ‘remains viable and capable of award alone’, but the prelim/OH/mobilisation cost behind BOTH stages is calculated ONCE for the combined 9.4-month, 3-mobilisation programme and then apportioned to 1B by a simple crew-day ratio (20/166). No independent stand-alone-1B cost scenario exists to test whether a smaller, isolated award would actually carry adequate establishment cost (a standalone smaller job typically has a HIGHER, not lower, overhead percentage). | Not quantified — the risk is structural (methodology), not a specific missing dollar amount. | Before repeating the standalone-viability claim unqualified, run (or obtain) an independent Stage-1B-only prelim/mobilisation estimate and compare it to the current 20/166 apportionment.
5 | MEDIUM | FT-13, RT-02 | Prelim percentage adequacy | Traffic control, erosion/sediment control and trade set-out are claimed as included (§59/§96) with zero itemised cost anywhere in the model, resting entirely on the 5.5% prelim percentage — which the model's own cross-check already shows running $19,628 (30.8%) short against the items it DOES itemise (genset, porta loo, container, insurance etc.). | $19,628 cost (≈$27,772 sell at the 41.5% chain) already disclosed as a shortfall by the model itself, before adding the three unpriced items above. | Either lift the prelim percentage, add priced lines for traffic control / erosion control / trade set-out, or accept and document the residual risk explicitly for the Director (currently undocumented outside the workbook's own memo cell).
6 | MEDIUM | FT-08 | HDPE main rate confidence | The single tightest, most confidently-worded technical position in the whole submission (§52, the HDPE-vs-copper departure) rests on a benchmark-derived (not project-quoted) HDPE PE100 SDR11 DN250 rate, flagged internally as ‘Gap #5 — PENDING RFQ’. | Not quantified — rate risk on 134.63 m of the project's largest single pipe run. | Obtain a live project-specific HDPE PE100 SDR11 DN250 quote before award; if the benchmark proves low, this is the headline technical position of the tender and the exposure would not be trivial.
7 | MEDIUM | FT-32 | CCTV/ADAC single-line coverage | A single $5,000 CCTV allowance sits on the Siteworks sheet only, with a stated basis of ‘~385 m’, while the package's total in-ground drainage across all three work areas (NBC 323m + PAM 68m + Site ≈224m ≈615m) is materially longer, and NBC/PAM carry no dedicated CCTV/ADAC establishment line of their own. | Not quantified — basis note does not reconcile cleanly to the stated ~385 m nor to the full ~615 m package total. | Confirm whether the $5,000 is meant to cover all three entities' assets in one mobilisation, or split/verify a per-building CCTV allowance is required (VOL 38 §3.56 implies per-asset attendance).
8 | LOW | FT-41 | Downpipe count internal inconsistency | Table 6 states ‘eleven’ NBC downpipes, Query C11 cites 11 (NBC)+4 (PAM) as drawn, and Table 8 states ‘19 (adopted)’ for a combined ‘Site (1A/1B)’ row — three different figures for the same item across one document. The cost model actually prices MORE (23: 19 NBC + 4 PAM) than any of the three stated counts, so there is no dollar exposure, only a documentation-consistency defect. | None — model over-covers. | Correct Table 8 to read ‘NBC 19 (adopted) + PAM 4 (adopted) = 23’ and align Table 6/Query C11 wording for internal consistency before red-team.
9 | LOW | FT-10, FT-11, FT-23 | Articulation/seismic allowance basis | Articulation and seismic hardware allowances (NBC $6,000, PAM $1,250 combined) are round-number estimator judgements pending supplier RFQ (Gaps #3/#4), not drawing-derived counts or supplier quotes — acceptable under Rule 1 given the structural drawings were never issued, but confidence should be tracked as Medium-Low, not treated as settled. | Not quantified — disclosed internally, adequately hedged externally (§54/55 cite the missing structural volumes). | No action required for red-team purposes beyond continuing to track Gaps #3/#4 to closure before award.
10 | LOW | RT-12 | Fixture quote header defect | The Tradelink 1066143 quotation ($252,694.77, the entire basis of the fixture PC Sum) is headed to ‘TriCore CIVIL Services Pty Ltd’ at the wrong street number/suburb (‘544 Yaamba Rd, Parkhurst’ vs the actual 554-700 Yaamba Rd, Norman Gardens). | None to the tender price — administrative/quote-integrity risk only. | Obtain a corrected-header confirmation from Tradelink before placing any order against this quote; not a tender-submission blocker.
11 | LOW | RT-04 | Big-ticket item margin (Director decision, already logged) | GIT/HWU/pump equipment carries a 14.49% effective margin (×1.15 legacy token) vs the 41.5% chain applied everywhere else — a live, already-quantified Director decision recorded in EQUIPMENT_TEST_TPS.md §5 ($6,805.55 sell delta if normalised). Not a new Rule 4 finding, listed here only so the concordance's own ranking is complete. | $6,805.55 sell if normalised to the standard chain (already quantified elsewhere). | No new action — Director decision already pending per EQUIPMENT_TEST_TPS.md; carried forward, not duplicated as a fresh issue.