## Register
Ref | Supplier | Quote No / Doc | Rev | Doc type | Date | Validity / expiry (as stated) | Addressed to | Entity / header issues | Category | GST basis | Freight / delivery basis | Stated exclusions (key) | Lead time | Escalation / freight / margin embedded? (double-count flags) | Total ex GST | Line-item summary (major items & rates, ex GST) | Scope element(s) priced | File path(s) under Material\
P01 | Tradelink | 1066143 SP | - | Quote | 15/07/26 | Prices valid for deliveries made by 13/08/26; goods delivered after sold at prevailing price at date of delivery | TRICORE CIVIL SERVICES PTY LTD (TCS) | WRONG ENTITY for hydraulic fixtures scope (should be TPS) and WRONG SITE header: '544 YAAMBA RD PARKHURST' vs actual 554-700 Yaamba Rd Norman Gardens. Job ref 28703083. | Project-specific (TEN16699) | Ex GST (some items GST-free, e.g. Caroma care grab rails marked 'NO GST' - so incl-GST total is not simply +10%) | Ex works branch + Standard Delivery Fee $31.82+GST per delivery; 'prices on certain products subject to increase if delivery location outside metro areas'; 2-person-lift / multi-storey extra | Signage for CF400 fountains extra ('IF WANTED SIGNAGE THERE WILL BE ADDED COST'); storage costs if required; custom order forms for non-standard items; 20% min restocking | Not stated | No escalation embedded - validity only to 13/08/26, then prevailing price. Freight NOT in rates (per-delivery fee extra). TRAP: package price basis - any qty variation/deletion may require re-quote. | 252,694.77 | Netball Clubhouse + Public Amenities fixture package. Key: 4x CF400-PREMIUM wall-mount chilled fountain DFCF400P @11,050; 5x Billi Quadra 4180 boil/chill @7,652.20; 5x custom L-shaped SS bench @4,986.50; 5x SS ambulant toilet suite @3,450.10; 6x accessible folding shower seat @550; 6x baby change @565.30; 2x vanity bench 1800 @4,650.10; Stoddart CC/WF toilets 2,130-3,650.31; knee-op basins @1,120.10; cleaners sinks @555.30; TMF pillar taps @335; misc grab rails/curtains/dispensers. | Fixtures (buildings); equipment (boil/chill); drinking fountains (chilled only) | 01 - Project Specific\Fixtures\tradelink\1066143_ROCKHAMPTON_SPORTS_PRECINCT.pdf
P02 | Atlan Stormwater | 26-87004 (Deal 87004 / Q41972) | - | Quote (high-level estimate) | 16/07/26 | 'The pricing is valid on the day of issue only' | 'TRICORE TRADE SERVICES' (neither TCS nor TPS - wrong entity name) | Wrong/loose entity name; project titled 'Rockhampton Netball Centre Norman Gardens Stage 1', correct site 554-700 Yaamba Rd | Project-specific (TEN16699) | Ex GST (T&C cl.4: consideration exclusive of GST) | FREIGHT-SALE line included in package, but 'quoted price does not include any fuel levy, which will be applied at the prevailing rate at time of dispatch'; flat-bed delivery, unloading & installation by others; 1 hr on site then demurrage | 'High level estimate only based on flowrate equivalent - once access to MUSIC model provided, Atlan will provide updated proposal'; unloading/installation by others; risers cut to height by others; lids boxed/bedded by others; commissioning visit is NOT installation | 'Approximately TBC from receipt of signed documents'; T&C indicates delivery approx 8-11 weeks from order acceptance | Freight INCLUDED in lump sum (do not add line freight again - only fuel levy + cranage/unload). No escalation embedded (same-day validity). TRAP: package includes commissioning - do not double-carry commissioning. | 88,838.00 | WSUD/detention package (lump sum): 38x Stormsack 600x600 (SSS.6060.C1) pit inserts; 10x FIL-3.0 filter (3.0 L/s @850mm head); 1x VAU.5023.1464-STD 14.9kL precast detention tank Class D (heaviest lift ~10t, incl weir walls); 1x HAC99HD 900x900 CI Class D cover; freight; commissioning/certification visit. | WSUD/filtration (pit inserts + filter) + detention tank | 01 - Project Specific\Material\CIVIL SW QUOTE\CIVIL SW DETENTION TANK\ATLAN\26-87004 ... - TRICORE.pdf
P03 | Atlan Stormwater | 26-87004-1 (SN8) (Deal 87004 / Q41968) | - | Quote | 16/07/26 | 'The pricing is valid on the day of issue only' | 'TRICORE TRADE SERVICES' | Wrong/loose entity name; correct site named | Project-specific (TEN16699) | Ex GST | Freight to site included as line ($2,950); fuel levy extra at prevailing rate at dispatch; unloading by others; 1 hr on site then demurrage; seals pre-fitted, bundles pre-slung | Unloading & installation by others | 'Approximately TBC'; T&C ~8-11 weeks | Freight line INCLUDED in total (do not add again); no escalation embedded (same-day validity) | 28,828.00 | HDPE SN8 storm pipe: 23x DN225 x6.28m @151 ($24.0/m); 36x DN375 x6.181m @353 ($57.1/m); 7x DN450 x6.121m @532 ($86.9/m); 7x DN600 x5.9m @829 ($140.5/m); 10x lube @17; freight $2,950. | Civil SW pipe (HDPE alternative to RCP/PVC) | 01 - Project Specific\Material\CIVIL SW QUOTE\CIVIL SW HDPE PIPE\ATLAN\26-87004-1 (SN8) ... - TRICORE.pdf
P04 | Humes (Holcim Australia) | Q21642316 | REV2 (24.07.26) | Quote - CURRENT revision | 16/07/26 | 'Valid to: 16.08.2026' / 'Quotation is valid for 30 days from issue' | TRICORE PLUMBING SERVICES P/L (TPS), PO Box 103 Rockhampton | Addressed to TPS although civil stormwater is TCS scope entity - entity mismatch to note at contract award. Ship-to 554-700 Yaamba Rd Norman Gardens = CORRECT site. | Project-specific (TEN16699) | Ex GST ('PRICES QUOTED ARE EXCLUSIVE OF G.S.T.') | Delivery Terms 'Delivered by us' - line 19: Freight to site FOT (customer to unload), 35 loads @710 = 24,850, 'less than 24km'. All unloading/cranage/rotation by others at no cost to Humes. 2-business-day delivery notice; Humes Service Fees schedule applies (waiting time $360/hr after first hour, etc.) | No liquidated damages; schedule of rates only (not lump sum); quantities to be checked by client - no responsibility if they differ; pricing subject to mould availability; no returns on made-to-order goods (incl large box culverts, MRTS headwalls, Class 4 pipes); steel shortage EOT clause; variation to supply scope may require re-pricing | Based on mould availability & order queue; updated at order confirmation | Freight INCLUDED as its own line in total (do not add freight again; DO add unload/cranage). No escalation embedded - 30-day validity; fuel levy regime flagged in Tender & Contract Terms. Rates are supply-only otherwise. | 296,267.24 | RCP + box culvert package: 299x Pipe 375x2.44 RJ Cl4 MRTS @256.20 + rings @4.80; 2x Pipe 600x2.44 Cl3 @447.90; headwalls 375 @380.80, 375 twin-cell @588.80; BC crowns: 900x450 x12 @1,404.80 / 1200x600 x8 @1,718.40 / 750x300 x3 @1,171.20 / 600x300 x15 @1,095.00; BCC headwalls: 900x450 x4 @2,425.63 / 1200x600 x2 @3,322.45 / 750x300 x1 @2,162.60 / 600x300 x8 @1,800.63 / 1500x600 x2 @4,222.78 / 2700x1200 x2 @5,241.45; Large box culverts AS1597.2: 1500x600x2.4 x13 @3,065.72; 2700x1200x2.4 x8 @5,891.95; freight 35 loads @710. Est delivered weight 186.31 t. | Civil SW RCP pipe, box culverts, headwalls | 01 - Project Specific\...\Humes\HUMES_Q21642316_REV2_...pdf.pdf
P05 | Humes (Holcim Australia) | Q21642316 | REV1 (16.07.26) | Quote - SUPERSEDED by REV2 | 16/07/26 | Valid to 16.08.2026 | TRICORE PLUMBING SERVICES P/L (TPS) | Same as REV2 | Project-specific - SUPERSEDED | Ex GST | As REV2 | As REV2 | As REV2 | As REV2 | 301,151.03 | Same scope as REV2. Differences vs REV2: BCC headwall 900x450 was 4,150.40 (now 2,425.63 = -1,724.77 ea); 750x300 was 1,792.35 (now 2,162.60); 600x300 was 1,595.00 (now 1,800.63). REV2 total is $4,883.79 lower. Use REV2 ONLY. | Civil SW RCP/box culverts/headwalls | 01 - Project Specific\...\Humes\SS_HUME QUOTE.pdf
P06 | Jaybro (Stephen Haslemore, BDM) | Email quote (no number) - 'RE: 260715 Quote request: rockhampton sport precinct' | - | Email quote (.msg) | 16/07/26 07:13 | None stated | Denis Zhong - TCS (cc Mitch - TCS) | Site correctly quoted in subject: 554-700 Yaamba Rd Norman Gardens | Project-specific (TEN16699) | 'all plus gst' | 'No allowance for freight' - freight EXCLUDED entirely | 'We don't do rcbc box culvert headwalls sorry' - ALL RCBC box-culvert headwalls (900x450, 1200x600, 1500x600, 600x300, 2700x1200, 750x300) DECLINED / unpriced. Grated trench schedule and Hauraton trash boxes in the request NOT priced in reply. | Not stated | No freight, no escalation, prices current-day. Must ADD freight to Rockhampton before use. | n/a (unit rates only) | Round/pipe headwalls only, priced inline: to suit 225 PVC $280 ea (qty 2); 375 RCP $372 ea (qty 5); 150 PVC $158 ea (qty 1); 2x375 RCP twin $1,670 ea (qty 2); 300 HDPE $352 ea (qty 1). Attachments: grated trench schedule image (GT1-GT9, no prices), TriCore logo, Jaybro banner - NO quote PDF attached. | Civil SW headwalls (round pipe only) | 01 - Project Specific\...\Jaybro\stephen quote.msg
P07 | Reece Australia (Civil, N Rockhampton br. 4070) | Q-459014445 ('ROCKY SPORTS') | - | Quote | 16/07/26 | Quote Expiry Date: 16/08/2026 | TRICORE CIVIL SERVICES PTY LTD (TCS) | Correct entity for civil scope; no site address on quote (order ref 'ROCKY SPORTS' only) | Project-specific (TEN16699) | Ex GST (columns show price before GST + GST) | Freight For Concrete: 25 loads @944.30 = 23,607.50, 'Customer To Unload'; $40+GST delivery fee per delivery, ground floor only; goods to be collected/delivered within 30 days of availability or storage fees | Most concrete/Hauraton lines flagged 'Specially Acquired Product (SAP) - supplier may not accept returns or handling fees may apply'; custom/specially-acquired products non-returnable & non-refundable | Not stated | Freight lines INCLUDED in total (do not add again for concrete; customer still to unload). No escalation embedded. NOTE embedded annotation on 550m Fibretec line: '550 $198.00 $108,900.00' - an apparent alternative/negotiated rate vs the invoiced 232.94/m ($128,117.00): clarify with Reece before adoption. | 444,084.12 | Stormwater: 70x DWV PVC 100 SN6 @43.07/6m; Stormpro SN8 poly: 21x225 @216.10, 10x300 @348.77, 33x375 @545.62, 7x600 @1,322.30; RCP Cl4: 262x375x2.44 @328.46 + rings, 17x450x2.44 @424.62, 1x600 Cl3 @574.23; 2x winged HW 375 @317.05; BC crowns: 900x450 x12 @1,599.77, 600x300 x16 @1,136.36, 750x300 x2 @1,330.91; LBC 1500x600 x8 @3,483.77, 2700x1200 x8 @6,797.67; concrete freight 25x944.30. HAURATON TRENCH DRAINS (approx. 162,349 ex GST subtotal): 32m Pro200 T010 G-tec ductile D @280.89; 550m Pro200 T010 Fibretec slotted B125 (47246) @232.94; 29m Pro100 T010 SS304 heelguard 200dp @368.24; trash boxes: 24x Pro200 Fibretec @535.29, 1x Pro200 G-tec @550.59, 4x Pro100 @214.12; end caps 10x23.53 + 8x9.41. | Civil SW pipe/culverts/headwalls + trench drains (Hauraton) - direct alternative to Humes P04 for concrete items | 01 - Project Specific\...\REECE CIVIL QUOTE FOR ALL\Q-459014445-260716_095312503-line.pdf
P08 | Australian Pump Solutions (APS) | Quote No 14065 | - | Quote (PDF owner-encrypted; opens w/ blank password) | 22/07/26 | None stated | Tricore Plumbing Services (TPS) | Correct entity; site 'Rockhampton Sports Precinct' | Project-specific - INTERFACE / ADD-PRICE EVIDENCE ONLY (pump station EXCLUDED from our scope per Addendum 2) | Ex GST (sub-totals ex GST + GST shown) | As-specified option: supply AND install incl delivery; FRP option: delivery to site included but 'lifting off transport by others', 30 min unloading allowed then extra charges | As-spec QMax: 'APS staff have NO involvement with design, manufacture, delivery, commissioning... all by Qmax'. FRP option EXCLUDES: mechanical installation on site; electrical conduits chamber-to-panel (min 2x65mm w/ LR bends); incoming power; cable extensions. Hot water pump excludes control panel, manifolding, power, installation, bypass pipework. | Not stated | MAJOR TRAP: As-specified $468,000 is SUPPLY + INSTALL + COMMISSIONING (progress payments: design 22,200 / deposit 95,040 / 327,360 pre-delivery / 23,400 at commissioning). It is NOT a material rate - do NOT apply material contingency/escalation multipliers built for supply-only rates, and the whole station is EXCLUDED scope anyway. | 555,195.00 (as-spec 468,000 + FRP option 85,950 + HW pump 1,245) | Sewer PS 10 L/s @10m: (a) QMax Fortis 3200 dia x 6700 deep as specified, dual Sulzer XFP80C, control panel/telemetry/HMI, install/test/commission/training/O&M = 468,000; (b) Option: FRP tank 2400 dia x 6700 (28.5kL), dual Sulzer XFP80C macerators, panel, transducer+float, delivery+commissioning (installation by others) = 85,950; (c) Grundfos UPS 25-60 N HW circulator = 1,245. | Pump station interface / add-price evidence; HWU circulation pump | 01 - Project Specific\Material\Hydraulic\APS SEWER STATION\Quote_No_14065 - Rockhampton Sports Precinct.pdf
P09 | Tradelink | 1065005 SP | Rev 15/07/26 (orig 03/07/26) | Quote - CURRENT revision (3 identical copies on file) | 15/07/26 | Prices valid for deliveries made by 02/08/26 - SHORTEST validity in the pack; then prevailing price | TRICORE PLUMBING SERVICES PTY LTD (TPS) | Addressed to TPS for civil SW materials (TCS scope) - entity mismatch; no site stated | Project-specific (TEN16699) | Ex GST | 'SF - SUPPLIER FREIGHT/HANDLING CHARGE' $3,750 line INCLUDED + Standard Delivery Fee $31.82+GST per delivery; non-metro increase clause | Package pricing - variation/deletion may require re-quote; 20% restocking; storage costs | Not stated | Supplier freight line ($3,750) already IN the total - do not add again. No escalation embedded; validity to 02/08/26 only. | 33,117.57 | SW pits & PVC: 450 pit @168.50 + Cl D grate&frame @228.90; 6x 600x600x600 HD pit @229.50 + 600 HD grate&frame @365.20; risers; 16x 300 SN8 x3m @302.10; 16x 225 SN8 x6m @776.50; 11x 150 SN8 x6m @220.10; SW junctions/bends/reducers; winged HW 300 @275.60; 225 HW @270.10; compact HW 90-150 @130.00; SF freight 3,750. | Civil SW pits/grates + SN8 PVC pipeline + headwalls | 01 - Project Specific\Material\Hydraulic\Tradelink\1065005...pdf (also filed: 01\...\quote reference...\tlink civil sw\ and 02\NAS_Material\...\pit and headwall\tradelink\)
P10 | Tradelink | 1065005 SP | Original 03/07/26 | Quote - SUPERSEDED by 15/07/26 revision (2 copies, NAS folders) | 03/07/26 | Deliveries by 02/08/26 | TPS | As P09 | Project-specific - SUPERSEDED | Ex GST | As P09 | As P09 | Not stated | As P09 | 52,522.57 | Earlier, larger take-off: includes 1050mm winged headwall @2,950.10 (deleted in rev) and different pit/pipe quantities; several rates re-cut in revision. Use P09 rev ONLY. | Civil SW pits/pipe/headwalls | 02 - Other Recent ROK Proj\NAS_Material\Material\civil storm water pipe line\tradelink\1065005...pdf + ss_ copy in pit and headwall\tradelink\
P11 | Tradelink | 1066334 SP | - | Quote | 17/07/26 | Prices valid for deliveries made by 16/08/26; then prevailing price | TRICORE CIVIL SERVICES PTY LTD (TCS) | Addressed TCS for hydraulic/pump-station package (TPS scope) - entity mismatch; no site stated | Project-specific (pump-station lines = interface/add-price evidence only - excluded per Addendum 2) | Ex GST | SF supplier freight $250 line + $31.82+GST per delivery; non-metro increase clause | Package pricing; 20% restocking; 'PLEASE CHECK WHAT SIZE IS NEEDED' (hose cock) | Not stated | TRAP: line 15780497 'MECHANICAL & ELECTRICAL INSTAL' $115,000 is INSTALLATION LABOUR inside a material quote - keep out of material-only escalation/contingency; pump-station lines are excluded scope. Freight line in total. | 454,113.65 | Pump station pack: QMax Fortis vessel + dual Sulzer XFP80C PE100 @281,000; M&E install @115,000; 'Sewer pump WSA 04-2005' @20,000 (station subtotal ~416,000). Trade waste: 1500L underground grease trap @6,110 + light top @1,308 / medium grate @2,004 / heavy @2,413.28. Water: RPZ 100mm complete @2,103; Woltman 100 meter @750.11; PD 32 meter @542.65; PRV 32 @360; 6x TMV AVG w/ SS cabinet @503.77; 5x RPZD 20 @210; butterfly/check valves. Equipment: Grundfos UPS20-60N dual circ @4,700; 3x Rheem 613/315 HWU @3,100; 1x Rheem 613/050 @1,900. | Pump station interface; trade waste (grease trap); water valves/meters/TMVs; equipment/HWU | 01 - Project Specific\Material\Hydraulic\Tradelink\1066334_TRICORE_CIVIL_SERVICES_PTY_LTD.pdf
P12 | Tradelink | 6595064 SQ | - | Quote (estimator IAN BAKER) | 21/07/26 | Prices valid for deliveries made by 20/08/26; then prevailing price | TRICORE PLUMBING SERVICES PTY LTD (TPS) | WRONG SITE header: '544 YAAMBA RD PARKHURST' (same error as 1066143); 'based on information supplied by you... does not constitute a take-off' | Project-specific (TEN16699) | Ex GST | $31.82+GST per delivery; non-metro increase clause | Quote is quantities-as-given, not a take-off | Not stated | No freight in rates; no escalation embedded (30-day delivery window). | 47,154.60 | DN200 copper main: 23x CU tube Type-B 200mm (203.2 OD, 14G) x6m @2,015/len (=335.83/m) = 46,345; 1x 200 HP weld elbow 90 @420; 1x 200 HP weld equal tee @389.60. This is the copper potable main the HDPE PE100 SDR11 O250 alternative would replace. | Water main (DN200 copper) - copper basis for the potable main | 01 - Project Specific\Material\Hydraulic\Tradelink\6595064_ROCKHAMPTON_SPORTS_PRECINCT.pdf
P13 | Reece Australia | Q-459014431 ('NETBALL') | - | Quote | 15/07/26 | Quote Expiry Date: 15/08/2026 | TRICORE CIVIL SERVICES PTY LTD (TCS) | Addressed TCS for hydraulic equipment package (TPS scope) - entity mismatch | Project-specific (pump-station line = interface/add-price evidence only) | Ex GST | StormFilter freight line 7,142.10 included; $40+GST per delivery ground floor only; 30-day collection window / storage fees | SAP lines non-returnable (stormfilter manhole, pump station) | Not stated | TRAPS: (1) 'Dual Pump Station Qmax Fortis 3200x6700 INSTALLATION AND COMMISSIONING' 523,170.73 is a supply+install lump sum AND excluded scope. (2) StormFilter line already has its own freight line (7,142.10) - do not add freight again. Rates otherwise supply-only, no escalation embedded. | 650,797.91 | KEY WSUD LINE: '22-cartridge 690mm Psorb Stormfilter Manhole' 1x @90,064.63 + freight 7,142.10 (this IS a project-specific price for the 22x Tall 690 PSorb + DN3300 manhole - single unpriced-detail lump line via Reece, verify against a direct Ocean Protect quote). Also: Graf 1500L grease trap Cl D @4,010.30; 3x Rheem 613/315 @3,438.29 + trays; Rheem 613/050 @2,016.08; Grundfos UPS32-80N dual @6,775.83; 6x TMV T160 20 @248.86 + recess boxes @241.80; 5x RPZ 20 @453.85; 316 press-fit tube rate-set: 22mm @64.68/6m, 28mm @80.63/6m, 35mm @132.03/6m + fittings (rate lines qty 1; NOTHING larger than 35mm); water meter 32 pulse @243.64; cleanouts, FW. | WSUD/filtration (StormFilter+manhole); trade waste; equipment/HWU; building rough-in valves; pump station interface; 316 SS press-fit rate basis | 01 - Project Specific\Material\Hydraulic\reece all package\equipment and material\Q-459014431-260716_062410652-line.pdf
P14 | Reece Australia | Q-459014438 ('TRADEWASTE') | - | Quote (rate set) | 16/07/26 | Quote Expiry Date: 16/08/2026 | TRICORE CIVIL SERVICES PTY LTD (TCS) | Entity mismatch as P13 | Project-specific (TEN16699) | Ex GST | $40+GST per delivery ground floor only | - | Not stated | Rate-set only (qty 1 lines) - unit rates for take-off pricing; no freight/escalation embedded | 285.92 (rate set) | Geberit HDPE trade waste rates: 110 pipe @84.16/5m; sleeve coupling @6.24; bends 45/88.5/15deg @4.73/5.55/15.39; junctions 45/88.5 @8.98/9.73; adj DT trap bottom @41.53; inspection opening @24.66; 4-way riser @32.47; expansion socket @12.48. | Trade waste (HDPE drainage) building rough-in | 01 - Project Specific\Material\Hydraulic\reece all package\trade waste\Q-459014438-260716_062210445-line.pdf
S01 | Humes (Holcim) | Humes Service Fees (from 1 Jan 2026) | - | Supporting document | 01/01/26 | Current from 1 Jan 2026 | - | - | Supporting document | Fees ex GST | Delivery notice 72h (48h +$325, 24h +$500); waiting time $360/hr after first 60 min ($520/hr OOH); min load 10t metro / 20t >75km; cancelled delivery $2,000/truck + original charge; additional drop $350; storage $35/day/unit std or 10%/wk non-std after 30 days | - | - | Applies on top of Humes quotes P04/C22 - allow for notice-period and waiting-time risk in programme, not in material rates | n/a | Fee schedule (see notes). | Civil SW supply logistics | Filed twice: project Humes folder + NAS humes folder
S02 | Humes (Holcim) | Tender & Contract Terms (April 2026) | - | Supporting document | Apr 2026 | - | - | - | Supporting document | - | - | No retentions/bank guarantees/parent guarantees; no LDs; liability cap + consequential loss exclusion required; fitness-for-purpose limited to common use; risk passes at commencement of unloading, title on payment; PI $10m / PL $20m; fuel levy regime may be required | - | Flags future fuel/steel escalation risk on Humes supply | n/a | Key commercial departures Humes will seek if awarded. | Civil SW supply terms | Filed twice: project + NAS Humes folders
S03 | Humes (Holcim) | Humes Terms of Sale (standard conditions) | - | Supporting document | - | - | - | - | Supporting document | Ex GST basis in cl. | - | Standard Holcim terms incl PPSA, returns at Humes discretion + service fees, title retention | - | - | n/a | Standard conditions of sale referenced by quotes. | - | Filed twice: project + NAS Humes folders
S04 | Humes (Holcim) | Direct deposit (bank) details | - | Supporting document | - | - | - | - | Supporting document | - | - | - | - | - | n/a | ANZ account details for payments (BSB 014002). | - | 02\NAS_Material\...\humes\DIRECT DEPOSIT DETAILS .pdf
C01 | Tradelink | 1057751 SP (CQU Rockhampton TAFE Consolidation Stage 2) | Rev 20/04/26 | Quote (comparable) - EXPIRED (2 identical copies) | 21/04/26 | Deliveries by 20/05/26 - EXPIRED | TPS | Header site '554/700 YAAMBA ROAD NORMAN GARDENS' = SAME precinct as TEN16699 (CQU TAFE job 27922524) - good locational comparability; job/date differ | Comparable-project reference | Ex GST | $31.82+GST per delivery | Package basis | Not stated | No freight/escalation in rates; EXPIRED Apr-26 rates - escalate before any use | 4,402.45 (rate set) | Copper rate schedule (Kembla/KemPress) 15-100mm: Type-B tube per 6m len: 100 @735.21, 80 @535.60, 65 @335.20, 50 @278.50, 40 @229.28, 32 @189.39, 25 @128.50, 20 @81.71, 15 @46.50 + press fittings each size. | Building rough-in copper benchmark (<=DN100) | 01 - Project Specific\Material\quote reference from previous or other project\tlink copper\ + 02\CQUTafe_Material\...\tradelink\ (copy)
C02 | Reece Australia | Q-459012370 ('ANACONDA') | - | Quote (comparable) - EXPIRED | 10/02/26 | Expiry 10/03/2026 - EXPIRED | TCS | Anaconda project, 337-341 Yaamba Rd Nth Rockhampton | Comparable-project reference | Ex GST | Pump station freight line 1,729 included; $40 delivery fee | SAP non-returnable | Not stated | Freight lines included per item; Feb-26 rates - escalate before use | 80,200.13 | Aline fibreglass holding well 1800x3000 w/ valves & auto-coupling @44,110 + freight 1,729; 4x Zip Hydrotap G5 BCHA20 @6,371.70; Everhot Pro 50L @1,551.58; meters/backflow: RPZ 40 @858.67, DCV 25 @430.67, meter cage @480.93. | Pump station (small) + equipment benchmark | 02\Anaconda_Material\big ticket item\reece\Q-459012370-...pdf
C03 | Reece Australia | Q-459012377 ('ANACONDA') | - | Quote (comparable) - EXPIRED | 10/02/26 | Expiry 10/03/2026 - EXPIRED | TCS | Anaconda project | Comparable-project reference | Ex GST | 'Delivery To Site Customer To Unload' 10 loads @877.80 included; $40 fee | SAP non-returnable | Not stated | Freight in total; Feb-26 rates - escalate; NOTE 375 RCP is 2.34m lengths (not 2.44m) - normalise per metre before comparing | 67,812.09 | Civil SW: 40x DWV PVC 225 SN8 @235.68/6m; 100x RCP Cl4 375x2.34 @209.80 (=89.7/m vs P04 Humes 105.0/m, P07 Reece 134.6/m); 22x RCP Cl4 450x2.44 @321.49; 25x RCP Cl4 600x2.44 @526.79; GMS trench grate D 300x2000 @368.75; BC 900x450x2.4 @1,782.41; BC crown 900x450x1.2 @953.49; freight 10x877.80. | Civil SW pipe benchmark | 02\Anaconda_Material\civil sw pipe\Reece\Q-459012377-...pdf
C04 | Ocean Protect | 19901 (337-341 Yaamba Rd Nth Rockhampton - Anaconda) | - | Quote (comparable) - EXPIRED | 05/03/26 | 'Validity Period: 30 Days' - EXPIRED ~04/04/26 | Tricore Civil Services P/L (Mitch Hannan) | Anaconda project - different site/scope/quantities; Rockhampton Regional council | Comparable-project reference | Ex GST (subtotal + GST shown) | 'Quoted freight prices based on units delivered Free on Truck (unloading by others), Mon-Fri'; precast freight line 8,000 + OceanGuard freight 1,200 included; 1 hr truck waiting then charges; special lifters returnable (else $400-$1,000+GST) | EXCLUDES: unloading & installation of tanks/modules; installation of cartridges & OceanGuards; cleaning/dewatering before fit-out; internal weir walls; risers/ladders/orifice plates/trash racks; inlet/outlet pipe connections; cranage & lifting equipment; site earthworks; joint sealing application | Confirmed after signed shop drawings & order acceptance | Freight lines included; Mar-26 rates, EXPIRED - re-quote/escalate; precast non-stock, made-to-order, non-refundable | 608,720.00 | 18-cart 690mm PSORB StormFilter DN3300 manhole @70,060; 13-cart 690mm PSORB DN3300 @60,460; precast freight @8,000; 22x OceanGuard 200 (to suit 900x900) @500 = 11,000 + freight 1,200; UrbanPond modular OSD 185kL @128,000; UrbanPond OSD 395kL @330,000. Implied cartridge increment (18 vs 13-cart) = 1,920/cartridge; manhole base ~35,500. | WSUD/filtration + OSD detention benchmark (basis for deriving 22-cartridge check estimate) | 02\Anaconda_Material\stormack...\ocean protect\19901 - ...pdf
C05 | Ocean Protect | 13C-DN3300-OP-SD | - | Technical reference | - | - | - | - | Comparable-project reference | - | - | - | - | - | n/a | Ocean Protect standard drawing: 13-cartridge StormFilter DN3300 manhole (design parameters, W80 rating, 690 PSORB SQIDEP 0.86 L/s/cartridge) | WSUD/OSD technical basis | 02\Anaconda_Material\stormack...\ocean protect\
C06 | Ocean Protect | 20C-DN3300-OP-SD | - | Technical reference | - | - | - | - | Comparable-project reference | - | - | - | - | - | n/a | Ocean Protect standard drawing: 20-cartridge StormFilter DN3300 manhole - closest published config to the 22-cartridge project requirement | WSUD/OSD technical basis | 02\Anaconda_Material\stormack...\ocean protect\
C07 | Ocean Protect | OceanGuard Installation Guide 07/24 | - | Technical reference | - | - | - | - | Comparable-project reference | - | - | - | - | - | n/a | Pit-insert installation methodology (install labour benchmark input) | WSUD/OSD technical basis | 02\Anaconda_Material\stormack...\ocean protect\
C08 | Ocean Protect | StormFilter Installation Guide 09/22 | - | Technical reference | - | - | - | - | Comparable-project reference | - | - | - | - | - | n/a | Cartridge/manhole installation methodology - contractor grouting, sealant, false floor duties | WSUD/OSD technical basis | 02\Anaconda_Material\stormack...\ocean protect\
C09 | Ocean Protect | UrbanPond Flyer 2024 | - | Technical reference | - | - | - | - | Comparable-project reference | - | - | - | - | - | n/a | Marketing/technical overview of modular OSD | WSUD/OSD technical basis | 02\Anaconda_Material\stormack...\ocean protect\
C10 | Ocean Protect | UrbanPond Installation Manual 2024 | - | Technical reference | - | - | - | - | Comparable-project reference | - | - | - | - | - | n/a | Install duties by others: bedding, backfill, sealing, cranage - scope items to price in install labour | WSUD/OSD technical basis | 02\Anaconda_Material\stormack...\ocean protect\
C11 | Ocean Protect | UrbanPond-OP-WO_OUTLET drawing | - | Technical reference | - | - | - | - | Comparable-project reference | - | - | - | - | - | n/a | Spec drawing: min bearing 150kPa, Class D covers, anti-flotation by others, S50 concrete | WSUD/OSD technical basis | 02\Anaconda_Material\stormack...\ocean protect\
C12 | Reece Australia | Q-459013148 (CQU) | - | Quote (comparable) - EXPIRED | 14/04/26 | Expiry 13/05/2026 - EXPIRED | TCS | CQU Rockhampton TAFE | Comparable-project reference | Ex GST | Tank freight lines included (both tanks 4,279.94; Bushmans 1,995); $40 fee | SAP non-returnable | Not stated | Freight per line; Apr-26 rates - escalate | 376,063.66 | Halgan 5000L grease trap Cl D @12,055.68; OWHS 5000 @14,874.55; 30,000L Bushman tank @211,120; 2x 15,000L @19,604; PRV Bermad-type 720 rate set 50-200mm (2,471.18-10,813.53); full RPZ/DCV rate set 15-50; Zip Hydrotaps @8,365-8,368; Rheem 613/315 @3,354.49; Grundfos UPS20-60N dual @6,126.09; Stiebel instantaneous HWUs. | Trade waste / tanks / valves / equipment benchmark | 02\CQUTafe_Material\big ticket and misc\Reece\Q-459013148-...pdf
C13 | Australian Pump Solutions (APS) | Quote No 13825 (CQU Rockhampton) | - | Quote (comparable; PDF owner-encrypted, blank password) | 15/04/26 | None stated | Tricore Plumbing Services (TPS) | CQU project | Comparable-project reference | Ex GST | Freight lines per pump set included ('delivery to site - unloading by others'; freight pricing must be confirmed at time of order); 30 min unload allowance | SDPS excludes delivery-lift-off, commissioning-after-install-by-others wording varies per section; excludes incoming power, mech/elec site installation, cable extensions | Not stated | Freight included per line but 'must be confirmed at time of order'; commissioning priced separately @9,065 - avoid double-carry | 84,745.16 | SDPS 3 L/s @35m FRP 2400x2800 dual Grundfos SEG40 @35,563 + freight 8,965; HW primary pump @3,560; 2x HWC pump sets @4,845; 2x rainwater pumps @2,092; rainwater filters @4,135.88; ice machine filters @4,258; commissioning @9,065. | Pump/equipment benchmark | 02\CQUTafe_Material\big ticket and misc\aps pumps\Quote_No_13825 - CQU Rockhampton.pdf
C14 | Jaybro Group | 20024961 ('Pits & Grates') | - | Quote (comparable) - EXPIRED | 13/04/26 | Quote Expiry 04/05/2026 - EXPIRED | Tricore Civil Services Pty Ltd ATF The Tricore Services Trust | Ship-to Moores Creek Road (CQU) | Comparable-project reference | Ex GST (net + GST shown) | Shipping cond. 'Reg & InSt Bulk'; no freight line | Starred items non-returnable | Not stated | No freight line - add freight; Apr-26 rates | 1,418.06 | Poly pit rate set: P30 300x300x450 @89.62 + grate @37.92; P45 450x450x600 @165.02 + riser @94.32 + grate @83.53; P60 600x600x600 @227.23 + riser @129.97 + grate @146.58; AS2000 SS-edge polymer channel @157.41/unit + 223mm Cl B SS heelguard grate @242.46. | Civil SW pits benchmark (poly) | 02\CQUTafe_Material\big ticket and misc\jaybro\Tricore Civil - Pits.pdf
C15 | Tradelink | 1057331 SP (CQU) | Rev 20/04/26 | Quote (comparable) - EXPIRED | 20/04/26 | Deliveries by 15/05/26 - EXPIRED | TPS | CQU project | Comparable-project reference | Ex GST | $31.82+GST per delivery | Package basis | Not stated | No freight/escalation in rates; Apr-26 - escalate | 156,578.63 | Valve/backflow/TMV rate schedule: AGA lever ball valves 10-80; sluice valves 80-200 (246.50-795.60); butterfly valves; Aquablend 1000/2500 TMVs + SS cabinets; Valvcheq RPZ complete 15-50 (412.30-926.50); DCV 007 sets 15-50; Zip Flushmaster sensor @1,056.30; trap primer @475.60. | Water valves/TMV/backflow benchmark | 02\CQUTafe_Material\big ticket and misc\tradelink\1057331_...260420.pdf
C16 | Tradelink | 1057331 SP (CQU) | Orig 15/04/26 | Quote (comparable) - SUPERSEDED by 20/04 rev | 15/04/26 | Deliveries by 15/05/26 | TPS | CQU project | Comparable - SUPERSEDED | Ex GST | As C15 | As C15 | - | As C15 | 130,709.71 | Earlier smaller cut of the same schedule. Use C15. | Water valves benchmark | 02\CQUTafe_Material\...\tradelink\1057331_...pdf
C17 | Tradelink | 1060158 SP (NAS-Rockhampton Warehouse) | - | Quote (comparable) - EXPIRED | 14/05/26 | Deliveries by 13/06/26 - EXPIRED | TPS | NAS warehouse project | Comparable-project reference | Ex GST (care items GST-free) | $31.82+GST per delivery | Package basis | Not stated | No freight/escalation in rates | 29,533.84 | Fixture set: Care 400 suite @737.10; 4x Opal CleanFlush suite @827.27; Cube 500 basins @443.54; care mixers @221.24; urinal kit @723.81; showers/rails. | Fixtures benchmark (small commercial) | 02\NAS_Material\Fixtures\1060158_NAS-ROCKHAMPTON_WAREHOUSE.pdf
C18 | Tradelink | 1067047 SP (NAS Office & Warehouse - 26608534) | - | Quote (comparable) | 24/07/26 | Printed 'deliveries made by 13/09/25' (as printed - apparent misprint; quote dated 24/07/26) | TPS | 737 Yamba Road Parkhurst; 'PRODUCTS AND QUANTITIES TO BE CONFIRMED' | Comparable-project reference | Ex GST | Standard Delivery Fee $22.72+GST per delivery (<$100 = $45.45+GST) | Products & quantities TBC | Not stated | No freight/escalation in rates | 21,643.27 | NAS fixture package (current pricing basis for similar Caroma/Stoddart items). | Fixtures benchmark | 02\NAS_Material\Fixtures\1067047_NAS_OFFICE_&_WAREHOUSE_-_26608534.pdf
C19 | Nitren (client schedule) / Tradelink prices | NAS OF Nitren fixture schedule.xlsx (2 versions, minor rate diffs) | - | Fixture schedule (xlsx) | - | - | - | Two versions on file: 'Copy' totals 14,651.71; 'ss_' version has slightly different rates (e.g. 987919BAG 737.10 vs 729.07; 631010W 547.24 vs 421.37) | Comparable-project reference | Rates appear ex GST | - | - | - | Client-side schedule with rates keyed from Tradelink quotes - NOT a supplier offer | 14,651.71 (Copy version) | FF&E schedule w/ marks (F20-F42): Cosmo Sovereign Care suite 729.07; Opal suites 806.67; Cube 500 461.71; Hydrotap G5 BCS20 5,698.16; urinal 1,150.12. | Fixtures schedule format reference | 02\NAS_Material\Fixtures\NAS OF Nitren fixture schedule - Copy.xlsx + ss_ version
C20 | Reece Australia | Q-459014437 (NAS) | - | Quote (comparable) - CURRENT | 16/07/26 | Expiry 16/08/2026 | TCS | NAS project | Comparable-project reference | Ex GST | $40+GST per delivery ground floor | SAP terms | Not stated | No freight/escalation in rates; current Jul-26 pricing - best PE100 benchmark on file | 35,011.65 | Water/fire main rates: PE100 PN16 blue-stripe 125 @186.65/6m (31.1/m); 50 coils @802/150m; 40 @241.42/50m; Friatec EF couplers 125 @36.28, tap tees 125x40 @173.53; hydrant riser twin @399.13; Cu rough-in: Ardent HD 25 @147.13/len; sewer/underslab DWV rates; Evopex PEX rates; TMV/RPZ singles. | Water/fire mains (PE100) + rough-in benchmark | 02\NAS_Material\Material\hydraluic material\reece\Q-459014437-...pdf
C21 | Tradelink | 1066369 SP (NAS) | - | Quote (comparable) - CURRENT | 17/07/26 | Deliveries by 16/08/26 | TCS | NAS project | Comparable-project reference | Ex GST | $31.82+GST per delivery | Package basis | Not stated | No freight/escalation in rates | 20,520.51 | Hydraulic DWV/PE/copper smalls: DWV multilayer SN6 100 @29.00/6m; PE 125 PN16 @198.50/6m; EF fittings; Cu 20 @96.94/6m; tundish @68.50. | Sewer/water rough-in benchmark | 02\NAS_Material\Material\hydraluic material\tradelink\1066369_...pdf
C22 | Humes (Holcim) | Q21641195 | REV1 (06.07.26) | Quote (comparable) - CURRENT | 06/07/26 | Valid to 06.08.2026 | TRICORE PLUMBING (TPS) | NAS project 787 Yaamba Rd Parkhurst | Comparable-project reference | Ex GST | Freight FOT to site customer-to-unload <24km @710/load included; same Humes terms as P04 | Same Humes standard clauses (no LDs, schedule of rates, quantities client-checked) | Based on mould availability | Freight line in total; current Jul-26 pricing | 6,155.53 | Precast pits: 600x600x600 base @423.20; riser 600x600x300 @228.45; 600 Cl D drop-in grate @325.45; headwall 375 AS @399.73; freight @710. | Civil SW pits/headwall benchmark (Humes vs Jaybro/Tradelink cross-check) | 02\NAS_Material\Material\pit and headwall\humes\HUMES_Q21641195_REV1_...pdf
C23 | Jaybro Group | 20043160 | - | Quote (comparable) - just expired | 02/07/26 | Quote Expiry 22/07/2026 - EXPIRED | Tricore Civil Services Pty Ltd ATF The Tricore Services Trust | NAS 787 Yaamba Rd Parkhurst | Comparable-project reference | Ex GST | FREIGHT-REGIONAL line 1,250 included | Starred items non-returnable | Not stated | Freight line in total (regional freight to Rockhampton 1,250/lot benchmark) | 10,719.00 | Concrete pit rate set: 450x450x450 base @151; 600x600x600 base @205; risers 107-146; hinged G&F Cl D 450 @475 / 600 @583; drop-in G&F Cl D 450 @144 / 600 @193; HW 300 SRC @352; HW small 100-225 @280; mini HW @130; freight 1,250. | Civil SW pits/grates/headwalls benchmark | 02\NAS_Material\Material\pit and headwall\jaybro\tricore 20043160.pdf

## KeyRates
Supplier | Quote ref | Item | Unit | Rate ex GST | Ex GST? | Freight included in rate? | Escalation embedded? | Safe to x1.18 contingency? | Safe to x1.38 escalation-to-2027? | Notes / double-count flags
Humes | Q21642316 R2 | RCP 375 Class 4 RJ MRTS (2.44m eff.) | len (2.44m) | 256.2 | Y | N (freight is separate line) | N | Y | Y - needed once | Supply-only rate; unloading/cranage by others; add crane. Made-to-order, non-returnable.
Humes | Q21642316 R2 | 375 rubber ring | ea | 4.8 | Y | N (freight is separate line) | N | Y | Y - needed once | Supply-only rate; unloading/cranage by others; add crane. Made-to-order, non-returnable.
Humes | Q21642316 R2 | RCP 600 Class 3 (2.44m) | len | 447.9 | Y | N (freight is separate line) | N | Y | Y - needed once | Supply-only rate; unloading/cranage by others; add crane. Made-to-order, non-returnable.
Humes | Q21642316 R2 | Headwall 375mm | ea | 380.8 | Y | N (freight is separate line) | N | Y | Y - needed once | Supply-only rate; unloading/cranage by others; add crane. Made-to-order, non-returnable.
Humes | Q21642316 R2 | Headwall 375mm twin cell | ea | 588.8 | Y | N (freight is separate line) | N | Y | Y - needed once | Supply-only rate; unloading/cranage by others; add crane. Made-to-order, non-returnable.
Humes | Q21642316 R2 | BC crown 900x450x2.4 MRTS | ea | 1404.8 | Y | N (freight is separate line) | N | Y | Y - needed once | Supply-only rate; unloading/cranage by others; add crane. Made-to-order, non-returnable.
Humes | Q21642316 R2 | BCC headwall 900x450 AS | ea | 2425.63 | Y | N (freight is separate line) | N | Y | Y - needed once | Supply-only rate; unloading/cranage by others; add crane. Made-to-order, non-returnable.
Humes | Q21642316 R2 | BC crown 1200x600x2.4 MRTS | ea | 1718.4 | Y | N (freight is separate line) | N | Y | Y - needed once | Supply-only rate; unloading/cranage by others; add crane. Made-to-order, non-returnable.
Humes | Q21642316 R2 | BCC headwall 1200x600 AS | ea | 3322.45 | Y | N (freight is separate line) | N | Y | Y - needed once | Supply-only rate; unloading/cranage by others; add crane. Made-to-order, non-returnable.
Humes | Q21642316 R2 | BC crown 750x300x2.4 MRTS | ea | 1171.2 | Y | N (freight is separate line) | N | Y | Y - needed once | Supply-only rate; unloading/cranage by others; add crane. Made-to-order, non-returnable.
Humes | Q21642316 R2 | BCC headwall 750x300 AS | ea | 2162.6 | Y | N (freight is separate line) | N | Y | Y - needed once | Supply-only rate; unloading/cranage by others; add crane. Made-to-order, non-returnable.
Humes | Q21642316 R2 | BC crown 600x300x2.4 MRTS | ea | 1095 | Y | N (freight is separate line) | N | Y | Y - needed once | Supply-only rate; unloading/cranage by others; add crane. Made-to-order, non-returnable.
Humes | Q21642316 R2 | BCC headwall 600x300 AS | ea | 1800.63 | Y | N (freight is separate line) | N | Y | Y - needed once | Supply-only rate; unloading/cranage by others; add crane. Made-to-order, non-returnable.
Humes | Q21642316 R2 | Large box culvert 1500x600x2.4 AS1597.2 | ea | 3065.72 | Y | N (freight is separate line) | N | Y | Y - needed once | Supply-only rate; unloading/cranage by others; add crane. Made-to-order, non-returnable.
Humes | Q21642316 R2 | BCC headwall 1500x600 AS | ea | 4222.78 | Y | N (freight is separate line) | N | Y | Y - needed once | Supply-only rate; unloading/cranage by others; add crane. Made-to-order, non-returnable.
Humes | Q21642316 R2 | Large box culvert 2700x1200x2.4 AS1597.2 | ea | 5891.95 | Y | N (freight is separate line) | N | Y | Y - needed once | Supply-only rate; unloading/cranage by others; add crane. Made-to-order, non-returnable.
Humes | Q21642316 R2 | BCC headwall 2700x1200 AS | ea | 5241.45 | Y | N (freight is separate line) | N | Y | Y - needed once | Supply-only rate; unloading/cranage by others; add crane. Made-to-order, non-returnable.
Humes | Q21642316 R2 | Freight to site FOT <24km (customer to unload) | load | 710 | Y | is freight | N | Y | Y | Do NOT add a second freight allowance on top of quote total - 35 loads already in the $296,267.24.
Reece | Q-459014445 | RCP 375 Class 4 (2.44m) | len | 328.46 | Y | N (freight separate line) | N | Y | Y | Supply-only, SAP non-returnable. vs Humes 256.20 - Humes cheaper by 72.26/len (~21.6k over 299)
Reece | Q-459014445 | RCP 450 Class 4 (2.44m) | len | 424.62 | Y | N (freight separate line) | N | Y | Y | Supply-only, SAP non-returnable. No Humes equivalent on P04 - only source for DN450 RCP
Reece | Q-459014445 | RCP 600 Class 3 (2.44m) | len | 574.23 | Y | N (freight separate line) | N | Y | Y | Supply-only, SAP non-returnable. vs Humes 447.90
Reece | Q-459014445 | Stormpro poly SN8 225 (5.99m) | len | 216.1 | Y | N (freight separate line) | N | Y | Y | Supply-only, SAP non-returnable. vs Atlan DN225 SN8 151.00/6.28m - Atlan cheaper/m
Reece | Q-459014445 | Stormpro poly SN8 375 (5.93m) | len | 545.62 | Y | N (freight separate line) | N | Y | Y | Supply-only, SAP non-returnable. vs Atlan DN375 353.00/6.181m - Atlan cheaper/m
Reece | Q-459014445 | Stormpro poly SN8 600 (5.85m) | len | 1322.3 | Y | N (freight separate line) | N | Y | Y | Supply-only, SAP non-returnable. vs Atlan DN600 829.00/5.9m - Atlan cheaper/m
Reece | Q-459014445 | DWV PVC 100 SN6 SWJ (6m) | len | 43.07 | Y | N (freight separate line) | N | Y | Y | Supply-only, SAP non-returnable.
Reece | Q-459014445 | BC crown 900x450x2.4 | ea | 1599.77 | Y | N (freight separate line) | N | Y | Y | Supply-only, SAP non-returnable. vs Humes 1404.80
Reece | Q-459014445 | BC crown 600x300x2.4 | ea | 1136.36 | Y | N (freight separate line) | N | Y | Y | Supply-only, SAP non-returnable. vs Humes 1095.00
Reece | Q-459014445 | BC crown 750x300x2.4 | ea | 1330.91 | Y | N (freight separate line) | N | Y | Y | Supply-only, SAP non-returnable. vs Humes 1171.20
Reece | Q-459014445 | LBC 1500x600x2.4 | ea | 3483.77 | Y | N (freight separate line) | N | Y | Y | Supply-only, SAP non-returnable. vs Humes 3065.72; qty 8 vs Humes 13 - reconcile take-off
Reece | Q-459014445 | LBC 2700x1200x2.4 | ea | 6797.67 | Y | N (freight separate line) | N | Y | Y | Supply-only, SAP non-returnable. vs Humes 5891.95
Reece | Q-459014445 | Winged concrete headwall 375 | ea | 317.05 | Y | N (freight separate line) | N | Y | Y | Supply-only, SAP non-returnable. vs Humes 380.80 / Jaybro 372.00
Reece | Q-459014445 | Freight for concrete (customer to unload) | load | 944.3 | Y | is freight | N | Y | Y | 25 loads in total; do not double-add freight.
Reece | Q-459014445 (Hauraton) | Hauraton Recyfix PRO200 T010 + G-tec ductile iron grate (Cl D) | m | 280.89 | Y | N | N | Y | Y | GT-schedule: check GT6 needs PRO100 D400 G-tec (code 47245) - NOT this Pro200 line; qty 32m aligns with GT6 31.4m - VERIFY substitution accepted
Reece | Q-459014445 (Hauraton) | Hauraton Recyfix PRO200 T010 + Fibretec slotted grate B125 (47246) | m | 232.94 | Y | N | N | Y | Y | 550m; embedded annotation '$198.00 / $108,900.00' suggests a negotiated alternative rate - confirm with Reece before pricing
Reece | Q-459014445 (Hauraton) | Hauraton Recyfix PRO100 T010 + SS304 heelguard wedgewire grate, 200 deep | m | 368.24 | Y | N | N | Y | Y | 29m for GT5/7/8/9
Reece | Q-459014445 (Hauraton) | PRO200 trash box w/ galv mud bucket + Fibretec grate | ea | 535.29 | Y | N | N | Y | Y | 24 off
Reece | Q-459014445 (Hauraton) | PRO100 trash box w/ PE mud bucket + Fibretec grate | ea | 214.12 | Y | N | N | Y | Y | 4 off
Reece | Q-459014445 (Hauraton) | PRO200 trash box w/ G-tec ductile grate D400 | ea | 550.59 | Y | N | N | Y | Y | 1 off
Reece | Q-459014445 (Hauraton) | End cap PRO/NC200 T010 w/ DN100 PVC outlet | ea | 23.53 | Y | N | N | Y | Y
Reece | Q-459014445 (Hauraton) | End cap closed PRO100 T010 200 deep | ea | 9.41 | Y | N | N | Y | Y
Atlan | 26-87004-1 | AtlanFlow DN225 SN8 pipe & seal (6.28m) | len | 151 | Y | N (freight separate line 2,950/lot) | N | Caution - price valid day of issue only | Y - but re-quote first | Same-day validity: treat as indicative; re-confirm before submission.
Atlan | 26-87004-1 | AtlanFlow DN375 SN8 (6.181m) | len | 353 | Y | N (freight separate line 2,950/lot) | N | Caution - price valid day of issue only | Y - but re-quote first | Same-day validity: treat as indicative; re-confirm before submission.
Atlan | 26-87004-1 | AtlanFlow DN450 SN8 (6.121m) | len | 532 | Y | N (freight separate line 2,950/lot) | N | Caution - price valid day of issue only | Y - but re-quote first | Same-day validity: treat as indicative; re-confirm before submission.
Atlan | 26-87004-1 | AtlanFlow DN600 SN8 (5.9m) | len | 829 | Y | N (freight separate line 2,950/lot) | N | Caution - price valid day of issue only | Y - but re-quote first | Same-day validity: treat as indicative; re-confirm before submission.
Atlan | 26-87004 | WSUD/detention package (38 Stormsack + 10 FIL-3.0 + 14.9kL tank + cover + freight + commissioning) | lot | 88838 | Y | Y (freight in lump sum; fuel levy extra) | Caution - day-of-issue validity | N - do not add freight or commissioning again; add fuel levy + cranage | Y - but re-quote on MUSIC model | 'High level estimate only' pending MUSIC model - must be re-proposed.
Jaybro | Email 16/07/26 | Headwall to suit 225 PVC | ea | 280 | Y | N - 'No allowance for freight' | N | Y - AFTER adding freight | Y | Email quote; RCBC box culvert headwalls DECLINED ('We don't do rcbc box culvert headwalls'). Twin 375 @1,670 vs Humes 588.80 - use Humes.
Jaybro | Email 16/07/26 | Headwall to suit 375 RCP | ea | 372 | Y | N - 'No allowance for freight' | N | Y - AFTER adding freight | Y | Email quote; RCBC box culvert headwalls DECLINED ('We don't do rcbc box culvert headwalls'). Twin 375 @1,670 vs Humes 588.80 - use Humes.
Jaybro | Email 16/07/26 | Headwall to suit 150 PVC | ea | 158 | Y | N - 'No allowance for freight' | N | Y - AFTER adding freight | Y | Email quote; RCBC box culvert headwalls DECLINED ('We don't do rcbc box culvert headwalls'). Twin 375 @1,670 vs Humes 588.80 - use Humes.
Jaybro | Email 16/07/26 | Headwall to suit 2x375 RCP (twin) | ea | 1670 | Y | N - 'No allowance for freight' | N | Y - AFTER adding freight | Y | Email quote; RCBC box culvert headwalls DECLINED ('We don't do rcbc box culvert headwalls'). Twin 375 @1,670 vs Humes 588.80 - use Humes.
Jaybro | Email 16/07/26 | Headwall to suit 300 HDPE | ea | 352 | Y | N - 'No allowance for freight' | N | Y - AFTER adding freight | Y | Email quote; RCBC box culvert headwalls DECLINED ('We don't do rcbc box culvert headwalls'). Twin 375 @1,670 vs Humes 588.80 - use Humes.
Tradelink | 1065005 R1 | 450x450x450 concrete pit | ea | 168.5 | Y | N (delivery fees / SF lines separate) | N | Y | Y | vs Jaybro 151.00 / Humes n/a
Tradelink | 1065005 R1 | 600x600x600 HD concrete pit (80 wall) | ea | 229.5 | Y | N (delivery fees / SF lines separate) | N | Y | Y | vs Jaybro 205.00 / Humes 423.20
Tradelink | 1065005 R1 | 600x600 Cl D grate & frame (HD) | ea | 365.2 | Y | N (delivery fees / SF lines separate) | N | Y | Y | vs Jaybro hinged 583 / drop-in 193 / Humes drop-in 325.45
Tradelink | 1065005 R1 | PVC SN8 DWV 225 SWJ (6m) | len | 776.5 | Y | N (delivery fees / SF lines separate) | N | Y | Y | vs Reece Stormpro 225 216.10 & Atlan 151.00 - PVC vs PP/HDPE class check before comparing
Tradelink | 1065005 R1 | PVC SN8 DWV 150 SWJ (6m) | len | 220.1 | Y | N (delivery fees / SF lines separate) | N | Y | Y
Tradelink | 1065005 R1 | Supplier freight/handling (lot) | lot | 3750 | Y | N (delivery fees / SF lines separate) | N | Y | Y | Already inside the 33,117.57 total - do not add again
Tradelink | 6595064 | CU tube Type-B DN200 (203.2 OD 14G, 6m) | len | 2015 | Y | N (delivery fees / SF lines separate) | N | Y | Y
Tradelink | 1066143 | Urban CF400-PREMIUM wall-mount chilled fountain DFCF400P | ea | 11050 | Y | N (delivery fees / SF lines separate) | N | Y | Y | 4 off (2 clubhouse + 2 amenities); signage extra; NON-chilled CF400 variant NOT quoted - gap
Tradelink | 1066143 | Billi Quadra 4180 boil/chill unit | ea | 7652.2 | Y | N (delivery fees / SF lines separate) | N | Y | Y | 5 off
Tradelink | 1066143 | Custom L-shaped SS bench SPPL.BE.1925.700.2290.600 | ea | 4986.5 | Y | N (delivery fees / SF lines separate) | N | Y | Y | 5 off - custom order form required
Tradelink | 1066143 | SS ambulant toilet suite w/ seat | ea | 3450.1 | Y | N (delivery fees / SF lines separate) | N | Y | Y | 5 off
Tradelink | 1066334 | QMax Fortis vessel + dual Sulzer XFP80C (supply) | ea | 281000 | Y | N (delivery fees / SF lines separate) | N | Y | Y | EXCLUDED SCOPE (Addendum 2) - interface evidence only
Tradelink | 1066334 | Mechanical & electrical installation (pump stn) | lot | 115000 | Y | N (delivery fees / SF lines separate) | N | Y | Y | INSTALL LABOUR in a material quote - never multiply as material
Tradelink | 1066334 | 1500L underground grease trap | ea | 6110 | Y | N (delivery fees / SF lines separate) | N | Y | Y | vs Reece Graf 1500L 4,010.30 - Reece cheaper
Tradelink | 1066334 | Rheem 613/315 HWU 3x3.6kW | ea | 3100 | Y | N (delivery fees / SF lines separate) | N | Y | Y | vs Reece 3,438.29 - Tradelink cheaper
Tradelink | 1066334 | TMV AVG w/ SS cabinet TMV15-PIB | ea | 503.77 | Y | N (delivery fees / SF lines separate) | N | Y | Y | 6 off
Tradelink | 1066334 | RPZ device 100mm complete | ea | 2103 | Y | N (delivery fees / SF lines separate) | N | Y | Y
Reece | Q-459014431 | 22-cartridge 690mm PSorb StormFilter manhole (supply) | ea | 90064.63 | Y | N unless noted | N | Y (except excluded/lump lines) | Y (except excluded/lump lines) | PROJECT-SPECIFIC price for the 22x Tall 690 PSorb + DN3300 - single lump SAP line; verify vs direct Ocean Protect quote (OP 19901 derivation ~52-57k+esc for 22-cart excl freight - large gap, interrogate scope)
Reece | Q-459014431 | Freight - StormFilter manhole | lot | 7142.1 | Y | N unless noted | N | Y (except excluded/lump lines) | Y (except excluded/lump lines) | Already in quote total - no second freight
Reece | Q-459014431 | QMax Fortis 3200x6700 dual pump station incl INSTALLATION AND COMMISSIONING | lot | 523170.73 | Y | N unless noted | N | Y (except excluded/lump lines) | Y (except excluded/lump lines) | Supply+install lump sum; EXCLUDED SCOPE - evidence only; do not multiply
Reece | Q-459014431 | Graf 1500L grease trap w/ CI lid Cl D | ea | 4010.3 | Y | N unless noted | N | Y (except excluded/lump lines) | Y (except excluded/lump lines)
Reece | Q-459014431 | Rheem 613/315 HWU | ea | 3438.29 | Y | N unless noted | N | Y (except excluded/lump lines) | Y (except excluded/lump lines)
Reece | Q-459014431 | Rheem 613/050 HWU | ea | 2016.08 | Y | N unless noted | N | Y (except excluded/lump lines) | Y (except excluded/lump lines)
Reece | Q-459014431 | Grundfos UPS32-80N dual SS HWC deluxe | ea | 6775.83 | Y | N unless noted | N | Y (except excluded/lump lines) | Y (except excluded/lump lines) | vs Tradelink UPS20-60N 4,700 - different models, check spec
Reece | Q-459014431 | Press-fit 316 SS tube 22mm (6m) | len | 64.68 | Y | N unless noted | N | Y (except excluded/lump lines) | Y (except excluded/lump lines) | Rate-only line; >35mm NOT priced by anyone; Tradelink refused - GAP
Reece | Q-459014431 | Press-fit 316 SS tube 28mm (6m) | len | 80.63 | Y | N unless noted | N | Y (except excluded/lump lines) | Y (except excluded/lump lines)
Reece | Q-459014431 | Press-fit 316 SS tube 35mm (6m) | len | 132.03 | Y | N unless noted | N | Y (except excluded/lump lines) | Y (except excluded/lump lines)
Reece | Q-459014431 | Tomson TMV T160 20mm LF | ea | 248.86 | Y | N unless noted | N | Y (except excluded/lump lines) | Y (except excluded/lump lines)
Reece | Q-459014431 | Valvcheq RPZ w/ ball valves 20mm | ea | 453.85 | Y | N unless noted | N | Y (except excluded/lump lines) | Y (except excluded/lump lines)
Ocean Protect | 19901 (comparable, EXPIRED) | 18-cartridge 690 PSORB StormFilter DN3300 manhole | ea | 70060 | Y | see note | N | Benchmark only - re-base + escalate | Benchmark only | COMPARABLE reference - record scope/date/location/spec/freight/qty deltas before any use. Mar-26 Anaconda; FOT unloading by others
Ocean Protect | 19901 | 13-cartridge 690 PSORB StormFilter DN3300 manhole | ea | 60460 | Y | see note | N | Benchmark only - re-base + escalate | Benchmark only | COMPARABLE reference - record scope/date/location/spec/freight/qty deltas before any use. Implies ~1,920/cartridge increment + ~35.5k manhole base
Ocean Protect | 19901 | OceanGuard 200 pit insert (to 900x900) | ea | 500 | Y | see note | N | Benchmark only - re-base + escalate | Benchmark only | COMPARABLE reference - record scope/date/location/spec/freight/qty deltas before any use. 22 off on Anaconda
Ocean Protect | 19901 | UrbanPond modular OSD 185kL | lot | 128000 | Y | see note | N | Benchmark only - re-base + escalate | Benchmark only | COMPARABLE reference - record scope/date/location/spec/freight/qty deltas before any use. ~692/kL
Ocean Protect | 19901 | UrbanPond modular OSD 395kL | lot | 330000 | Y | see note | N | Benchmark only - re-base + escalate | Benchmark only | COMPARABLE reference - record scope/date/location/spec/freight/qty deltas before any use. ~835/kL
Ocean Protect | 19901 | Freight precast to site (Rockhampton) | lot | 8000 | Y | see note | N | Benchmark only - re-base + escalate | Benchmark only | COMPARABLE reference - record scope/date/location/spec/freight/qty deltas before any use. Mar-26 freight benchmark
Reece | Q-459012377 (comparable, EXPIRED) | RCP 375 Class 4 (2.34m! not 2.44m) | len | 209.8 | Y | see note | N | Benchmark only - re-base + escalate | Benchmark only | COMPARABLE reference - record scope/date/location/spec/freight/qty deltas before any use. = 89.7/m Feb-26; normalise lengths before trending
Reece | Q-459014437 (NAS, current) | PE100 PN16 blue-stripe 125mm (6m) | len | 186.65 | Y | see note | N | Benchmark only - re-base + escalate | Benchmark only | COMPARABLE reference - record scope/date/location/spec/freight/qty deltas before any use. = 31.1/m; closest current PE benchmark for deriving O250 SDR11
Tradelink | 1057751 (CQU, EXPIRED) | CU tube Type-B 100mm (6m) | len | 735.21 | Y | see note | N | Benchmark only - re-base + escalate | Benchmark only | COMPARABLE reference - record scope/date/location/spec/freight/qty deltas before any use. Copper curve 15-100mm on file for rough-in benchmarking
Humes | Q21641195 (NAS, current) | 600x600x600 pit base | ea | 423.2 | Y | see note | N | Benchmark only - re-base + escalate | Benchmark only | COMPARABLE reference - record scope/date/location/spec/freight/qty deltas before any use. vs Tradelink 229.50 / Jaybro 205
Jaybro | 20043160 (NAS) | Hinged grate & frame 600x600 Cl D | ea | 583 | Y | see note | N | Benchmark only - re-base + escalate | Benchmark only | COMPARABLE reference - record scope/date/location/spec/freight/qty deltas before any use. Hinged vs drop-in price gap 583 vs 193
Jaybro | 20043160 (NAS) | Regional freight to Rockhampton | lot | 1250 | Y | see note | N | Benchmark only - re-base + escalate | Benchmark only | COMPARABLE reference - record scope/date/location/spec/freight/qty deltas before any use. Benchmark for adding freight to Jaybro email rates (P06)

## Gaps
# | Scope element | Status | Closest evidence on file | Recommended sourcing action
1 | Ocean Protect StormFilter: 22x Tall (690mm) PSorb cartridges + DN3300 manhole - THIS project | PARTIALLY COVERED - no direct Ocean Protect quote. Reece Q-459014431 carries a project-specific lump line '22-cartridge 690mm Psorb Stormfilter Manhole' @ 90,064.63 + 7,142.10 freight (SAP, no spec/drawing basis stated). | Reece P13 line; Anaconda OP 19901 (EXPIRED 04/26): 18-cart 70,060 / 13-cart 60,460 / freight 8,000; OP 20C-DN3300 standard drawing (closest published config) | RE-QUOTE direct with Ocean Protect for this site (they will want the MUSIC model). Cross-check: OP 19901 derivation for 22-cart = approx 35.5k base + 22 x 1.92k = approx 77.7k + freight, pre-escalation - the Reece lump at 90.1k is plausible but unverified; interrogate what the Reece line includes (cartridges? false floor? install?) before adoption.
2 | 316 stainless press-fit pipe >DN22 (through DN35+ / larger sizes) | OPEN - Tradelink refused a rate. Reece Q-459014431 gives rate-only lines at 22/28/35mm; nothing larger priced by anyone. | Reece 316 tube 22 @64.68, 28 @80.63, 35 @132.03 per 6m + fittings | RE-QUOTE larger sizes (Reece special order, Auspress, AllValve, Kembla KemPress 316). Interim: benchmark-derive >35mm from the Reece 22-35 curve (state basis + % uplift assumption in quals).
3 | Seismic bracing hardware (AS1170.4 restraint of services) | OPEN - no quote in any folder. | None | RFQ nVent CADDY / Unistrut / Hilti seismic channel & brace kits. Interim: benchmark-derive as % of rough-in material value with stated basis; carry as qualification.
4 | Articulation / expansion joints (Storm Plastics) | OPEN - no quote. | None (Reece DWV expansion couplings priced on NAS quote are not the spec item) | RFQ Storm Plastics direct (note lead time). Interim: allowance per joint from prior invoices, stated basis.
5 | HDPE PE100 SDR11 O250 potable main (copper-replacement alternative) | OPEN - only the DN200 copper basis is priced (Tradelink 6595064: 2,015/6m len). | NAS Reece Q-459014437 PE100 PN16 125 @186.65/6m (current) as nearest PE curve point | RFQ Acu-Tech / Vinidex / Atlan for PE100 SDR11 PN16 O250 pipe + EF couplers/stub flanges. Keep copper quote as conforming basis; price PE as alternative with derivation stated.
6 | Drinking fountains CF400 - chilled AND non-chilled | PARTIAL - chilled priced: 4x Urban CF400-PREMIUM wall-mount chiller DFCF400P @11,050 (Tradelink 1066143); NON-chilled CF400 variant not priced anywhere; signage explicitly extra. | Tradelink 1066143 | Confirm chilled/non-chilled split from fixture schedule; RE-QUOTE non-chilled CF400 (Civiq/Urban via Tradelink) + signage price if required.
7 | Trench drain GT6 - RECYFIX PRO100 Class D400 w/ heelguard G-TEC ductile grate (code 47245, 31.4m amenities) | VERIFY - Reece quote prices PRO200 G-tec (32m) and PRO100 B125 SS heelguard, but the schedule's 47245 PRO100 D400 G-tec line as such does not appear. | Reece Q-459014445 lines 21/23 | Confirm with Reece whether the 32m Pro200 G-tec line was their GT6 offer (or approved equivalent); otherwise re-quote 47245.
8 | Sewer pump station (EXCLUDED scope per Addendum 2) | COVERED AS INTERFACE/ADD-PRICE EVIDENCE ONLY - three competing references: APS 14065 as-spec S+I 468,000 (+option supply-only 85,950); Tradelink 1066334 pack approx 416,000 (incl 115,000 install); Reece Q-459014431 S+I 523,170.73. | P08 / P11 / P13 | Carry as excluded with a clear interface qualification (civils, conduits, power, cranage by others). If an add-price is requested, base it on APS 14065 as-specified and state validity risk.
9 | Ocean Protect OceanGuard / Stormsack pit inserts + WSUD certification for THIS project | PARTIAL - Atlan 26-87004 lump sum covers 38 Stormsacks + 10 FIL-3.0 + tank + commissioning BUT is a 'high level estimate only' pending MUSIC model, valid day-of-issue only. | Atlan P02; OP OceanGuard benchmark 500 ea (Anaconda) | RE-QUOTE Atlan once MUSIC model is released (they request it in the quote); obtain competing Ocean Protect offer for the same duty as a check.
10 | Quantity reconciliation - Humes vs Reece civil take-offs | DISCREPANCIES: RCP375 299 (Humes) vs 262 (Reece); LBC 1500x600 13 vs 8; BC600x300 15 vs 16; BC750x300 3 vs 2; freight 35 vs 25 loads. | P04 vs P07 | Reconcile both take-offs against the drainage schedule (04_Quantity_Reconciliation) before selecting supplier; both quotes are schedule-of-rates so quantity risk stays with us.
11 | Copper building rough-in <=DN100 (current pricing) | STALE - only CQU 1057751 copper schedule (Apr-26, EXPIRED) covers 15-100mm; project quotes only cover DN200. | C01 rate curve; NAS Reece Ardent Cu lines (current) | RE-QUOTE 15-100mm copper schedule from Tradelink/Reece for tender-stage pricing, or escalate C01 with stated % and date basis.