## TCS $ Sched
SUMMARY | [9 empty] | BIG TICKET ITEMS
JOB DESCRIPTION: | ROK Sports Precinct |  | DATE: | 26/07/2026 | [5 empty] | Club house (NBC )
SITE ADDRESS: | 554-700 Yaamba Rd, Norman Gardens QLD 4701 |  | TPS-TEN16699-V2
[7 empty] | Cost | (Cost + O/H) + Profit |  | 1500 Liters Git Viking Panel TIm in Ground ( grease trap ) |  |  | Hot Water Pump set to suit Rheem Hot Water Unit |  |  | Rheem HWU
|  |  | TOTALS | [6 empty] | Purchase Cost Total | 8523.28 |  | Purchase Cost Total | 6775.83 |  | Purchase Cost Total | 3438.29
[16 empty] | Safe Tray | 52.8
[10 empty] | TPS Markup | 1.15 |  | TPS Markup | 1.15 |  | TPS Markup | 1.15
[10 empty] | Qty | 1 |  | Qty | 1 |  | Qty | 2
| N16 rewired = S16+W17+Z17+AC17 - NBC Rheem HWU block was orphaned (never reached summary) | [8 empty] | Freight | 250 |  | Freight | 150 |  | Freight | 300
| CLUBHOUSE |  | 692573.5398 |  |  |  | 470848.0963 | 666250.0563 |  | Installation_MH | 0 | RULE 4: token $250 set to $0 26/07/26 - installation labour is priced in Phase 7 activity T1-08: NBC trade waste 110 HDPE + Geberit 50 + 1500L Viking GIT install (8 crew-days, Crew 1; rate basis explicitly includes 'GIT excavation/set'; plant 3-5T exc 4d + crane truck 1d). Commissioning in T5-02. Retaining the token would DOUBLE-COUNT. Supply, freight, safe tray and mounting are priced separately - see EQUIPMENT_TEST_TPS.md. | Installation_MH | 0 | RULE 4: token $200 set to $0 26/07/26 - installation labour is priced in Phase 7 activity T4-03: 2x Rheem 315L HWU + HW circulating pump + flow/return loop (3 crew-days, Crew 4). Commissioning in T5-06. Retaining the token would DOUBLE-COUNT. Supply, freight, safe tray and mounting are priced separately - see EQUIPMENT_TEST_TPS.md. | Installation_MH | 0 | RULE 4: token $600 set to $0 26/07/26 - installation labour is priced in Phase 7 activity T4-03: 2x Rheem 315L HWU + HW circulating pump + flow/return loop (3 crew-days, Crew 4; crane truck 0.5d for HWU delivery/set). Commissioning in T5-06 ('HWU'). Retaining the token would DOUBLE-COUNT. Supply, freight, safe tray and mounting are priced separately - see EQUIPMENT_TEST_TPS.md.
[10 empty] | TOTAL | 10051.772 |  | TOTAL | 7942.2045 |  | TOTAL | 8329.507
HWU qty 2 adopted (QUANTITY_RECONCILIATION TPS_NBC - take-off double-count removed; 2 drawn H-NBC-200/202)
Public Amenities Block
| PUBLIC AMENITIES |  | 157680.5643 |  |  |  | 109647.5988 | 155151.3523
[10 empty] | Rheem HWU |  | PAM HWU is Rheem 50L 613/050 (H-PAM-200) - rate corrected from $3,438.29 (315L model) to $2,016.08 (Reece Q-459014431)
[10 empty] | Purchase Cost Total | 2016.08
[10 empty] | Safe Tray | 52.8
[10 empty] | TPS Markup | 1.15
[10 empty] | Qty | 1
| SITEWORKS |  | 641445.3993 |  |  |  | 453318.3034 | 641445.3993 |  | Freight | 150
[10 empty] | Installation_MH | 0 | RULE 4: token $200 set to $0 26/07/26 - installation labour is priced in Phase 7 activity T4-06: PAM Rheem 50L HWU + TMV + O32 check-meter assembly (1 crew-day, Crew 4). Commissioning in T5-06. Retaining the token would DOUBLE-COUNT. Supply, freight, safe tray and mounting are priced separately - see EQUIPMENT_TEST_TPS.md.
[10 empty] | TOTAL | 2529.212
| ACCOMMODATION - FIFO Option A (apartments + LH nightly) |  | 124117.2457 |  |  |  | 87715.368 | 124117.2457 | Phase 7 Accommodation TPS: 14 apt-months x $4,606.06 (crew of 3/apt) + LH 225 nights x $103.2468 = $87,715 (Option A recommended). Option B all-individual = 1,275 nights x $103.2468 = $131,640 - premium $43,925 not taken. No sharing with TCS (SS5.2).
| FLIGHTS - FIFO roster (return every 2nd w/e) |  | 63505.2 |  |  |  | 44880 | 63505.2 | 51 person-months (Phase 7) x 2 returns/person-month x 2 legs x $220/leg = $44,880 - assumption stated (Misc Rates flight basis)
Sewer pump station EXCLUDED - installed by Council per Addendum 2 (10 Jul 2026); interfaces per interface ledger L6; add-price held in EBC register (APS 14065 basis) - see EBC_Alternates. Prior orphaned block W37 $468,000 -> W43 $545,700 removed (fed no roll-up; never in N64).
1166409.3665
[5 empty] | Prelim | 5.5% | 64152.5152 | of total cost
[5 empty] | O/H | 18% | 209953.686 | of total cost
[5 empty] | Sub Total |  | 1440515.5676 | total cost + Prelim + O/H
[5 empty] | Gross Profit | 18% | 209953.686 | of total cost (SS5.4 re-base 26/07/26; was =R45*Q47 -> effective 45.73%)
1650469.2536
[5 empty] | Total Markup | 41.5%
[5 empty] | Net Profit Incl Equip |  | 0
|  | TOTAL - TPS BASE SELL ex GST (excl PC Sums) | 1679321.9491
GST rows removed - ALL PRICING EX GST per SS5.4
[5 empty] | Prelim | 5.5%
[5 empty] | O/H | 18%
.
|  | PC SUMS - separate identified lines (ex GST) |  |  | Sub Total |  | Fixtures PC build (ex GST)
|  | PC-1A Fixtures supply - Tradelink 1066143 adjusted + 15% | 207268.8355 | Quote validity 13/08/26 vs 2027 start - escalation/validity qualification carried; Phase 4 line-by-line reconciliation mandatory |  |  | Tradelink 1066143 quote total | 252694.77
|  | PC-1A Drinking fountains - 2x CF400 chilled (NBC) + 15% | 25415 |  | Profit | 18% | less 4x CF400 chilled fountains (moved to DF PC lines) | -44200
|  | PC-1A Provisional connection fees - as directed, NO markup | 20000 | 1A 5.0 / 1B 4.6: $20,000 actual-cost reimbursement carried in BOTH stages exactly as directed (SS5.4) - no markup | Total Markup | 41.5% | less 5x Billi Quadra 4180 - SUPPLIED BY RCC per FF&E VOL25 (install labour retained in base) | -38261
|  | PC-1B Fixtures supply - PAM adopted-count extension + 15% | 17250 |  | Grand Total |  | plus NBC adopted-count extension allowance | 10000
|  | PC-1B Drinking fountains - 2x CF400 non-chilled (PAM, benchmark) + 15% | 16560 |  |  |  | plus PAM adopted-count extension allowance (PAM set never counted: 8 s/s WC + cisterns, trough, CSK, taps, 2 TR) | 15000
|  | PC-1B Water bubbler stations - 4x site DF (H003, benchmark) + 15% | 33120 |  |  |  | Adjusted PC base (1A+1B) | 195233.77
|  | PC-1B Provisional connection fees - as directed, NO markup | 20000 |  |  |  | Extension deltas are stated allowances: quote quantities unfinalised; only 25 of ~108 adopted fixtures were counted when quote was assembled (Fixtures sheet). Where adopted counts exceed known quote lines they extend at quote-rate family; delta = +$25,000 total. Phase 4 reconciliation governs before award.
|  | PC SUMS TOTAL ex GST | 339613.8355 |  |  |  | Non-chilled CF400 benchmark rate (chilled $11,050 less ~35% chiller premium; Gap #6 pending re-quote) | 7200
STAGE SPLIT (SCOPE_MATRIX: mains-through-1B in 1A; PAM/bubblers/1B connections in 1B)
|  | 1A base sell: NBC + Siteworks + accom/flights share (146/166 crew-days) | 1499036.2708
|  | 1A PC sums | 252683.8355
|  | STAGE 1A TOTAL ex GST | 1751720.1063
|  | 1B base sell: PAM sheet (incl 1B site branches T2-09) + accom/flights share (20/166) | 180285.6783
|  | 1B PC sums | 86930
|  | STAGE 1B TOTAL ex GST | 267215.6783
|  | GRAND TOTAL ex GST (1A + 1B incl PC sums) | 2018935.7846
|  | Tie check (N64 + N78 - N87) = 0 | 0

## 00_ TCS Prelim & OH
Project:
Tricore -
Stage 1 Version 1
Item | [8 empty] | Source
A | PRELIMINARIES
SUMMARY (Not added in prelim$)
|  | TOTAL Days Mobilized On Site | 285 |  |  | Re-based from Phase 7 TPS_Programme (link [1] severed): 197 work days across 3 discrete site windows; 10 months elapsed less inter-window demob = 285 calendar days on site |  |  | frozen from [1] CQU ROK_PROGRAM - MASTER.V1 (SharePoint) - link severed 26/07/26; re-based from Phase 7 TPS_Programme
|  | Months Mobilized | 9.4 | [5 empty] | frozen from [1] CQU ROK_PROGRAM - MASTER.V1 (SharePoint) - link severed 26/07/26; re-based from Phase 7 TPS_Programme
|  | Work Weeks' Mobilized On Site | 40 | [5 empty] | frozen from [1] CQU ROK_PROGRAM - MASTER.V1 (SharePoint) - link severed 26/07/26; re-based from Phase 7 TPS_Programme
|  | Work Days | 197 |  |  | 197 work days = Phase 7 programme finish (T5-07 as-cons) |  |  | frozen from [1] CQU ROK_PROGRAM - MASTER.V1 (SharePoint) - link severed 26/07/26; re-based from Phase 7 TPS_Programme
Breakdown as per program
| TRADESMAN_LEADING HAND | Day |  | 1329.6343 | 0
| TRADESMAN_PLUMBER_OPERATOR | Day |  | 1016.4579 | 0
| T/A & Apprentice | Day |  | 829.5103 | 0
| Crew #1 - InGround Drainage | Day |  | 2862.4261 | 0
| Crew #2 - InGround Water/Fire | Day |  | 2862.4261 | 0
|  |  |  | Total Labour | 0
Total as per stage boq
|  |  |  | Total Part A Labour | 0
|  |  |  | Total Stage 1 Labour | 0
|  |  |  | Total Stage 2 Labour | 0
|  |  |  | Total Stage 3 Labour | 0
|  |  |  | Total Stage 4 Labour | 0
0
|  |  |  | Difference | 0
|  | Unit | REQ | Cost ex GST | Total ex GST
Labour
Contingencies; Wet Weather ?
| Superviser; Return Trip, 2 day stay - Inclusive | item |  | 2423.831 | 0
| TRADESMAN_LEADING HAND | Day | 0 | 1329.6343 | 0 | MEMO ONLY - 140 LH supervision days (1,400 hr) are priced IN the three work-area labour blocks per Phase 7 (Siteworks 489.2 + NBC 742.1 + PAM 168.5 = 1,399.8 hr). Not repeated here - double-count control.
| TRADESMAN_PLUMBER_OPERATOR | Day |  | 1016.4579 | 0
| T/A & Apprentice | Day |  | 829.5103 | 0
| Crew #1 - InGround Drainage | Day |  | 2862.4261 | 0
| Crew #2 - InGround Water/Fire | Day |  | 2862.4261 | 0
Management Labour
| TRADESMAN_LEADING HAND | Day |  | 1329.6343 | 0 | Included within stages?
| MH / DQ | Day |  | 120 | 0 | Refer Program for approx attendance on site. Technically covered in overheads. E/O for meals etc?
| MH / DQ - FLIGHTS | ea |  | 200 | 0
ACCOMODATION (Refer Program)
Per Month - Full Project (6 Persons)
| Full Apartment / TownHouse / Unit - VIA AGENT | Month | 0 | 4606.0606 | 0 | ** 1 x 4Bed House (@650/Wk) fully kitted, +Consumable, +Cleaner etc | MEMO - accommodation Option A (14 apt-months + LH 225 nights = $87,715) carried as a cost row on 'TCS $ Sched' R32; not repeated here
| Full Apartment / TownHouse / Unit - VIA AGENT | Month | 0 | 4606.0606 | 0 | ** 1 x 4Bed House (@650/Wk) fully kitted, +Consumable, +Cleaner etc
| Individual Night Stay - Private Room/Suite | [5 empty] | Avrg Nightly Book (LONG STAY)
| TRADESMAN_LEADING HAND |  |  |  |  | 0 | 103.2468 | 0
| TRADESMAN_PLUMBER_OPERATOR |  |  |  |  | 0 | 103.2468 | 0
| T/A & Apprentice |  |  |  |  | 0 | 103.2468 | 0
| Crew #1 - InGround Drainage |  |  |  |  | 0 | 103.2468 | 0
Per Night - Extra-Over, Per Person.
| TCS Cost Per Person - Private Unit - NO SHARE - Nightly Booking (average allowance) | item |  | 112.8571 | 0
| MH / DQ | item |  | 140 | 0 | TOTAL ACCOM ALLOWANCE
[6 empty] | 0 |  | 0
Equipment, Hire, Subbies
| Vehicle - UTE - SUPERVISER | Day | 140 | 90 | 12600 | Supervisor ute - 140 LH days on site @ $90/d
| Vehicle - UTE - TRADESMAN | Day | 166 | 60 | 9960 | One crew ute per crew-day - 166 base crew-days @ $60/d (Phase 7 roll-up)
| Vehicle - UTE - TRADESMAN / TA | Day | 0 | 40 | 0 | nil - second crew ute is inside the $60/d crew allowance above
| Site Vehicle - Ute/Buggy | Day |  | 90 | 0
| Genset hire + fuel - TPS compound (no site power, ITT S17.3) | Day | 285 | 45 | 12825 | Allowance $45/d single-phase genset + fuel, full 285-day site duration
| Temporary potable water storage pods + site distribution (no site water, ITT S17.3) | item | 1 | 5000 | 5000 | 2 pods over ~10 months + fittings/stands. Test/flush water PURCHASE is priced separately on Siteworks r148 - no overlap
| Porta Loo_No Tank | Day | 285 | 5.46 | 1556.1 | Portable toilet - full site duration (TPS own; no shared compound - interface L5)
| 6*3m Demantable Lunchroom - COMPLETE | Day | 285 | 23 | 6555
| 6*3m Demantable Office - COMPLETE | Day | 285 | 23 | 6555
| 20Ft Shipping Container | BUY | 1 | 1800 | 1800 | 20 ft container - purchase, TPS site store
| Skip Bin | Changeover | 9.4 | 239.8 | 2254.12 | Skip changeovers = months mobilised
| Three-mobilisation allowance - plant float (3 discrete site windows per Phase 7 programme) | mob | 3 | 1440 | 4320 | 3 mob x 2 loads x 4 hr x $180/hr ex-ROK transport (Equip&HIRE D66). Crew remobilisation LABOUR is Phase 7 T1-12, priced in Siteworks - no overlap
Misc.
| INSURANCE | item | 1 | 20000 | 20000 | Project-specific insurances (contract works + project PL/PI excess) - allowance; review against corporate cover before close
|  |  |  | Total TCS Prelims | 83425.22 | CROSS-CHECK: 5.5% prelims markup allowance ('TCS $ Sched' R42) | 64152.5152
[6 empty] | Variance $ (bottom-up F89 less 5.5% allowance) | 19272.7048
[6 empty] | Variance % of the 5.5% allowance | 30.04%
A | OverHeads |  |  |  |  | Bottom-up prelims are the DIRECT establishment / temp-services / vehicle / mobilisation costs TPS must carry standalone (SS5.2 - no shared compound). Where bottom-up exceeds the 5.5% margin allowance the difference is a real exposure: lift the prelims % or carry the delta as a priced line before close.
|  | Unit | REQ | Cost ex GST | Total ex GST | Percentage across Project COST
| TriCore Overheads - COMPLETE…PER MONTH | item | 9.4 | 40000 | 376000 | 18% | 9.4 months mobilised x $40,000/month TriCore corporate overhead (full corporate rate)
| less share attributable to concurrent TriCore projects (TPS carries 45% of corporate O/H over this window) | item | 1 | -206800 | -206800 |  | STATED ASSUMPTION: charging 100% of corporate overhead to one project would over-recover. A 45% allocation is adopted for a project of this duration and value against expected concurrent workload - Director to confirm before close.
|  |  |  | Total TCS O/H | 169200 | CROSS-CHECK: 18% O/H markup allowance ('TCS $ Sched' R43) | 209953.686
[6 empty] | Variance $ (bottom-up F96 less 18% allowance) | -40753.686
[6 empty] | Variance % of the 18% allowance | -19.41%
[6 empty] | COMBINED bottom-up prelims + O/H | 252625.22
[6 empty] | COMBINED 5.5% + 18% margin allowance | 274106.2011
[6 empty] | Combined variance $ / % | -21480.9811 | -7.837%

## ClubHouse (NBC )
Project:
Tricore -
Stage 1 Version 1
Item
1 | Complete -
Labour
[6 empty] | Denis qty | Qty / rate source note
| DAY | [7 empty] | april 2026 direct impact Increase % (not contigency)
| TRADESMAN_LEADING HAND | Day |  | 1329.6343 | 0
| TRADESMAN_PLUMBER_OPERATOR | Day |  | 1016.4579 | 0 |  |  |  |  | PE Pipe & Fitting | 38% | 1.38
| T/A & Apprentice | Day |  | 829.5103 | 0 |  |  |  |  | PVC Pipe & Fittings | 38% | 1.38
| Crew #1 - InGround Drainage | Day | 26 | 2862.4261 | 74423.0786 |  | Phase 7 crew-days: T1-07 14 + T1-08 8 + T1-10 4 (DP stubs NBC+PAM) |  |  | Subby Rates | 15% | 1.15
| Crew #2 - InGround Water/Fire | Day |  | 2862.4261 | 0 |  |  |  |  | Delivey Rate | 20% | 1.2
| Crew #3 - Above Ground Drainage | Day | 14 | 2862.4261 | 40073.9654 |  | Phase 7 crew-days: T3-01 6 + T3-02 5 + T3-04 3
| Crew #4 - Above Ground WATER/FIRE | Day | 21 | 2862.4261 | 60110.9481 |  | Phase 7 crew-days: T4-01 12 + T4-02 3 + T4-03 3 + T4-04 1 + T4-07 2
| Crew #5 - Above Ground FitOff / Misc | Day | 27 | 2862.4261 | 77285.5047 |  | Phase 7 crew-days: T5-01 13 + T5-02 3 + T5-04a 1 + T5-05 3 + T5-06 4 + T5-07 3
| Crew #6 - DEMO | Day |  | 1845.9682 | 0
HOUR
| TRADESMAN_LEADING HAND | HR | 742.1 | 132.9634 | 98672.1603 |  | Phase 7 LH supervision - NBC activities 742.1 hr
| TRADESMAN_PLUMBER_OPERATOR | HR | 0 | 101.6458 | 0
| T/A & Apprentice | HR | 0 | 82.951 | 0
| Crew #1 - InGround Drainage | HR | 0 | 286.2426 | 0
| Crew #2 - InGround Water/Fire | HR | 0 | 286.2426 | 0
Demolition & Reinstatement
DEMO
| Asphalt Cutting | m |  | 15.525 | 0
| Concrete Cutting | m |  | 18.4 | 0
| Con Cut Establishemnt Fee | ea |  | 92 | 0
REINSTATE - CONCRETE
| Road/Drveway Reinstate; 1mW x 150 Thck, N25/20/80, Incl Reinforcement | m |  | 145 | 0
| Kerb & Channel - 1m Wide | ea |  | 155 | 0
| Footpath - 1.5mW, N25/20/80, Incl Reinforcement | lm |  | 180 | 0
| Footpath - 1.5mW, EXPOSED AGG, N25/20/80, Incl Reinforcement | lm |  | 185 | 0
REINSTATE - ASPHALT
| 50mm Thck - Trench Reinstatement Through Road/Driveway | m2 |  | 97 | 0
| 50mm Thck - 1.5-2m Wide Footpath reinstatements | m2 |  | 97 | 0
| Establishment Fee (1 per stage) | Ea |  | 5500 | 0
Equipment & Hire - INCL WET PLANT HIRE
HIDDEN | PLANT HIRE - WET
| 1.8T Excavator | Hr |  | 100 | 0
| 3-5 ton Excavator | Hr |  | 115 | 0
| 3-5T Combo | Hr |  | 154 | 0
| Hammer attachment 3.5-4T | Hr |  | 21 | 0
| Ripper 3.5-4T | Hr |  | 10 | 0
| 5t Excavator | Hr |  | 150 | 0
| Hammer attachment 5T | Hr |  | 50 | 0
| Skid steer | Hr |  | 140 | 0
| 8T Excavator | Hr |  | 128 | 0
| Hammer attachment 8T | Hr |  | 26 | 0
| Ripper 8T | Hr |  | 10 | 0
| 13-15T Excavator | Hr |  | 153 | 0
| Hammer attachment 14T | Hr |  | 36 | 0
| Ripper 14T | Hr |  | 10 | 0
| 3000L Hydro Excavation Truck | Hr |  | 190 | 0
| 4500L Hydro Excavation Truck | Hr |  | 220 | 0
| 6300L Hydro Excavation Truck | Hr |  | 250 | 0
| Water Truck allow for water at cost | Hr |  | 110 | 0
| 12t Body Truck Tipper | Hr |  | 110 | 0
HIRE - DRY
| Skid Steer Loader_Tracked (CAT249+) | Day |  | 225.4333 | 0
| Skid Steer Loader_Wheeled (CAT226+) | Day |  | 163.9667 | 0
| Mini Loader, Stand-on Type | Day |  | 180 | 0
|  |  |  | 0 | 0
| 1.5-1.8 Ton_Excavator | Day | 14 | 137.1429 | 1920 |  | Phase 7 plant: T1-07 10 + T1-10 4
| 1.7-2Ton_Excavator | Day |  | 0 | 0
| 3-5Ton_Excavator | Day | 8 | 238.6667 | 1909.3333 |  | Phase 7 plant: T1-08 4 + T1-07 combo 4 (combo classed as 3-5T)
| 8Ton_Excavator | Day |  | 261.1667 | 0
| 10-12Ton_Excavator | Day |  | 0 | 0
| 13-16Ton_Excavator | Day |  | 317.2 | 0
| 20-24Ton_Excavator | Day |  | 314.2857 | 0
|  |  |  | 0 | 0
| Ripper_1.7-2T | Day |  | 0 | 0
| Ripper_1.5-4T | Day |  | 32.74 | 0
| Ripper_3-5T | Day |  | 0 | 0
| Ripper_8T | Day |  | 40.38 | 0
| Breaker_1.7-2T | Day |  | 123.33 | 0
| Breaker_3-5T | Day |  | 165.89 | 0
| Breaker_8T | Day |  | 165.89 | 0
| Breaker_10-12T | Day |  | 0 | 0
| Breaker_13-15T | Day |  | 203 | 0
| Auger Drive_10-12T |  |  | 0 | 0
| 300Dia Auger Drill |  |  | 0 | 0
|  |  |  | 0 | 0
| 1.25T_Tipper Truck | Day |  | 205 | 0
| 2-4T_Tipper Truck | Day |  | 166.98 | 0
| <6T_Tipper Truck | Day |  | 171.4286 | 0
|  |  |  | 0 | 0
| <10T_Articulated Site Tipper | Day |  | 0 | 0
| Upright Rammer_Wacker | Day | 10 | 34.2857 | 342.8571 |  | Phase 7 plant: T1-07 10
| Trench Roller_Dbl Drum_Remote | Day |  | 165 | 0
| <26Ft_Scissor Lift - Diesel | Day |  | 300 | 0
| <26Ft_Scissor Lift - Elec | Day | 13 | 30 | 390 |  | Phase 7: 13 d (T3-01 4 + T3-04 3 + T4-01 4 + T4-07 2); rate $150/wk (Civ Equip_HIRE weekly)/5 = $30/d - confirm Phase 6
| <34Ft_Boom Lift - Diesel | Day |  | 0 | 0
| <34Ft_Boom Lift - Elec | Day |  | 0 | 0
|  |  |  | 0 | 0
| Porta Loo_No Tank | Day |  | 5.46 | 0
| 6*3m Demantable Lunchroom - COMPLETE | Day |  | 23 | 0
| 6*3m Demantable Office - COMPLETE | Day |  | 23 | 0
| 20Ft Shipping Container | Day |  | 0 | 0
| Quick Cut Demo Saw | Day |  | 0 | 0
| Sngl Ph_6KVA Genset | Day |  | 0 | 0
| Diesel Air Compressor_Trailer | Day |  | 0 | 0
| Air Breaker - Heavy | Day |  | 0 | 0
| Air Hose <10m | Day |  | 0 | 0
| Elec Breaker/Jachammer | Day |  | 0 | 0
| Flexdrive Motor Unit | Day |  | 0 | 0
| Flexdrive_Pump Shaft | Day |  | 0 | 0
| Temporary Power Board | Day |  | 0 | 0
|  |  |  | 0 | 0
| Dual CabUte | Day |  | 0 | 0
| 3m3 Skip Bbin | per serive |  | 230 | 0
| plus disposal | Tonne |  | 309 | 0
| site fee | Week |  | 35 | 0
| ~4m3_Skip Bin | per change over |  | 229.9 | 0
| ~6m3_Skip Bin | per change over |  | 239.8 | 0
| Plus disposal | Tonne |  | 309 | 0
| Site fee | Week |  | 35 | 0
| Vacuum Excavator - Vermeer VT250D | Day |  | 295.77 | 0
| Vac Trailer – Dry Hire | Day |  | 355 | 0
|  |  |  | 0 | 0
| TRANSPORT_Ex BRIS - Return | Day |  | 0 | 0
| TRANSPORT_Ex ROK - Return | Hour |  | 180 | 0
| 0-4T Per Hour Delivery Rate | Hour |  | 125 | 0
| 5 - 9t Transport Hourly Rate | Hour |  | 160 | 0
| 10 - 19t Low Loader Hourly rate - Minimum 2 Hour Charge | Hour |  | 200 | 0
| PE butt welder + EF processor - ALLOWANCE (not in hire registers) | Day | 6 | 350 | 2100 |  | Phase 7: T1-08 trade waste 6 d
| FUEL - Average_Candle | Week |  | 1850 | 0
Subbies & Misc
| Surveyor | ea |  | 180 | 0
| Services Locator | ea |  | 130 | 0
| Compaction Testing - TEST | ea | 15 | 115 | 1725
| Compaction Testing - Site Establishment | ea | 4 | 90 | 360
| Crane truck / HIAB - GIT set + HWU delivery (allowance) | Hr | 15 | 180 | 2700 |  | Phase 7: T1-08 1 d + T4-03 0.5 d @ ~$180/hr
| Hydro/commissioning test gear (subbie rate $450/d) | Day | 2 | 450 | 900 |  | T5-06 commissioning
| FIRE TESTING / CERT | ea |  |  | 0
| FULL Hydro Test - Per Test (6.5Hr 1 x fitter, 1 x apprentice, 1 day Test gear) | ea |  | 1945 | 0
| Provision of Form 72 | ea |  | 350 | 0
| Provision of Form 72 - buildings | ea | 1 | 350 | 350 |  | T5-06
| Consumables & small tools - NBC crews (allowance) | item | 1 | 3500 | 3500 |  | Phase 7 consumables flag
Material - Quarry, Misc
*HIDDEN - Calc in below
| Bedding / Fill Sand | m3 | 73.2715 | 39.75 | 2912.5429 |  | Bedding import = helper I971 (auto from adopted pipe lengths)
| CBR 45/2.5 Roadbase | m3 |  | 41.9 | 0
| Turf Underlay/Topsoil | m3 |  | 45.25 | 0
| Standard Garden Woodchip | m3 |  | 87 | 0
| Turf - Standard Couch or Similar | Slab (.5m2) |  | 6.48 | 0
| Spoil haulage & dump (take-off helper M971 @ $15/m3) | item | 1 | 1099.0728 | 1099.0728 |  | Auto from helper
| Cement Stabalized Sand (3-5%) | m3 |  | 169 | 0
| Exposed Agg Concrete - Standard/Cheapest Exposed Agg Stone | m3 |  | 252 | 0
| N25 20mm 80 Slump Concrete | m3 |  | 263 | 0
| Valve Margin strips; Concrete slab, 1 directions sign, 3 x valve No sign. | ea |  | 380 | 0
FIRE SERVICES - INGROUND
| 200 HDPE PN16 SDR11 - REDLINE | m |  | 46.8107 | 0
| 180 HDPE PN16 SDR11 - REDLINE | m |  | 35.144 | 0
| 125 HDPE PN16 SDR11 - REDLINE | m |  | 16.9936 | 0
| 75 HDPE PN16 SDR11 - REDLINE | m |  | 12.31 | 0
| 32 HDPE PN16 SDR11 - BLUELINE | m |  | 1.6779 | 0
0
| 200 EF Coupler | ea |  | 60.8028 | 0
| 180 EF Coupler | ea |  | 35.4936 | 0
| 125 EF Coupler | ea |  | 19.4718 | 0
| 200 EF 45DFeg Bend | ea |  | 150.6408 | 0
| 180 EF 45DFeg Bend | ea |  | 135.1986 | 0
| 125 EF 45DFeg Bend | ea |  | 61.6722 | 0
| 200 EF 90DFeg Bend | ea |  | 150.6408 | 0
| 180 EF 90DFeg Bend | ea |  | 134.9778 | 0
| 125 EF 90DFeg Bend | ea |  | 61.617 | 0
| 200 EF TEE | ea |  | 151.455 | 0
| 180 EF TEE | ea |  | 157.7064 | 0
| 125 EF TEE | ea |  | 67.965 | 0
| 200*180 EF TEE | ea |  | 289.0686 | 0
| 200*125 EF TEE | ea |  | 301.4196 | 0
| 180*125 EF TEE | ea |  | 168.5394 | 0
| 200*180 EF Reducer | ea |  | 173.3556 | 0
| 180*125 EF Reducer | ea |  | 82.938 | 0
| 180*32 EF Reducer | ea |  | 65 | 0
| 200PE*8"(200m) - MaxiStub W/Backing Ring | ea |  | 472.443 | 0
| 180PE*6"(150mm) - MaxiStub W/Backing Ring | ea |  | 179.0826 | 0
| 125PE*4" (100mm) - MaxiStub W/Backing Ring | ea |  | 127.8846 | 0
| 180mm PE x 150mm GALV ADAPTER - PLASSON Brand | ea |  | 432.2022 | 0
| 125mm PE x 100mm GALV ADAPTER - PLASSON Brand | ea |  | 281.6718 | 0
|  | 0 |  | 0 | 0
| 180mm PE x 150mm GALV ADAPTER | ea |  | 435.6798 | 0
| 125mm PE x 100mm GALV ADAPTER | ea |  | 277.9734 | 0
| 200 Long SPIG 45DFeg Bend | ea |  | 94.5852 | 0
| 180 Long SPIG 45DFeg Bend | ea |  | 88.9548 | 0
| 125 Long SPIG 45DFeg Bend | ea |  | 53.4888 | 0
| 200 Long SPIG 90DFeg Bend | ea |  | 118.9146 | 0
| 180 Long SPIG 90DFeg Bend | ea |  | 93.9918 | 0
| 125 Long SPIG 90DFeg Bend | ea |  | 43.677 | 0
| 200 Long SPIG TEE | ea |  | 176.1432 | 0
| 180 Long SPIG TEE | ea |  | 157.6236 | 0
| 125 Long SPIG TEE | ea |  | 52.7988 | 0
| 200*180 Long SPIG TEE | ea |  | 253.2024 | 0
| 200*125 Long SPIG TEE | ea |  | 265.5534 | 0
| 180*125 Long SPIG TEE | ea |  | 256.2798 | 0
| 200*180 Long SPIG Reducer | ea |  | 77.0592 | 0
| 180*125 Long SPIG Reducer | ea |  | 54.9654 | 0
| 75PE 50 CU TRANSITION | ea |  | 45 | 0
| 32 PE 25 CU TRANSITION | ea |  | 35 | 0
|  | 0 |  | 0 | 0
| 200 FL DICL Sluice Valve | ea |  | 679.41 | 0
| 150 FL DICL Sluice Valve | ea |  | 323.53 | 0
| 100 FL DICL Sluice Valve | ea |  | 202.94 | 0
| Valve Spindle Riser - 600Long | ea |  | 136.94 | 0
| Valve Box - Cast Iron Trafficable - Rectangle Type "V" | ea |  | 123.53 | 0
| Valve Box - Non-Trafficable - Plastic Surround with CI Drop In "V" | ea |  | 98.82 | 0
|  | 0 |  | 0 | 0
| 200*150mm DICL FL Reducer | ea |  | 291.18 | 0
| 200*100mm DICL FL Reducer | ea |  | 330 | 0
| 150*100mm DICL FL Reducer | ea |  | 156 | 0
| 150mm DICL FL * SP Adapter | ea |  | 106.24 | 0
| 100mm DICL FL * SP Adapter | ea |  | 70.59 | 0
| 200mm DICL FL 90Deg Bend | ea |  | 516.35 | 0
| 150mm DICL FL 90Deg Bend | ea |  | 198.88 | 0
| 100mm DICL FL 90Deg Bend | ea |  | 108.71 | 0
| 200mm DICL FL TEE | ea |  | 672.65 | 0
| 150mm DICL FL TEE | ea |  | 228.24 | 0
| 100mm DICL FL TEE | ea |  | 128.24 | 0
| 200*150*200 DICL FL TEE | ea |  | 536.76 | 0
| 200*100*200 DICL FL TEE | ea |  | 576.47 | 0
| 150-100-150 DICL FL TEE | ea |  | 198.82 | 0
| 200mm DICL FL Pipe @ 1000 | ea |  | 898.82 | 0
| 200mm DICL FL Pipe @ 600 | ea |  | 640 | 0
| 200mm DICL FL Pipe @ 300 | ea |  | 355.29 | 0
| 150mm DICL FL Pipe @ 1000 | ea |  | 534.41 | 0
| 150mm DICL FL Pipe @ 600 | ea |  | 280 | 0
| 150mm DICL FL Pipe @ 450 | ea |  | 236.47 | 0
| 150mm DICL FL Pipe @ 300 | ea |  | 178.8 | 0
| 100mm DICL FL Pipe @ 1000 | ea |  | 362.35 | 0
| 100mm DICL FL Pipe @ 600 | ea |  | 144.71 | 0
| 100mm DICL FL Pipe @ 450 | ea |  | 135.88 | 0
| 100mm DICL FL Pipe @ 300 | ea |  | 76.47 | 0
| 150mm DICL FL Deadplate | ea |  | 67.65 | 0
| 100mm DICL FL Deadplate | ea |  | 43.53 | 0
|  | 0 |  | 0 | 0
| 200mm PE*DI Gasket Kit Complete | ea |  | 67.06 | 0
| 200mm DI*DI Gasket Kit Complete | ea |  | 46.71 | 0
| 150mm PE*DI Gasket Kit Complete | ea |  | 60 | 0
| 150mm DI*DI Gasket Kit Complete | ea |  | 42.35 | 0
| 100mm PE*DI Gasket Kit Complete | ea |  | 24.71 | 0
| 100mm DI*DI Gasket Kit Complete | ea |  | 20 | 0
|  | 0 |  | 0 | 0
| 150mm SS Gibault Adapter Coupling | ea |  | 108.71 | 0
| 100mm SS Gibault Adapter Coupling | ea |  | 87.06 | 0
| 180mm PE GRIPPER Adapter Coupling | ea |  | 305.88 | 0
| 125mm PE GRIPPER Adapter Coupling | ea |  | 182.35 | 0
| 180mm PE GRIPPER * 150FL Adapter Coupling | ea |  | 229.41 | 0
| 125mm PE GRIPPER * 100FL Adapter Coupling | ea |  | 152.94 | 0
| 180mm PE GRIPPER Sluice Valve | ea |  | 690 | 0
| 125mm PE GRIPPER Sluice Valve | ea |  | 408.47 | 0
|  | 0 |  | 0 | 0
| Detectable Tape - Fire x 250m | ea |  | 90 | 0
| Alcohol Weld Wipes | ea |  | 13.5 | 0
| Denzo Tape 100mm roll | ea |  | 27.14 | 0
| Black over-wrap tape - roll | ea |  | 27.14 | 0
0
| FIRE SERVICES - ABOVE GROUND |  |  |  | 0
| Description | Unit
| 150mm MED DUTY Galv Pipe | m |  | 43.8462 | 0
| 100mm MED DUTY Galv Pipe w/RG Ends | m |  | 28.4615 | 0
| 100mm Class B Copper Pipe | m |  | 106.2417 | 0
| 25mm Class B Copper Pipe | m |  | 59.82 | 0
|  | 0 |  | 0 | 0
| 150mm Galv RG Coupling | ea |  | 12.83 | 0
| 100mm Galv RG Coupling | ea |  | 7.55 | 0
| 150mm Galv RG TEE | ea |  | 35.5 | 0
| 100mm Galv RG TEE | ea |  | 16.93 | 0
| 150mm Galv RG BEND 90Deg | ea |  | 22.85 | 0
| 100mm Galv RG BEND 90Deg | ea |  | 10.62 | 0
| 150mm Galv RG BEND 45Deg | ea |  | 23.5 | 0
| 100mm Galv RG BEND 45Deg | ea |  | 11.4 | 0
| 150mm Galv RG x 100mm FLANGE Adapt | ea |  | 30.75 | 0
| 100mm Galv RG x 100mm FLANGE Adapt | ea |  | 23.21 | 0
| 150mm RG Butterfly Valve Geared Wheel | ea |  | 217.8 | 0
| 100mm RG Butterfly Valve Geared Wheel | ea |  | 169.4 | 0
|  | 0 |  | 0 | 0
| 150mm H-Pattern Booster Assembly Complete | ea |  | 2350 | 0
| Booster Cabinet - Compl with doors and stickers | ea |  | 1155 | 0
|  | 0 |  | 0 | 0
| 100mm Dual Pillar Hydrant Complete_ Flanged Base 1500 High w/landing Valves | ea |  | 365 | 0
| 100mm Dual Pillar Hydrant Complete_ RG Base 1500 High w/landing Valves_OPTION | ea |  | 365 | 0
| 65mm RG Landing Valve | ea |  | 90 | 0
| Red caps and chain - suit 65mm QLD Landing valve | ea |  | 5 | 0
| 36m Fire Hose Reel w/25mm isolation valve | ea | 1 | 125 | 125
| FB fire blanket 1.2x1.8 (kitchen) | ea | 1 | 60 | 60 |  | Matrix 4.11-d: FHR x1 + FB x1 priced; FE x8 = EBC (CL B8)
| AS1851 12-month fire services maintenance & tagging (FHR/FB/booster/hydrant) incl FIFO attendance share | item | 1 | 2500 | 2500 |  | VOL38 12-month maintenance obligation - allowance incl 6-monthly service visits piggybacked on attendance
| 150mm FL Testable Double Check Valve - Compl. w/Valves | ea |  | 3100.7 | 0
| 150mm FL RPZD Valve - Compl. w/Valves | ea |  | 4237.09 | 0
|  | 0 |  | 0 | 0
| 100mm FL Levered Butterfly Vlave | ea |  | 114.44 | 0
| 100mm Copper Crimp - TEE | ea |  | 219.36 | 0
| 100mm Copper Crimp - 90Deg Bend | ea |  | 135.09 | 0
| 100mm Copper Crimp - 45Deg Bend | ea |  | 125.77 | 0
| 100mm Copper Crimp - Straight Socket | ea |  | 83.25 | 0
| 100mm Copper Crimp - 100mm FL Adapter | ea |  | 52.25 | 0
| 80mm Copper Crimp - TEE | ea |  | 175.66 | 0
| 100mm*80mm Copper Crimp - REDUCER | ea |  | 164.08 | 0
|  | 0 |  | 0 | 0
| 50mm Cu Tube Type B | m |  | 46.4167 | 0
| Elbow 90 Deg 50mm Water Kembla Kempress | ea |  | 45.02 | 0
| Equal Tee 50mm Water Kembla Kempress | ea |  | 56.35 | 0
| Reducer 50mm 25mm Water CU | ea |  | 34.92 | 0
| 32mm Fi Lockable Ball Valve | ea |  | 77.95 | 0
| 32mm Cu Crimp * 32mi Adapt | ea |  | 17.16 | 0
| 32mm Cu Crimp Coupling Straight | ea |  | 7.23 | 0
| 32mm Cu Crimp 90Deg Bend | ea |  | 14.31 | 0
| 32mm Cu Crimp 45Deg Bend | ea |  | 16.24 | 0
| 25mm Cu Tube Type B | ea |  | 21.4167 | 0
| 32mm*25mm Cu Crimp Reducer | ea |  | 14.36 | 0
| 25mm Fi Lockable Ball Valve | ea |  | 46.94 | 0
| 25mm Cu Crimp * 25mi Adapt | ea |  | 8.46 | 0
| 25mm Cu Crimp Coupling Straight | ea |  | 5.74 | 0
| 25mm Cu Crimp 90Deg Bend | ea |  | 7.7 | 0
| 25mm Cu Crimp 45Deg Bend | ea |  | 10.19 | 0
|  | 0 |  | 0 | 0
| 150mm Galv 2 Piece Weld-nut Bracket M12 | ea |  | 5.86 | 0
| 100mm Galv 2 Piece Weld-nut Bracket M12 | ea |  | 4.41 | 0
| 150 Galv 2 Piece Channel Clip | ea |  | 5.36 | 0
| 100 Galv 2 Piece Channel Clip | ea |  | 4.4 | 0
| 12mm Galv Threaded Rod | ea |  | 10.64 | 0
| Galv Braced Counter Lever Bracket - 450Long | ea |  | 20 | 0
| 003 Padlock | ea |  | 19.5 | 0
| 100mm DI*DI Gasket Kit Complete | ea |  | 20 | 0
FIRE SERVICES - Misc.
Description
| Decommisioning Material | ea |  | 1388 | 0
| Electrofusion PE Welder 25-250mmPE. Please detail Spec | ea |  | 0 | 0
| PE Butt Welder. Automatic. 125-250mmPE. Please detail Spec - HIRE | WEEK |  | 450 | 0
| Hand Roll Groover. 65-150mm. | ea |  | 0 | 0
| Delivery - To Rockhampton PIPE LENGTHS as quoted | ea |  | 2178.48 | 0
| Delivery - To Rockhampton Standard/Palletised items | ea |  | 2178.48 | 0
POTABLE WATER_MAINS & R'Ins
Description
| 125 HDPE PN16 SDR11 - BLUELINE | m |  | 34.5 | 0
| 90 HDPE PN16 SDR11 - BLUELINE | m |  | 20 | 0
| 75 HDPE PE100 PN 16 -Blueline | m |  | 12.31 | 0
| 63 HDPE PE100 PN 16 -Blueline | m |  | 9.66 | 0
| 63 HDPE PN12.5 SDR11 - BLUELINE | m |  | 4.63 | 0
| 50 HDPE PE100 PN 16 - BLUELINE | m |  | 5.4 | 0
| 40 HDPE PE100 PN16 Blue Line | m | 27.78 | 4.4 | 122.232 | 28 | ADOPTED qty per QUANTITY_RECONCILIATION TPS_NBC
| 40 HDPE PN12.5 SDR11 - BLUELINE | m |  | 2.3621 | 0
| 32 HDPE PE100 PN 16 -Blueline | m | 21.31 | 2.1 | 44.751 | 22 | ADOPTED qty per QUANTITY_RECONCILIATION TPS_NBC
| 25 HDPE PE100 PN16 - BLUELINE | m | 15.45 | 1.22 | 18.849 | 16 | ADOPTED qty per QUANTITY_RECONCILIATION TPS_NBC
| 25 HDPE PN12.5 SDR11 - BLUELINE | m |  | 2.43 | 0
| EF COUPLER 125MM (EA) | m |  | 22 | 0
| TEE EQUAL PE100 E/F 125MM | ea |  | 57.75 | 0
| TEE PE100 E/F 125*63MM | ea |  | 139 | 0
| EF REDUCER 125 X 90MM | ea |  | 104.15 | 0
| EF REDUCER 125 X 63MM | ea |  | 26.1 | 0
| EF REDUCER 75 X 63MM | ea |  | 37.5 | 0
| EF REDUCER 63 X 50MM | ea |  | 35.93 | 0
| EF REDUCER 50 X 40MM | ea |  | 35 | 0
| EF REDUCER 40 X 32MM | ea |  | 35 | 0
| EF REDUCER 40 X 25MM | ea |  | 35 | 0
| EF REDUCER 32 X 25MM | ea |  | 20 | 0
| ELBOW PE100 E/F 125MM X 45D | ea |  | 50 | 0
| ELBOW PE100 E/F 125MM X 90D | ea |  | 54 | 0
| HDPE 75mm X 90 D ELBOW | ea |  | 15.55 | 0
| HDPE 63MM X 90 D ELBOW | ea |  | 15 | 0
| HDPE 50MM X 90 D ELBOW | ea |  | 10.87 | 0
| HDPE 40MM X 90 D ELBOW | ea | 3 | 55 | 165
| Reducing Tee 125mm x 90mm | ea |  | 55 | 0
| Reducing Tee 125mm x 32mm | ea |  | 35 | 0
| Reducing Tee 75mm x 63mm | ea |  | 35 | 0
| Reducing Tee 75mm x 50mm | ea |  | 35 | 0
| Reducing Tee 75mm x 32mm | ea |  | 35 | 0
| Reducing Tee 63mm x 32mm | ea |  | 35 | 0
| Reducing Tee 50mm x 40mm | ea |  | 35 | 0
| Reducing Tee 40mm x 25mm | ea |  | 35 | 0
| Reducing Tee 32mm x 25mm | ea |  | 26 | 0
| EF Reducer 50mm x 25mm | ea |  | 35 | 0
| 50mm Tee | ea |  | 10.87 | 0
| 40mm Tee | ea |  | 35 | 0
| 32mm Tee | ea |  | 20 | 0
| HDPE 32mm X 90 D ELBOW | ea | 4 | 20 | 80
| HDPE 25mm X 90 D ELBOW | ea | 5 | 18 | 90
| HDPE 25mm X 45 D ELBOW | ea |  |  | 0
| 25mm Tee | ea |  |  | 0
| PE MAXI STUB FLANGE W/SS BK RING 125X 4" (EA) | ea |  | 35 | 0
| SLUICE VALVE PN16 T/D ACC FLNGD 100MM | ea |  | 102.5 | 0
| Valve Box - Cast Iron - Rectangle - Large - HD | ea |  | 235 | 0
| SADDLE TAPPING EF 125PE X 25PE | ea |  | 100 | 0
| SADDLE TAPPING EF 125PE X 32PE | ea |  | 47.41 | 0
| SADDLE TAPPING EF 125PE X 63PE | ea |  | 41.69 | 0
| 90mm PE X 80mm Copper Transition | ea |  | 200 | 0
| Detectable WATER Marker Tape - 250m | ea |  | 85.55 | 0
| WIPES WELDING PLASSON XL (120 PK) | ea |  | 70 | 0
| Paint Pen - WHITE | ea |  | 19 | 0
|  |  |  | 16 | 0
| 100 Cu Above Grnd | m |  |  | 0
| 80 CU Above Grnd | m |  | 89.2667 | 0
| 65 CU Above Grnd | m |  | 55.8667 | 0
| 50 Cu Above Grnd | m |  | 46.4167 | 0
| 316SS press-fit tube 35mm (was 32 Cu) - WS2 conforming | m | 17.86 | 22.005 | 393.0093 | 18 | ADOPTED 17.86 m; RE-RATED 316SS press-fit 35mm - WS2 conforming base (>DN22); copper alternate in EBC_Alternates (Opens #17) | 316SS press-fit BASE per WS2 (>DN22): pipe rate = Reece Q-459014431 316 tube rate set (project quote; no >35mm needed). PENDING RFQ PER GAP LIST (Gap #2). Copper alternate: EBC_Alternates.
| 316SS press: 32mm x25mm reducing tee | ea | 2 | 29.97 | 59.94 |  |  | 316SS press fitting benchmark = Cu press rate x1.5 (SS press fittings 1.4-1.6x Cu per supplier curves) - pending RFQ (Gap #2)
| 316SS press: 32mm x20mm reducing tee | ea | 1 | 22.5 | 22.5 |  |  | 316SS press fitting benchmark = Cu press rate x1.5 (SS press fittings 1.4-1.6x Cu per supplier curves) - pending RFQ (Gap #2)
| 316SS press-fit tube 28mm (was 25 Cu) - WS2 conforming | m | 112.72 | 13.4383 | 1514.7689 | 113 | ADOPTED 112.72 m; RE-RATED 316SS press-fit 28mm - WS2 conforming base (>DN22)
| 316SS press: B-PRESS WATER EQUAL TEE 32MM (EA) | ea | 1 | 35.265 | 35.265 |  |  | 316SS press fitting benchmark = Cu press rate x1.5 (SS press fittings 1.4-1.6x Cu per supplier curves) - pending RFQ (Gap #2)
| 316SS press: B-PRESS WATER EQUAL TEE 25MM (EA) | ea | 15 | 10.755 | 161.325 |  |  | 316SS press fitting benchmark = Cu press rate x1.5 (SS press fittings 1.4-1.6x Cu per supplier curves) - pending RFQ (Gap #2)
| 20 Cu Above Grnd | m | 19.88 | 13.6667 | 271.6933 | 20 | ADOPTED qty per QUANTITY_RECONCILIATION TPS_NBC - 20 Cu 19.88 m (<=DN22 - retained copper; PEX conforms WS2)
| B-PRESS WATER EQUAL TEE 20MM (EA) | ea | 5 | 9.785 | 48.925
| 50mm Cu 10mm Nut Clip | ea |  | 1.4 | 0
| 32mm Cu 10mm Nut Clip | ea |  | 1.38 | 0
| 25mm Cu 10mm Nut Clip | ea |  | 1.32 | 0
| 20mm Cu 10mm Nut Clip | ea |  | 1.24 | 0
| 10mm Zinc Threaded Rod | m |  | 5.1 | 0
0
| Kembla copper WATER ELBOW 90DEG X 80MM (EA) | ea |  | 118.5 | 0
| Kembla copper WATER ELBOW 90DEG X 65MM (EA) | ea |  | 79.8 | 0
| Kembla copper WATER ELBOW 90DEG X 50MM (EA) | ea |  | 45.02 | 0
| 316SS press: Kembla copper WATER ELBOW 90DEG X 32MM (EA) | ea | 3 | 26.055 | 78.165 |  |  | 316SS press fitting benchmark = Cu press rate x1.5 (SS press fittings 1.4-1.6x Cu per supplier curves) - pending RFQ (Gap #2)
| 316SS press: Kembla copper WATER ELBOW 90DEG X 25MM | ea | 35 | 11.55 | 404.25 |  |  | 316SS press fitting benchmark = Cu press rate x1.5 (SS press fittings 1.4-1.6x Cu per supplier curves) - pending RFQ (Gap #2)
| Kembla copper WATER ELBOW 90DEG X 20MM | ea | 16 | 4.58 | 73.28
0
| 316SS press: 40mm Poly to 32mm Copper B Press Adapter | ea | 1 | 52.5 | 52.5 |  |  | 316SS press fitting benchmark = Cu press rate x1.5 (SS press fittings 1.4-1.6x Cu per supplier curves) - pending RFQ (Gap #2)
| 316SS press: 32mm Poly to 32mm Copper B Press Adapter | ea | 2 | 37.5 | 75 |  |  | 316SS press fitting benchmark = Cu press rate x1.5 (SS press fittings 1.4-1.6x Cu per supplier curves) - pending RFQ (Gap #2)
HIDDEN |  |  |  |  | 0
| 63mm E/F PE 90 Deg Elb |  |  |  | 0
| 63mm E/F PE 45 Deg Elb | ea |  | 13.5 | 0
| 63mm E/F PE TEE | ea |  | 13.5 | 0
| 63x40x63 E/F PE TEE | ea |  | 9.5 | 0
| 63x32x63 E/F PE TEE | ea |  | 18.5 | 0
| 63x25x63 E/F PE TEE | ea |  | 18.5 | 0
| 63mm E/F PE Coupling | ea |  | 6 | 0
| 63x40 E/F PE Reducer Coupling | ea |  | 5.5 | 0
| 63x32 E/F PE Reducer Coupling | ea |  | 17.5 | 0
| 63x25 E/F PE Reducer Coupling | ea |  | 16.5 | 0
| 63PEx50Fi E/F PE Adapter | ea |  | 2.5 | 0
| 63PEx50Mi E/F PE Adapter | ea |  | 43.5 | 0
| 63PEx50Fi E/F PE Tramsiton Union | ea |  | 43.5 | 0
| 63PEx50Mi E/F PE Transition Union | ea |  | 45.5 | 0
| 40mm E/F PE 90 Deg Elb | ea |  | 76 | 0
| 40mm E/F PE 45 Deg Elb | ea |  | 11.5 | 0
| 40mm E/F PE TEE | ea |  | 11.5 | 0
| 40x32x40 E/F PE TEE | ea |  | 12 | 0
| 40x25x40 E/F PE TEE | ea |  | 18.5 | 0
| 40mm E/F PE Coupling | ea |  | 19.5 | 0
| 40x32 E/F PE Reducer Coupling | ea |  | 4.5 | 0
| 40x25 E/F PE Reducer Coupling | ea |  | 10.5 | 0
| 40PEx32Fi E/F PE Adapter | ea |  | 14.5 | 0
| 40PEx32Mi E/F PE Adapter | ea |  | 28.5 | 0
| 40PEx32Fi E/F PE Tramsiton Union | ea |  | 29.5 | 0
| 40PEx32Mi E/F PE Transition Union | ea |  | 36 | 0
| 32mm E/F PE 90 Deg Elb | ea |  | 54 | 0
| 32mm E/F PE 45 Deg Elb | ea |  | 10.5 | 0
| 32mm E/F PE TEE | ea |  | 10 | 0
| 32x25x32 E/F PE TEE | ea |  | 5.5 | 0
| 32mm E/F PE Coupling | ea |  | 18 | 0
| 32x25 E/F PE Reducer Coupling | ea |  | 4.5 | 0
| 32PEx25Fi E/F PE Adapter | ea |  | 6.5 | 0
| 32PEx25Mi E/F PE Adapter | ea |  | 25.5 | 0
| 32mm E/F PE End Cap | ea |  | 22.5 | 0
| 32mm E/F PE End Plug | ea |  | 8.5 | 0
| 25mm E/F PE 90 Deg Elb | ea |  | 6.5 | 0
| 25mm E/F PE 45 Deg Elb | ea |  | 10.5 | 0
| 25mm E/F PE TEE | ea |  | 0 | 0
| 25mm E/F PE Coupling | ea |  | 4.5 | 0
| 25PEx25Fi E/F PE Adapter | ea |  | 4 | 0
| 25PEx25Mi E/F PE Adapter | ea |  | 17 | 0
| 25PEx20Fi E/F PE Adapter | ea |  | 17.5 | 0
| 25PEx20Mi E/F PE Adapter | ea |  | 4.5 | 0
| 25mm E/F PE End Cap | ea |  | 2 | 0
| 25mm E/F PE End Plug | ea |  | 8.5 | 0
HIDDEN |  | ea |  | 4 | 0
| 100mm CU Crimp 90 DEG FxF Elbow |  |  |  | 0
| 100mm CU Crimp 45 DEG FxF Elbow | ea |  | 137 | 0
| 100mm CU Crimp Tee | ea |  | 139.5 | 0
| 100x50x100 CU Crimp Tee | ea |  | 183 | 0
| 100x50 CU Crimp Reducer | ea |  | 184.5 | 0
| 100mm CU Crimp Repair Coupling | ea |  | 56 | 0
| 100mm CU Crimp Coupling | ea |  | 103 | 0
| 100Cu x 100Flange CU Crimp Coupling | ea |  | 95 | 0
| 80mm x 65mm Cu Reducer | ea |  | 100 | 0
| 65mm Cu Crimp Tee | ea |  | 130.1 | 0
| 65mmX 50 Cu WAT Crimp Reducer | ea |  | 60 | 0
| 65mmX 32 Cu WAT Crimp Reducer | ea |  | 55 | 0
| 65 mmX 20 Cu WAT Crimp Reducer | ea |  | 50 | 0
| 50mm CU Crimp 90 DEG FxF Elbow | ea |  | 99.5 | 0
| 50mm CU Crimp 45 DEG FxF Elbow | ea |  | 33.5 | 0
| 50mm CU Crimp Tee | ea |  | 56.35 | 0
| 50x40x50 CU Crimp Tee | ea |  | 60.5 | 0
| 50x40x40 CU Crimp Tee | ea |  | 61 | 0
| 50x32x50 CU Crimp Tee | ea |  | 65 | 0
| 50x32x32 CU Crimp Tee | ea |  | 65 | 0
| 50x32x40 CU Crimp Tee | ea |  | 65 | 0
| 50x25x50 CU Crimp Tee | ea |  | 65 | 0
| 50x20x50 CU Crimp Tee | ea |  | 45 | 0
| 50x15x50 CU Crimp Tee | ea |  | 55 | 0
| 50x40 CU Crimp Reducer | ea |  | 55 | 0
| 50x32 CU Crimp Reducer | ea |  | 21.5 | 0
| 50x25 CU Crimp Reducer | ea |  | 34.92 | 0
| 50x20 CU Crimp Reducer | ea |  | 35 | 0
| 50x15 CU Crimp Reducer | ea |  | 22 | 0
| 50Cu x 50Mi CU Crimp Adapter | ea |  | 22 | 0
| 50Cu x 50Fi CU Crimp Adapter | ea |  | 78 | 0
| 50mm CU Crimp Repair Coupling | ea |  | 89 | 0
| 50mm CU Crimp Coupling | ea |  | 21 | 0
| 50Cu x 50Flange CU Crimp Coupling | ea |  | 21 | 0
| 50mm CU Crimp Cap | ea |  | 0 | 0
| 50Cu x W69/Barrell Barrell Union CU Crimp | ea |  | 0 | 0
| 40mm CU Crimp 90 DEG FxF Elbow | ea |  | 0 | 0
| 40mm CU Crimp 45 DEG FxF Elbow | ea |  | 0 | 0
| 40mm CU Crimp 90 DEG MxF Elbow | ea |  | 0 | 0
| 40mm CU Crimp 45 DEG MxF Elbow | ea |  | 0 | 0
| 40mm CU Crimp Tee | ea |  | 0 | 0
| 40x32x40 CU Crimp Tee | ea |  | 0 | 0
| 40x32x32 CU Crimp Tee | ea |  | 0 | 0
| 40x32x25 CU Crimp Tee | ea |  | 0 | 0
| 40x25x40 CU Crimp Tee | ea |  | 0 | 0
| 40x25x20 CU Crimp Tee | ea |  | 0 | 0
| 40x20x40 CU Crimp Tee | ea |  | 0 | 0
| 40x15x40 CU Crimp Tee | ea |  | 0 | 0
| 40x32 CU Crimp Reducer | ea |  | 0 | 0
| 40x25 CU Crimp Reducer | ea |  | 0 | 0
| 40x20 CU Crimp Reducer | ea |  | 0 | 0
| 40x15 CU Crimp Reducer | ea |  | 0 | 0
| 40Cu x 40Mi CU Crimp Adapter | ea |  | 0 | 0
| 40Cu x 40Fi CU Crimp Adapter | ea |  | 0 | 0
| 40mm CU Crimp Repair Coupling | ea |  | 0 | 0
| 40mm CU Crimp Coupling | ea |  | 0 | 0
| 40Cu x 40Flange CU Crimp Coupling | ea |  | 0 | 0
| 40mm CU Crimp Cap | ea |  | 0 | 0
| 40Cu x W69/Barrell Barrell Union CU Crimp | ea |  | 0 | 0
| 32mm CU Crimp 90 DEG FxF Elbow | ea |  | 0 | 0
| 32mm CU Crimp 45 DEG FxF Elbow | ea |  | 0 | 0
| 32mm CU Crimp 90 DEG MxF Elbow | ea |  | 0 | 0
| 32mm CU Crimp 45 DEG MxF Elbow | ea |  | 0 | 0
| 32mm CU Crimp Tee | ea |  | 0 | 0
| 32x25x32 CU Crimp Tee | ea |  | 18.54 | 0
| 32x25x20 CU Crimp Tee | ea |  | 0 | 0
| 32x20x32 CU Crimp Tee | ea |  | 0 | 0
| 32x20x20 CU Crimp Tee | ea |  | 18.35 | 0
| 32x20x15 CU Crimp Tee | ea |  | 0 | 0
| 32x15x32 CU Crimp Tee | ea |  | 0 | 0
| 32x15x25 CU Crimp Tee | ea |  | 0 | 0
| 32x15x20 CU Crimp Tee | ea |  | 0 | 0
| 32x15x15 CU Crimp Tee | ea |  | 0 | 0
| COUPLING RED CU KEMPRESS WATER 32MM X 25MM | ea |  | 20 | 0
| 32x20 CU Crimp Reducer | ea |  | 16.33 | 0
| 32x15 CU Crimp Reducer | ea |  | 0 | 0
| 32Cu x 32Mi CU Crimp Adapter | ea |  | 0 | 0
| 32Cu x 32Fi CU Crimp Adapter | ea |  | 0 | 0
| 32mm CU Crimp Repair Coupling | ea |  | 0 | 0
| 32mm CU Crimp Coupling | ea |  | 0 | 0
| 32mm CU Crimp Cap | ea |  | 0 | 0
| 32Cu x W69/Barrell Barrell Union CU Crimp | ea |  | 0 | 0
| 25mm CU Crimp 90 DEG FxF Elbow | ea |  | 0 | 0
| 25mm CU Crimp 45 DEG FxF Elbow | ea |  | 0 | 0
| 25mm CU Crimp 90 DEG MxF Elbow | ea |  | 0 | 0
| 25mm CU Crimp 45 DEG MxF Elbow | ea |  | 0 | 0
| 25mm CU Crimp Tee | ea |  | 0 | 0
| 25x20x25 CU Crimp Tee | ea |  | 0 | 0
| 25x20x20 CU Crimp Tee | ea |  | 0 | 0
| 25x20x15 CU Crimp Tee | ea |  | 0 | 0
| 25x15x25 CU Crimp Tee | ea |  | 0 | 0
| 25x15x20 CU Crimp Tee | ea |  | 0 | 0
| 25x15x15 CU Crimp Tee | ea |  | 0 | 0
| 25x20 CU Crimp Reducer | ea |  | 0 | 0
| 25x15 CU Crimp Reducer | ea |  | 0 | 0
| 25Cu x 25Mi CU Crimp Adapter | ea |  | 0 | 0
| 25Cu x 25Fi CU Crimp Adapter | ea |  | 0 | 0
| 25mm CU Crimp Repair Coupling | ea |  | 0 | 0
| 25mm CU Crimp Coupling | ea |  | 0 | 0
| 25mm CU Crimp Cap | ea |  | 0 | 0
| 25Cu x W69/Barrell Barrell Union CU Crimp | ea |  | 0 | 0
| 20mm CU Crimp 90 DEG FxF Elbow | ea |  | 0 | 0
| 20mm CU Crimp 45 DEG FxF Elbow | ea |  | 0 | 0
| 20mm CU Crimp 90 DEG MxF Elbow | ea |  | 0 | 0
| 20mm CU Crimp 45 DEG MxF Elbow | ea |  | 0 | 0
| 20mm CU Crimp Tee | ea |  | 0 | 0
| 20x15x20 CU Crimp Tee | ea |  | 5.61 | 0
| 20x15x15 CU Crimp Tee | ea |  | 0 | 0
| 20x15 CU Crimp Reducer | ea |  | 0 | 0
| 20Cu x 20Mi CU Crimp Adapter | ea |  | 0 | 0
| 20Cu x 20Fi CU Crimp Adapter | ea |  | 0 | 0
| 20mm CU Crimp Repair Coupling | ea |  | 0 | 0
| 20mm CU Crimp Coupling | ea |  | 0 | 0
| 20mm CU Crimp Cap | ea |  | 0 | 0
| 20Cu x W69/Barrell Barrell Union CU Crimp | ea |  | 0 | 0
| 15mm CU Crimp 90 DEG FxF Elbow | ea |  | 0 | 0
| 15mm CU Crimp 45 DEG FxF Elbow | ea |  | 0 | 0
| 15mm CU Crimp 90 DEG MxF Elbow | ea |  | 0 | 0
| 15mm CU Crimp 45 DEG MxF Elbow | ea |  | 0 | 0
| 15mm CU Crimp Tee | ea |  | 0 | 0
| 15Cu x 15Mi CU Crimp Adapter | ea |  | 0 | 0
| 15Cu x 15Fi CU Crimp Adapter | ea |  | 0 | 0
| 15Cu Fi BP, wall elbow | ea |  | 0 | 0
| 15Cu Mi BP, Wall elbow - 90 Long | ea |  | 0 | 0
| 15Cu Mi BP, Wall elbow - 120+ Long | ea |  | 0 | 0
| 15mm CU Crimp Repair Coupling | ea |  | 0 | 0
| 15mm CU Crimp Coupling | ea |  | 0 | 0
| 15mm CU Crimp Cap | ea |  | 0 | 0
| 15Cu x W69/Barrell Barrell Union CU Crimp | ea |  | 0 | 0
| 50mm Ball Valve Fi | ea |  | 0 | 0
| 40mm Ball Valve Fi | ea |  | 0 | 0
| 32mm Ball Valve Fi | ea |  | 0 | 0
| 25mm Ball Valve Fi | ea |  | 26.25 | 0
| 20mm Ball Valve Fi | ea |  | 0 | 0
| 15mm Ball Valve Fi | ea |  | 0 | 0
| 50mm Mi BRS Nipple | ea |  | 0 | 0
| 50mm Fi BRS Socket | ea |  | 0 | 0
| 50mm Mi BRS Union | ea |  | 0 | 0
| 50mm Fi BRS Union | ea |  | 0 | 0
| 50mm BRS Plug | ea |  | 0 | 0
| 50mm BRS Cap | ea |  | 0 | 0
| 40mm Mi BRS Nipple | ea |  | 0 | 0
| 40mm Fi BRS Socket | ea |  | 0 | 0
| 40mm Mi BRS Union | ea |  | 0 | 0
| 40mm Fi BRS Union | ea |  | 0 | 0
| 40mm BRS Plug | ea |  | 0 | 0
| 40mm BRS Cap | ea |  | 0 | 0
| 32mm Mi BRS Nipple | ea |  | 0 | 0
| 32mm Fi BRS Socket | ea |  | 0 | 0
| 32mm Mi BRS Union | ea |  | 0 | 0
| 32mm Fi BRS Union | ea |  | 0 | 0
| 32mm BRS Plug | ea |  | 0 | 0
| 32mm BRS Cap | ea |  | 0 | 0
| 25mm Mi BRS Nipple | ea |  | 0 | 0
| 25mm Fi BRS Socket | ea |  | 0 | 0
| 25mm Mi BRS Union | ea |  | 0 | 0
| 25mm Fi BRS Union | ea |  | 0 | 0
| 25mm BRS Plug | ea |  | 0 | 0
| 25mm BRS Cap | ea |  | 0 | 0
|  | ea |  | 0 | 0
| 20mm pex Pipe - Black | m | 157.82 | 2.7468 | 433.5056 | 158 | ADOPTED qty per QUANTITY_RECONCILIATION TPS_NBC |  | 434
| 20mm pex Pipe - Red | m | 65.29 | 3.5 | 228.515 | 66 | ADOPTED qty per QUANTITY_RECONCILIATION TPS_NBC
| 15mm Pex pipe - Black | m |  | 0 | 0
| 15mm Pex pipe - Red | m |  | 0 | 0
| 20 pex Elbow | m | 104 | 5.15 | 535.6
| 20 Pex TEE | ea | 66 | 7.49 | 494.34
| 20x15 Pex TEE | ea |  | 0 | 0
| 20 PEX Mi Adapter | ea |  | 0 | 0
| 20 PEX Fi Adapter | ea |  | 0 | 0
| 20x15 Pex Reducer | ea |  | 0 | 0
| PEX - 32 Cu Crimp Adapter | ea | 1 | 20 | 20
| PEX - 25 Cu Crimp Adapter | ea | 14 | 14 | 196
| PEX - 20 Cu Crimp Adapter | ea | 5 | 10.05 | 50.25
| 20 PEXxCU Crimp conversion coupling | ea |  | 0 | 0
| 20 PEX Straight coupling | ea |  | 0 | 0
| 15 Pex Elbow | ea |  | 0 | 0
| 15 Pex TEE | ea |  | 0 | 0
| 15 PEXMi Adapter | ea |  | 0 | 0
| 15 PEX Fi Adapter | ea |  | 0 | 0
| 15 PEX Fi BP, wall elbow | ea |  | 0 | 0
| 15 PEX Mi BP, Wall elbow - 90 Long | ea |  | 0 | 0
| 15 PEX Mi BP, Wall elbow - 120+ Long | ea |  | 0 | 0
| 15 PEXxCU Crimp conversion coupling | ea |  | 0 | 0
| 15 PEX Straight coupling | ea |  | 0 | 0
|  | ea |  | 0 | 0
| Hose Taps Complete | ea | 5 | 56 | 280 | 4 | ADOPTED qty per QUANTITY_RECONCILIATION TPS_NBC - hose taps 5 (drawn-but-uncounted symbol NBC-201; H002 n.15 adopt higher)
| 100 FL DICL SLUICE VALVE | ea |  | 202.94 | 0
| 125PE*4" (100mm) - MaxiStub W/Stainless Steel Backing Ring | ea |  | 92.67 | 0
| 100mm PE*DI Gasket Kit Complete Parts & Labour | ea |  | 24.71 | 0
| 100mm DI*DI Gasket Kit Complete | ea |  | 20 | 0
| Valve Spindle Riser - 600Long | ea |  | 136.94 | 0
| 100mm Dual Pillar Hydrant Complete_ RG Base 1500 High w/landing Valves_OPTION | ea |  | 365 | 0
| 125mm PE x 100mm GALV ADAPTER - Acutech Brand | ea |  | 201.43 | 0
| Red caps and chain - suit 65mm QLD Landing valve | ea |  | 5 | 0
| RPZD 32mm | ea |  | 853 | 0
| RPZD 20mm | ea | 4 | 503 | 2012 | 3 | ADOPTED qty per QUANTITY_RECONCILIATION TPS_NBC - 20mm RPZD 4 (~4 positions NBC-202, adopt higher)
| RPZD 100mm | ea |  | 1809.63 | 0
| Office - Water & Rough IN | ea |  | 1650 | 0
| Ofice - NOGINS & Fixings | ea |  | 160 | 0
| Safety shr fittings | ea |  | 750 | 0
| In Grnd Fittings misc | ea |  | 450 | 0
| Abv Grnd Fittings misc | ea |  | 1250 | 0
| HWU quickie kit | ea |  | 190 | 0
| TMV | ea |  | 412.59 | 0
| 20mm check valve | ea | 4 | 80 | 320
| 20mm Isolavtive valve | ea | 3 | 18.65 | 55.95
| 25mm Isolavtive valve | ea |  | 26.55 | 0
| 32mm Isolavtive valve | ea | 1 | 60 | 60
| 50mm Isolavtive valve | ea |  | 92.1 | 0
| 450 SQ PIT | ea |  | 30 | 0
| Dock Office Water Mat | ea |  | 1850 | 0
| 25mm RPZD | ea |  | 1800 | 0
0
| misc. | ea |  | 3800 | 0
| 150mm isolation valve in valve pit (connect to authority watermain ) | ea |  | 371.37 | 0
| 25mm DCW Isolation vlave in valve pit with path box cover | ea |  | 469.04 | 0
| 25mm water meter in tamper steel cage with isolative valves in both side | ea |  | 659.8 | 0
| TMV in Box | ea | 10 | 587.96 | 5879.6
| 100 mm Water meter | ea |  | 641.58 | 0
| 32 valve in pit | ea |  | 50 | 0
| 50mm control valve | ea |  | 31.71 | 0
| TLV under basin | ea |  | 146.09 | 0
| AUTOMATIC TRAP PRIMER | ea | 2 | 99.49 | 198.98
| Basket trap (water charge / self-priming) - water layer | ea | 2 | 250 | 500 |  | ADOPTED 2 (TPS_NBC water layer) - distinct from sewer basket traps, do not merge
SEWER DRAINAGE -
Description
| PIPE DWV PVC S/WELD 150MM - In Grnd | m |  | 14.49 | 0
| PIPE DWV SN8 PVC S/WELD 100MM | m | 230.07 | 9.5496 | 2197.0765 | 231 | ADOPTED qty per QUANTITY_RECONCILIATION TPS_NBC
| 150MM * 45D PVC JUNCTION | ea |  | 9.66 | 0
| 100MM * 45D PVC JUNCTION | ea | 80 | 4.7886 | 383.088
| 150MM X 100MM 45D PVC JUNCTION | ea |  | 13.8 | 0
| 100*40 PVC DWV JUNCTION | ea | 2 | 5 | 10
| 100*50 PVC DWV JUNCTION | ea |  | 6.5274 | 0
| 100MM * 65 PVC PVC JUNCTION | ea |  | 8.5974 | 0
| 150MM X 45 Deg Bend | ea |  | 6.9 | 0
| 150MM X 90 Deg Bend | ea |  | 6.9 | 0
| 100MM X 90Deg Bend | ea | 75 | 2.5668 | 192.51
| 100MM X 45Deg Bend | ea | 66 | 2.3308 | 153.8341
| DWV PIPE REDUCER 150X100mm | ea |  | 5.52 | 0
| DWV PIPE REDUCER 100 X 50mm | ea | 3 | 2.6772 | 8.0316
| DWV PIPE REDUCER 100 X 40mm | ea | 1 | 2 | 2
| PIPE DWV PVC S/WELD 100MM - In Grnd | m |  | 6.9 | 0
| PIPE DWV PVC S/WELD 65MM - In Grnd | m |  | 5.52 | 0
| 63 HDPE PN12.5 SDR11 - BLACK or CREAM - In Grnd | m |  | 8.7354 | 0
| PIPE DWV PVC S/WELD 50mm | m | 12.68 | 3.726 | 47.2457 | 13 | ADOPTED qty per QUANTITY_RECONCILIATION TPS_NBC
| PIPE DWV PVC S/WELD 40mm | m | 25.61 | 2.898 | 74.2178 | 26 | ADOPTED qty per QUANTITY_RECONCILIATION TPS_NBC
| 65MM * 45D PVC JUNCTION | ea |  | 3.5 | 0
| 50MM * 45D PVC JUNCTION | ea |  | 3 | 0
| DWV BEND 65X 45 DEG | ea |  | 2.3322 | 0
| DWV BEND 65X 90 DEG | ea |  | 2.33 | 0
| DWV BEND 40 X 45 DEG | ea | 18 | 4 | 72
| DWV BEND 40 X 85 DEG | ea | 18 | 4.14 | 74.52
| DWV BEND 50 X 45 DEG | ea | 8 | 0.9384 | 7.5072
| DWV BEND 50 X85 DEG | ea | 7 | 11.7162 | 82.0134
| 50mm Condensate INSULATION | m |  | 14 | 0
| 100mm Condensate INSULATION | m |  | 6 | 0
0
| 150mm - Gas Tight H/D Cast Iron Clearout (Peepeye) | ea |  | 40 | 0
| 150mm Clear Out Cover - L/D - Brass | ea |  | 30 | 0
| 100mm - Gas Tight H/D Cast Iron Clearout (Peepeye) | ea | 18 | 33 | 594
| 100mm Clear Out Cover - L/D - Brass | ea | 18 | 23.26 | 418.68
| 100 mm Inspection Opening | ea | 10 | 50 | 500
| 100mm Trapped point - 100mm Gully Trap | ea |  | 7.65 | 0
| FWG - 100mm Gully Trap | ea |  | 7.65 | 0
| FWG - 100mm 4-way Riser | ea | 9 | 13.59 | 122.31
| FWG - Grate - Tile Insert 100*100 Chrome Plated | ea |  | 0 | 0
| In-Wall TD & View Panel - SS | ea | 2 | 75 | 150
0
| 100mm PVC 10mm nut hanging clip | ea |  | 2 | 0
| 50mm PVC 10mm nut hanging clip | ea |  | 1.5 | 0
| 10mm Zinc Threaded Rod | m |  | 0 | 0
0
| Glue - Blue - 4Ltr | ea |  | 26.4 | 0
| Primer - Red - 4Ltr | ea |  | 23 | 0
| Detectable SEWER Marker Tape - 250m | ea |  | 75 | 0
| 100mm AbleFlex Roll | ea |  | 22 | 0
| Concrete Mix bag | ea |  | 10 | 0
0
| External Sewer Mains fitting | ea |  | 520 | 0
| Vents Complete | ea |  | 230 | 0
| Office Drainage mat | ea |  | 2800 | 0
| Dock Office Drainage Mat | ea |  | 950 | 0
| misc. | ea |  | 1250 | 0
| Overflow Gully | ea | 1 | 200 | 200
| COS | ea |  | 120 | 0
| Articulation/expansion joint hardware - H1 'P' reactive site adder (slab entries, risers, <=6 m DP spacing) | item | 1 | 2500 | 2500 |  | NewItems #12 allowance ~25 joints @ ~$100 avg (H-NBC-300 det.1) - pending Storm Plastics RFQ (Gap #4); labour in T5-05
| SIVEL EXPANSION JOINT | ea | 1 | 100 | 100
| FWG | ea | 1 | 250 | 250
| Basket trap | ea | 12 | 250 | 3000
| Fire Collars & Misc | ea |  | 300 | 0
| plaster /slip trap | ea |  | 1200 | 0
| Basket Arrestors for Floor Drains | ea |  | 350 | 0
Vent
Description
| Vertical vent risers x13 (O50-O100, terminate 300 mm above roof) - height + flashing allowance | EA | 13 | 95 | 1235 |  | NewItems #7 allowance - ~4 m/riser + roof-colour flashing per SD8; heights from sections at Phase 6
| PIPE DWV SN8 PVC S/WELD 100MM | m | 17.06 | 9.5496 | 162.9162 | 17 | ADOPTED qty per QUANTITY_RECONCILIATION TPS_NBC (vent horizontal plan only - 13 vertical risers added below)
| PIPE DWV PVC S/WELD 50mm | m | 0.7 | 3.726 | 2.6082 | 1 | ADOPTED qty per QUANTITY_RECONCILIATION TPS_NBC
| 100MM X 90Deg Bend | ea | 12 | 2.5668 | 30.8016
| 100MM X 45Deg Bend | ea | 6 | 2.3308 | 13.9849
| 100MM * 45D PVC JUNCTION | ea | 1 | 4.7886 | 4.7886
| DWV BEND 50 X85 DEG | ea | 1 | 11.7162 | 11.7162
| DWV PIPE REDUCER 100 X 50mm | ea | 1 | 2.6772 | 2.6772
| 100 mm Inspection Opening | ea | 1 | 50 | 50
| 110 HDPE | m | 0 | 11.6 | 0 | 2 | MERGED into TW package (Opens #25): 1.98 m vent-layer stub counted once in r813 54.78 m
| 110 HDPE 90 Deg Bend ( TRADE WASTE ) | ea | 0 | 10 | 0 | 1 | MERGED into TW 90-bend count r814 (Opens #25)
| 110 HDPE X 45 DEG (TRADE WASTE ) | ea | 0 | 5.16 | 0 | 1 | MERGED into TW 45-bend count r815 (Opens #25)
| Trench Drain ( spec in drawing ) | m | 1 | 500 | 500
Trade Waste
Description
| 110 HDPE (TRADE WASTE DRAIN ) | m | 54.78 | 17 | 931.26 | 53 | ADOPTED qty per QUANTITY_RECONCILIATION TPS_NBC - 52.80 TW layer + 1.98 vent-layer stub merged, counted once
| 110 HDPE 90 Deg Bend ( TRADE WASTE ) | ea | 8 | 5.55 | 44.4 | 7 | ADOPTED qty per QUANTITY_RECONCILIATION TPS_NBC - TW 90 bends 8 (7 + 1 vent-layer)
| 110 HDPE X 45 DEG (TRADE WASTE ) | ea | 24 | 8.98 | 215.52 | 23 | ADOPTED qty per QUANTITY_RECONCILIATION TPS_NBC - TW 45 bends 24 (23 + 1 vent-layer)
| JUNCTION 110 HDPE X 45 DEG | ea | 16 | 4.73 | 75.68
| JUNCTION 110 HDPE X 50 HDPE 45 DEG | ea | 2 | 10 | 20
| 100 HDPE (TRADE WASTE DRAIN ) | m |  | 10 | 0
| JUNCTION 100 HDPE X 45 DEG | ea |  | 4 | 0
| 110 HDPE X 100 HDPE REDUCER | ea |  | 15 | 0
| 110 HDPE X 50 HDPE REDUCER | ea | 5 | 12 | 60
| 100 HDPE 90 Deg Bend ( TRADE WASTE ) | ea |  | 8 | 0
| 100 HDPE X 45 DEG (TRADE WASTE ) | ea |  | 5.16 | 0
| 65 HDPE (TRADE WASTE DRAIN ) | m |  | 8 | 0
| 65 HDPE X 45 DEG (TRADE WASTE ) | ea |  | 4 | 0
| 65 HDPE X 90 DEG (TRADE WASTE ) | ea |  | 5 | 0
| 50 HDPE (TRADE WASTE DRAIN ) | ea | 12.47 | 7 | 87.29 | 13 | ADOPTED qty per QUANTITY_RECONCILIATION TPS_NBC
| 50 HDPE X 90 DEG (TRADE WASTE ) | ea | 9 | 4 | 36 | 10 | ADOPTED qty per QUANTITY_RECONCILIATION TPS_NBC - Geberit bend 50x88.5 = 9
| 50 HDPE X 45 DEG (TRADE WASTE ) | ea | 5 | 3.8 | 19
| BUCKEY TRAP /SILT TRAP | ea | 1 | 100 | 100
| IOS TRADE WASTE | ea | 1 | 25 | 25
| in wall tundish | ea | 2 | 75 | 150
| tundish | ea | 4 | 60 | 240
| 50mm rpzd | ea | 2 | 880 | 1760 | 1 | ADOPTED qty per QUANTITY_RECONCILIATION TPS_NBC - 50mm RPZD 2 (verify vs NBC-202 positions, Opens #15)
| 100mm check valve | ea | 1 | 1200 | 1200
| Geberit 4 Way Riser 110x56 | ea | 6 | 33 | 198
| Geberit Exp Socket 110 | ea | 2 | 13 | 26
| Geberit Adj DT Trap Bottom Hdpe 110mm | ea | 6 | 41.53 | 249.18
STORMWATER DRAINAGE
Description
| Roof-DP in-ground connection stub to 'CONNECT TO CIVIL' (allow 2 m O100 DWV + bend + coupling) | EA | 19 | 40 | 760 |  | ADOPTED 19 EA (NewItems #5; count RFI Opens #23). Stub ends at CONNECT TO CIVIL - civil beyond is TCS (L2); expansion provision <=6 m spacing
| PIPE 600MM - RIBBED | m |  | 165.6 | 0
| PIPE 450MM - RIBBED | m |  | 89.7 | 0
| PIPE 375MM - RIBBED BLACK MAX | m |  | 66.24 | 0
| PIPE 300MM - RIBBED BLACK MAX | m |  | 0 | 0
| PIPE DWV SN8 PVC S/WELD 375MM | m |  | 85.1046 | 0
| PIPE DWV SN8 PVC S/WELD 300MM | m |  | 84.18 | 0
| PIPE DWV SN4 PVC S/WELD 300MM | m |  | 68.77 | 0
| PIPE SW H/D PVC S/WELD 300MM | m |  | 55.2 | 0
| PIPE DWV SN8 PVC S/WELD 225MM | m |  | 55.2 | 0
| PIPE DWV SN4 PVC S/WELD 225MM | m |  | 42.78 | 0
| PIPE SW H/D PVC S/WELD 225MM | m |  | 32.66 | 0
| PIPE DWV SN8 PVC S/WELD 150MM | m |  | 19.55 | 0
| PIPE DWV SN4 PVC S/WELD 150MM | m |  | 16.1 | 0
| PIPE DWV SN8 PVC S/WELD 150MM - Suspended | m |  | 19.55 | 0
| PIPE DWV SN4 PVC S/WELD 150MM | m |  | 16.56 | 0
| PIPE DWV SN8 PVC S/WELD 100MM | m |  | 6.693 | 0
| PIPE DWV SN4 PVC S/WELD 100MM | m |  | 6.9 | 0
| PIPE DWV SN8 PVC S/WELD 50MM | m |  | 6.693 | 0
|  |  |  | 0 | 0
| DWV Grade Option |  |  | 0 | 0
|  | ea |  | 0 | 0
| 600*225 Ribbed Saddle | ea |  | 676.2 | 0
| 600*45Deg RIBBED Bend | ea |  | 897 | 0
| 600*450 Ribbed Reducer | ea |  | 1518 | 0
| 450*375 Ribbed*PVC Reducer | ea |  | 634.8 | 0
| 450 45 Deg ribbed Bend | ea |  | 800.4 | 0
| 450 * 225 Ribbed Saddle | ea |  | 441.6 | 0
| 375mm X 45Deg Junction | ea |  | 579.6 | 0
| 375X300X45D PVC JUNCTION | ea |  | 776.0982 | 0
| 375X225X45D PVC JUNCTION | ea |  | 777.4782 | 0
| 375MM X 300MM Reducer | ea |  | 524.4 | 0
| 375MM X 225MM Reducer | ea |  | 496.8 | 0
| 375MM X 90Deg Bend | ea |  | 745.2 | 0
| 375MM X 45Deg Bend | ea |  | 621 | 0
| 300MM * 45D PVC JUNCTION | ea |  | 496.8 | 0
| 300X225X45D PVC JUNCTION | ea |  | 441.6 | 0
| 300MM X 225MM Reducer | ea |  | 262.2 | 0
| 300MM X 90Deg Bend | ea |  | 345 | 0
| 300MM X 45Deg Bend | ea |  | 262.2 | 0
| 300MM X 150 Junction | ea |  | 455.4 | 0
| 225MM * 45D PVC JUNCTION | ea |  | 117.645 | 0
| 225X150X45D PVC JUNCTION | ea |  | 289.8 | 0
| 225MM X 90Deg Bend | ea |  | 85.56 | 0
| 225MM X 45Deg Bend | ea |  | 84.18 | 0
| 225MM X 150MM Reducer | ea |  | 62.1 | 0
| 150 PVC DWV 45Deg Junct | ea |  | 24.84 | 0
| 150MM X 90Deg Bend | ea |  | 22.08 | 0
| 150MM X 45Deg Bend | ea |  | 16.56 | 0
| 150X100X45D PVC JUNCTION | ea |  | 22.08 | 0
| PVC PIPE REDUCER 150X 100 mm | ea |  | 22.08 | 0
| 100MM * 45D PVC JUNCTION | ea |  | 6.486 | 0
| 100X50 X45D PVC JUNCTION | ea |  | 22.08 | 0
| PVC PIPE REDUCER 100X 50 mm | ea |  | 22.08 | 0
| 100MM X 90Deg Bend | ea |  | 16.56 | 0
| 100MM X 45Deg Bend | ea |  | 16.56 | 0
| 50 PVC X 45D PVC JUNCTION | ea |  | 19.32 | 0
| 50MM X 90Deg PVC Bend | ea |  | 0.897 | 0
| 50MM X 45Deg PVC Bend | ea |  | 0.897 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
| 150mm PVC 10mm nut hanging clip | ea |  | 2.622 | 0
| 10mm Zinc Threaded Rod | m |  | 2.76 | 0
| Glue - Blue - 4Ltr | ea |  | 36.432 | 0
| Primer - Red - 4Ltr | ea |  | 31.74 | 0
|  |  |  | 0 | 0
| SW_RRJ (RIBBED) Fittings |  |  | 0 | 0
|  |  |  | 0 | 0
| 375MM X 45Deg Bend | ea |  | 362.1396 | 0
| DN 375 X DN150 45 DEG BLACKMAX REDUCING JUNCTION (PVC FAB) | ea |  | 828 | 0
| DN375 x dn225 BlackMax® Reducing Adaptor FF RRJ x DWV SWJ (PVC Fab) | ea |  | 552 | 0
|  |  |  | 0 | 0
| DN 300 X DN150 45 DEG BLACKMAX REDUCING JUNCTION (PVC FAB) | ea |  | 690 | 0
| DN300 BLACK MAX 45 DEG BEND | ea |  | 414 | 0
| DN300 x dn225 BlackMax® Reducing Adaptor FF RRJ x DWV SWJ (PVC Fab) | ea |  | 414 | 0
| DN300 BLACK MAX 45 DEG BEND | ea |  | 414 | 0
| SWGP 1 300 x300 x450 | ea |  | 127.54 | 0
| SWGP 2 600x600 x600 | ea |  | 375 | 0
| SWGP 4 450x450x600 | ea |  | 250 | 0
| 150mm Cap | ea |  | 20.7 | 0
| 150mm expansion coupler | ea |  | 110.4 | 0
| 450X450 GRATED SW GULLY | ea |  | 180 | 0
FITOFF
| Fit-Off consumable material - per adopted fixture (allow $30/EA x 93) | ea | 93 | 30 | 2790 | 1 | Fit-off consumable basis re-based: 93 adopted fixtures x $30/EA allowance (was $1,800 lump)
| Fit-Off Material; Ground & First Floor - | ea |  | 0 | 0 |  | stray rate cleared (was 1801 with no qty)
| Seismic restraint hardware - AS1170.4 EDC 2, subsoil Ce (channel/brace/strap kits) | item | 1 | 3500 | 3500 |  | Gap #3 allowance (~2.5% rough-in material) - RFQ nVent/Unistrut/Hilti pending; install labour T3-04/T4-07; layout drafting only (CL C7)
| HWU mounting - 316 SS plinth/stand + fixings per H-NBC-301 detail (2x Rheem 315L) | EA | 2 | 260 | 520 |  | RULE 4 GAP CLOSED: H-NBC-301 install detail calls up safe tray + SS plinth + seismic strap. Safe tray is priced in the big-ticket block (AC12 $52.80/unit); seismic strap is in the seismic hardware allowance (r932) with labour at T4-07; the PLINTH/STAND was priced nowhere. Estimator basis: fabricated 316 SS plinth ~$220 + dynabolt/Unistrut fixings ~$40. Install labour already in T4-03 - materials only here.
SUB TOTALS
414596.5146
|  |  |  | Contingency | 12%
|  |  |  | Deliveries | 6500
TOTALS
470848.0963
Excavation/Quarry/Misc/ Takeoff.
|  | Qty | Unit
| Avrg Trench = .900D*.450W | 387.68 | m
| L/M Of Asphalt Reinstate | 0 | m
| M2 Of Asphalt Reinstate | 0 | m2
| L/M Of CBR Reinstate | 0 | m
| L/M of Inground Pipe (Average Depth) | 387.68 | m
| L/M of Inground Pipe (Deeper Than Average Depth) |  | m
| Avergage of trtenches 'Shared'…. Shared trench Factor | 0.1 | m
| SEWER / SW / TW - InGrnd |  | m | 0%
| WAT / FIRE - InGrnd |  | m | 0%
| SPK - InGrnd |  | m | 0%
|  | D | W | L | Spoil/Compact Factor; | Shared Trench Factor | Total m3 - EXCAVATED | Total M3 - Bed, Pipe, Cover reduction | Total M3 - Backfill Req (Less Bed&Pipe) | Total M3 - Spoil - REMOVE | TCS Load - Haulage & dump rate only
| L/M of Inground Pipe (Average Depth) | 0.95 | 0.6 | 387.68 | 1.3 | 0.1 | 265.1731
| L/M of Inground Pipe (Deeper Than Average Depth) | 1.1 | 0.5 | 0 | 1.3 | 0 | 0
| L/M of Bed, Pipe, Cover material reduction (Average Depth) | 0.35 | 0.6 | 387.68 | 0 | 0.1 |  | 73.2715
| L/M of Bed, Pipe, Cover material reduction (Deeper Than Average Depth) | 0.2 | 0.5 | 0 | 0 | 0 |  | 0
| L/M of BACKFILL required (Average Depth) | 0.95 | 0.6 | 387.68 | 1.3 | 0.1 |  |  | 191.9016
| L/M of BACKFILL required (Deeper Than Average Depth) | 1.1 | 0.5 | 0 | 1.3 | 0 |  |  | 0
[10 empty] | QTY | Rate | Total
[7 empty] | 265.1731 | 73.2715 | 191.9016 | 73.2715 | 15 | 1099.0728
| Thrust Block Concrete | m3/TB | Qty | Total m3 | Contingency | Total m3 | Total Cost
|  | 0.1 |  | 0 | 1.1 | 0 | 0
Quarry & Concrete Product
1.12
| Description | Unit/LM | Unit | Rate | Rate/LM |  |  | QTY | Shared Trench Factor | Total Req. | Total | Contingency | TOTAL | Drainage Use | Fire/WAT Use | SPK Use
| 5-7mm Stone | 0.203 | Ton | 62 | 12.586 |  |  | 78.699 | 0.1 | 70.8291 | 4391.4064 | 526.9688 | 4918.3752 | 0
| 5-7mm Stone | 0.14 | m3 | 62 | 16.926
| 10-12mm Stone | 0.45 | Ton | 62 | 27.9 |  |  | 0 |  |  | 0 |  | 0
| 80-110mm Stone | 0 | Ton | 25 | 0 |  |  | 0 |  |  | 0 |  | 0
| Medium River / Bed Sand | 0.225 | Ton | 62 | 13.95 |  |  | 87.228 | 0.1 | 78.5052 | 4867.3224 | 584.0787 | 5451.4011 |  | 0 | 0
| Medium River / Bed Sand | 0.14 | m3 | 62 | 13.02
| CBR15 Road Base | 0.36 | Ton | 27 | 9.72 |  |  | 0 |  |  | 0 |  | 0
| CBR45 | 0.36 | Ton | 30 | 10.8 |  |  | 0 |  |  | 0 |  | 0
| LEANMIX | 0.3 | m3 | 0 | 0 |  |  | 0 |  |  | 0 |  | 0
|  |  |  | TCS | Q2
| Description |  | Unit | Rate | Rate
| 5-7mm Stone |  | T | 62 | 31
| 10-12mm Stone |  | T | 62 | 39
| 80-110mm Stone |  | T | 25 | 29
| Medium River / Bed Sand |  | T | 62 | 26
| CBR15 Road Base |  | T | 48 | 27
| CBR45 |  | T | 50 | 30
| LEANMIX_20mm-12:1 |  | M3 | 168 | 0
| Concrete_25/20/80 |  | M3 | 153 | 0

## Public Amenities (PAM)
Project:
Tricore -
Stage 1 Version 1
Item
1 | Complete -
Labour
[6 empty] | Denis qty | Qty / rate source note
| DAY | [7 empty] | april 2026 direct impact Increase % (not contigency)
| TRADESMAN_LEADING HAND | Day |  | 1329.6343 | 0
| TRADESMAN_PLUMBER_OPERATOR | Day |  | 1016.4579 | 0 |  |  |  |  | PE Pipe & Fitting | 38% | 1.38
| T/A & Apprentice | Day |  | 829.5103 | 0 |  |  |  |  | PVC Pipe & Fittings | 38% | 1.38
| Crew #1 - InGround Drainage | Day | 4 | 2862.4261 | 11449.7044 |  | Phase 7 crew-days (1B): T1-09 PAM UG drainage 4 |  |  | Subby Rates | 15% | 1.15
| Crew #2 - InGround Water/Fire | Day | 4 | 2862.4261 | 11449.7044 |  | Phase 7 crew-days (1B): T2-09 1B site branch take-offs 4 (1B scope carried on PAM sheet as 1B roll-up collector - interface L9) |  |  | Delivey Rate | 20% | 1.2
| Crew #3 - Above Ground Drainage | Day | 2 | 2862.4261 | 5724.8522 |  | Phase 7 crew-days (1B): T3-03 PAM vent + AG waste 2
| Crew #4 - Above Ground WATER/FIRE | Day | 5 | 2862.4261 | 14312.1305 |  | Phase 7 crew-days (1B): T4-05 4 + T4-06 1
| Crew #5 - Above Ground FitOff / Misc | Day | 5 | 2862.4261 | 14312.1305 |  | Phase 7 crew-days (1B): T5-03 4 + T5-04b 1 (bubbler install)
| Crew #6 - DEMO | Day |  | 1845.9682 | 0
HOUR
| TRADESMAN_LEADING HAND | HR | 168.5 | 132.9634 | 22404.3377 |  | Phase 7 LH supervision - 1B activities 168.5 hr
| TRADESMAN_PLUMBER_OPERATOR | HR | 0 | 101.6458 | 0
| T/A & Apprentice | HR | 0 | 82.951 | 0
| Crew #1 - InGround Drainage | HR | 0 | 286.2426 | 0
| Crew #2 - InGround Water/Fire | HR | 0 | 286.2426 | 0
Demolition & Reinstatement
DEMO
| Asphalt Cutting | m |  | 15.525 | 0
| Concrete Cutting | m |  | 18.4 | 0
| Con Cut Establishemnt Fee | ea |  | 92 | 0
REINSTATE - CONCRETE
| Road/Drveway Reinstate; 1mW x 150 Thck, N25/20/80, Incl Reinforcement | m |  | 145 | 0
| Kerb & Channel - 1m Wide | ea |  | 155 | 0
| Footpath - 1.5mW, N25/20/80, Incl Reinforcement | lm |  | 180 | 0
| Footpath - 1.5mW, EXPOSED AGG, N25/20/80, Incl Reinforcement | lm |  | 185 | 0
REINSTATE - ASPHALT
| 50mm Thck - Trench Reinstatement Through Road/Driveway | m2 |  | 97 | 0
| 50mm Thck - 1.5-2m Wide Footpath reinstatements | m2 |  | 97 | 0
| Establishment Fee (1 per stage) | Ea |  | 5500 | 0
Equipment & Hire - INCL WET PLANT HIRE
PLANT HIRE - WET
| 1.8T Excavator | Hr |  | 100 | 0
| 3-5 ton Excavator | Hr |  | 115 | 0
| 3-5T Combo | Hr |  | 154 | 0
| Hammer attachment 3.5-4T | Hr |  | 21 | 0
| Ripper 3.5-4T | Hr |  | 10 | 0
| 5t Excavator | Hr |  | 150 | 0
| Hammer attachment 5T | Hr |  | 50 | 0
| Skid steer | Hr |  | 140 | 0
| 8T Excavator | Hr |  | 128 | 0
| Hammer attachment 8T | Hr |  | 26 | 0
| Ripper 8T | Hr |  | 10 | 0
| 13-15T Excavator | Hr |  | 153 | 0
| Hammer attachment 14T | Hr |  | 36 | 0
| Ripper 14T | Hr |  | 10 | 0
| 3000L Hydro Excavation Truck | Hr |  | 190 | 0
| 4500L Hydro Excavation Truck | Hr |  | 220 | 0
| 6300L Hydro Excavation Truck | Hr |  | 250 | 0
| Water Truck allow for water at cost | Hr |  | 110 | 0
| 12t Body Truck Tipper | Hr |  | 110 | 0
HIRE - DRY
| Skid Steer Loader_Tracked (CAT249+) | Day |  | 225.4333 | 0
| Skid Steer Loader_Wheeled (CAT226+) | Day |  | 163.9667 | 0
| Mini Loader, Stand-on Type | Day |  | 180 | 0
|  |  |  | 0 | 0
| 1.5-1.8 Ton_Excavator | Day | 8 | 137.1429 | 1097.1429 |  | Phase 7 plant (1B): T1-09 4 + T2-09 4
| 1.7-2Ton_Excavator | Day |  | 0 | 0
| 3-5Ton_Excavator | Day |  | 238.6667 | 0
| 8Ton_Excavator | Day |  | 261.1667 | 0
| 10-12Ton_Excavator | Day |  | 0 | 0
| 13-16Ton_Excavator | Day |  | 317.2 | 0
| 20-24Ton_Excavator | Day |  | 314.2857 | 0
|  |  |  | 0 | 0
| Ripper_1.7-2T | Day |  | 0 | 0
| Ripper_1.5-4T | Day |  | 32.74 | 0
| Ripper_3-5T | Day |  | 0 | 0
| Ripper_8T | Day |  | 40.38 | 0
| Breaker_1.7-2T | Day |  | 123.33 | 0
| Breaker_3-5T | Day |  | 165.89 | 0
| Breaker_8T | Day |  | 165.89 | 0
| Breaker_10-12T | Day |  | 0 | 0
| Breaker_13-15T | Day |  | 203 | 0
| Auger Drive_10-12T |  |  | 0 | 0
| 300Dia Auger Drill |  |  | 0 | 0
|  |  |  | 0 | 0
| 1.25T_Tipper Truck | Day |  | 205 | 0
| 2-4T_Tipper Truck | Day |  | 166.98 | 0
| <6T_Tipper Truck | Day |  | 171.4286 | 0
|  |  |  | 0 | 0
| <10T_Articulated Site Tipper | Day |  | 0 | 0
| Upright Rammer_Wacker | Day | 4 | 34.2857 | 137.1429 |  | Phase 7 plant (1B): T1-09 4
| Trench Roller_Dbl Drum_Remote | Day |  | 165 | 0
| <26Ft_Scissor Lift - Diesel | Day |  | 0 | 0
| <26Ft_Scissor Lift - Elec | Day |  | 0 | 0
| <34Ft_Boom Lift - Diesel | Day |  | 0 | 0
| <34Ft_Boom Lift - Elec | Day |  | 0 | 0
|  |  |  | 0 | 0
| Porta Loo_No Tank | Day |  | 5.46 | 0
| 6*3m Demantable Lunchroom - COMPLETE | Day |  | 23 | 0
| 6*3m Demantable Office - COMPLETE | Day |  | 23 | 0
| 20Ft Shipping Container | Day |  | 0 | 0
| Quick Cut Demo Saw | Day |  | 0 | 0
| Sngl Ph_6KVA Genset | Day |  | 0 | 0
| Diesel Air Compressor_Trailer | Day |  | 0 | 0
| Air Breaker - Heavy | Day |  | 0 | 0
| Air Hose <10m | Day |  | 0 | 0
| Elec Breaker/Jachammer | Day |  | 0 | 0
| Flexdrive Motor Unit | Day |  | 0 | 0
| Flexdrive_Pump Shaft | Day |  | 0 | 0
| Temporary Power Board | Day |  | 0 | 0
|  |  |  | 0 | 0
| Dual CabUte | Day |  | 0 | 0
| 3m3 Skip Bbin | per serive |  | 230 | 0
| plus disposal | Tonne |  | 309 | 0
| site fee | Week |  | 35 | 0
| ~4m3_Skip Bin | per change over |  | 229.9 | 0
| ~6m3_Skip Bin | per change over |  | 239.8 | 0
| Plus disposal | Tonne |  | 309 | 0
| Site fee | Week |  | 35 | 0
| Vacuum Excavator - Vermeer VT250D | Day |  | 295.77 | 0
| Vac Trailer – Dry Hire | Day |  | 355 | 0
|  |  |  | 0 | 0
| TRANSPORT_Ex BRIS - Return | Day |  | 0 | 0
| TRANSPORT_Ex ROK - Return | Hour |  | 180 | 0
| 0-4T Per Hour Delivery Rate | Hour |  | 125 | 0
| 5 - 9t Transport Hourly Rate | Hour |  | 160 | 0
| 10 - 19t Low Loader Hourly rate - Minimum 2 Hour Charge | Hour |  | 200 | 0
| FUEL - Average_Candle | Week |  | 1850 | 0
Subbies & Misc
| Surveyor | ea |  | 180 | 0
| Services Locator | ea |  | 130 | 0
| Compaction Testing - TEST | ea | 3 | 115 | 345 |  | DERIVED 27 Jul 2026 on the NBC basis (Director decision: compaction testing included). NBC carries 15 tests against its own adopted trench length 387.68 m ('ClubHouse (NBC )'!C955) = 1 test per 25.8 m. That frequency is corroborated by VOL 38 spec cl 3.62 (compaction schedule), which mandates 1 test per 25 m in vehicular locations / 1 per 50 m elsewhere, 2 per layer at pits. Quantity is a live formula = this sheet's own trench metres x NBC tests / NBC trench metres, rounded up. Rate unchanged (Misc Subbie Rates_Master D72, $115/ea). PAM adopted trench length 71.36 m (C876) -> 71.36 x 15/387.68 = 2.76 -> 3 tests.
| Compaction Testing - Site Establishment | ea | 1 | 90 | 90 |  | DERIVED SEPARATELY 27 Jul 2026 - establishment is a per-VISIT mobilisation charge, it does NOT scale with metres. Basis = NBC's own batching ratio: 15 tests over 4 establishments = 3.75 tests presented per lab visit. Quantity = this sheet's test count / 3.75, rounded up. Cross-check: the same result is obtained from NBC's visit density (387.68 m / 4 visits = 1 visit per 96.9 m of trench). Consistent with the programme's mobilisation logic (PROGRAMME_LABOUR_PLANT TPS_Activities T1-12: separate mobilisations assumed for site mains / rough-in / fit-off). Rate unchanged (Misc Subbie Rates_Master D73, $90/ea). PAM 3 tests / 3.75 = 0.80 -> 1 establishment visit.
|  | ea |  |  | 0
|  | ea |  |  | 0
| FIRE TESTING / CERT | ea |  |  | 0
| FULL Hydro Test - Per Test (6.5Hr 1 x fitter, 1 x apprentice, 1 day Test gear) | ea |  | 1945 | 0
| Provision of Form 72 | ea |  | 350 | 0
| Consumables & small tools - PAM/1B crews (allowance) | item | 1 | 800 | 800 |  | Phase 7 consumables flag
Material - Quarry, Misc
| Bedding / Fill Sand | m3 | 13.487 | 39.75 | 536.1098 |  | Bedding import = helper I892 (auto)
| CBR 45/2.5 Roadbase | m3 |  | 41.9 | 0
| Turf Underlay/Topsoil | m3 |  | 45.25 | 0
| Standard Garden Woodchip | m3 |  | 87 | 0
| Turf - Standard Couch or Similar | Slab (.5m2) |  | 6.48 | 0
| Spoil haulage & dump (take-off helper M892 @ $15/m3) | item | 1 | 202.3056 | 202.3056 |  | Auto from helper
| Cement Stabalized Sand (3-5%) | m3 |  | 169 | 0
| Exposed Agg Concrete - Standard/Cheapest Exposed Agg Stone | m3 |  | 252 | 0
| N25 20mm 80 Slump Concrete | m3 |  | 263 | 0
| Valve Margin strips; Concrete slab, 1 directions sign, 3 x valve No sign. | ea |  | 380 | 0
FIRE SERVICES - INGROUND
| 200 HDPE PN16 SDR11 - REDLINE | m |  | 46.8107 | 0
| 180 HDPE PN16 SDR11 - REDLINE | m |  | 35.144 | 0
| 125 HDPE PN16 SDR11 - REDLINE | m |  | 16.9936 | 0
| 32 HDPE PN16 SDR11 - BLUELINE | m |  | 1.6779 | 0
0
| 200 EF Coupler | ea |  | 60.8028 | 0
| 180 EF Coupler | ea |  | 35.4936 | 0
| 125 EF Coupler | ea |  | 19.4718 | 0
| 200 EF 45DFeg Bend | ea |  | 150.6408 | 0
| 180 EF 45DFeg Bend | ea |  | 135.1986 | 0
| 125 EF 45DFeg Bend | ea |  | 61.6722 | 0
| 200 EF 90DFeg Bend | ea |  | 150.6408 | 0
| 180 EF 90DFeg Bend | ea |  | 134.9778 | 0
| 125 EF 90DFeg Bend | ea |  | 61.617 | 0
| 200 EF TEE | ea |  | 151.455 | 0
| 180 EF TEE | ea |  | 157.7064 | 0
| 125 EF TEE | ea |  | 67.965 | 0
| 200*180 EF TEE | ea |  | 289.0686 | 0
| 200*125 EF TEE | ea |  | 301.4196 | 0
| 180*125 EF TEE | ea |  | 168.5394 | 0
| 200*180 EF Reducer | ea |  | 173.3556 | 0
| 180*125 EF Reducer | ea |  | 82.938 | 0
| 200PE*8"(200m) - MaxiStub W/Backing Ring | ea |  | 472.443 | 0
| 180PE*6"(150mm) - MaxiStub W/Backing Ring | ea |  | 179.0826 | 0
| 125PE*4" (100mm) - MaxiStub W/Backing Ring | ea |  | 127.8846 | 0
| 180mm PE x 150mm GALV ADAPTER - PLASSON Brand | ea |  | 432.2022 | 0
| 125mm PE x 100mm GALV ADAPTER - PLASSON Brand | ea |  | 281.6718 | 0
|  | 0 |  | 0 | 0
| 180mm PE x 150mm GALV ADAPTER | ea |  | 435.6798 | 0
| 125mm PE x 100mm GALV ADAPTER | ea |  | 277.9734 | 0
| 200 Long SPIG 45DFeg Bend | ea |  | 94.5852 | 0
| 180 Long SPIG 45DFeg Bend | ea |  | 88.9548 | 0
| 125 Long SPIG 45DFeg Bend | ea |  | 53.4888 | 0
| 200 Long SPIG 90DFeg Bend | ea |  | 118.9146 | 0
| 180 Long SPIG 90DFeg Bend | ea |  | 93.9918 | 0
| 125 Long SPIG 90DFeg Bend | ea |  | 43.677 | 0
| 200 Long SPIG TEE | ea |  | 176.1432 | 0
| 180 Long SPIG TEE | ea |  | 157.6236 | 0
| 125 Long SPIG TEE | ea |  | 52.7988 | 0
| 200*180 Long SPIG TEE | ea |  | 253.2024 | 0
| 200*125 Long SPIG TEE | ea |  | 265.5534 | 0
| 180*125 Long SPIG TEE | ea |  | 256.2798 | 0
| 200*180 Long SPIG Reducer | ea |  | 77.0592 | 0
| 180*125 Long SPIG Reducer | ea |  | 54.9654 | 0
|  | 0 |  | 0 | 0
| 200 FL DICL Sluice Valve | ea |  | 679.41 | 0
| 150 FL DICL Sluice Valve | ea |  | 323.53 | 0
| 100 FL DICL Sluice Valve | ea |  | 202.94 | 0
| Valve Spindle Riser - 600Long | ea |  | 136.94 | 0
| Valve Box - Cast Iron Trafficable - Rectangle Type "V" | ea |  | 123.53 | 0
| Valve Box - Non-Trafficable - Plastic Surround with CI Drop In "V" | ea |  | 98.82 | 0
|  | 0 |  | 0 | 0
| 200*150mm DICL FL Reducer | ea |  | 291.18 | 0
| 200*100mm DICL FL Reducer | ea |  | 330 | 0
| 150*100mm DICL FL Reducer | ea |  | 156 | 0
| 150mm DICL FL * SP Adapter | ea |  | 106.24 | 0
| 100mm DICL FL * SP Adapter | ea |  | 70.59 | 0
| 200mm DICL FL 90Deg Bend | ea |  | 516.35 | 0
| 150mm DICL FL 90Deg Bend | ea |  | 198.88 | 0
| 100mm DICL FL 90Deg Bend | ea |  | 108.71 | 0
| 200mm DICL FL TEE | ea |  | 672.65 | 0
| 150mm DICL FL TEE | ea |  | 228.24 | 0
| 100mm DICL FL TEE | ea |  | 128.24 | 0
| 200*150*200 DICL FL TEE | ea |  | 536.76 | 0
| 200*100*200 DICL FL TEE | ea |  | 576.47 | 0
| 150-100-150 DICL FL TEE | ea |  | 198.82 | 0
| 200mm DICL FL Pipe @ 1000 | ea |  | 898.82 | 0
| 200mm DICL FL Pipe @ 600 | ea |  | 640 | 0
| 200mm DICL FL Pipe @ 300 | ea |  | 355.29 | 0
| 150mm DICL FL Pipe @ 1000 | ea |  | 534.41 | 0
| 150mm DICL FL Pipe @ 600 | ea |  | 280 | 0
| 150mm DICL FL Pipe @ 450 | ea |  | 236.47 | 0
| 150mm DICL FL Pipe @ 300 | ea |  | 178.8 | 0
| 100mm DICL FL Pipe @ 1000 | ea |  | 362.35 | 0
| 100mm DICL FL Pipe @ 600 | ea |  | 144.71 | 0
| 100mm DICL FL Pipe @ 450 | ea |  | 135.88 | 0
| 100mm DICL FL Pipe @ 300 | ea |  | 76.47 | 0
| 150mm DICL FL Deadplate | ea |  | 67.65 | 0
| 100mm DICL FL Deadplate | ea |  | 43.53 | 0
|  | 0 |  | 0 | 0
| 200mm PE*DI Gasket Kit Complete | ea |  | 67.06 | 0
| 200mm DI*DI Gasket Kit Complete | ea |  | 46.71 | 0
| 150mm PE*DI Gasket Kit Complete | ea |  | 60 | 0
| 150mm DI*DI Gasket Kit Complete | ea |  | 42.35 | 0
| 100mm PE*DI Gasket Kit Complete | ea |  | 24.71 | 0
| 100mm DI*DI Gasket Kit Complete | ea |  | 20 | 0
|  | 0 |  | 0 | 0
| 150mm SS Gibault Adapter Coupling | ea |  | 108.71 | 0
| 100mm SS Gibault Adapter Coupling | ea |  | 87.06 | 0
| 180mm PE GRIPPER Adapter Coupling | ea |  | 305.88 | 0
| 125mm PE GRIPPER Adapter Coupling | ea |  | 182.35 | 0
| 180mm PE GRIPPER * 150FL Adapter Coupling | ea |  | 229.41 | 0
| 125mm PE GRIPPER * 100FL Adapter Coupling | ea |  | 152.94 | 0
| 180mm PE GRIPPER Sluice Valve | ea |  | 690 | 0
| 125mm PE GRIPPER Sluice Valve | ea |  | 408.47 | 0
|  | 0 |  | 0 | 0
| Detectable Tape - Fire x 250m | ea |  | 90 | 0
| Alcohol Weld Wipes | ea |  | 13.5 | 0
| Denzo Tape 100mm roll | ea |  | 27.14 | 0
| Black over-wrap tape - roll | ea |  | 27.14 | 0
0
| FIRE SERVICES - ABOVE GROUND |  |  |  | 0
| Description | Unit
| 150mm MED DUTY Galv Pipe | m |  | 43.8462 | 0
| 100mm MED DUTY Galv Pipe w/RG Ends | m |  | 28.4615 | 0
| 100mm Class B Copper Pipe | m |  | 106.2417 | 0
| 25mm Class B Copper Pipe | m |  | 59.82 | 0
|  | 0 |  | 0 | 0
| 150mm Galv RG Coupling | ea |  | 12.83 | 0
| 100mm Galv RG Coupling | ea |  | 7.55 | 0
| 150mm Galv RG TEE | ea |  | 35.5 | 0
| 100mm Galv RG TEE | ea |  | 16.93 | 0
| 150mm Galv RG BEND 90Deg | ea |  | 22.85 | 0
| 100mm Galv RG BEND 90Deg | ea |  | 10.62 | 0
| 150mm Galv RG BEND 45Deg | ea |  | 23.5 | 0
| 100mm Galv RG BEND 45Deg | ea |  | 11.4 | 0
| 150mm Galv RG x 100mm FLANGE Adapt | ea |  | 30.75 | 0
| 100mm Galv RG x 100mm FLANGE Adapt | ea |  | 23.21 | 0
| 150mm RG Butterfly Valve Geared Wheel | ea |  | 217.8 | 0
| 100mm RG Butterfly Valve Geared Wheel | ea |  | 169.4 | 0
|  | 0 |  | 0 | 0
| 150mm H-Pattern Booster Assembly Complete | ea |  | 2350 | 0
| Booster Cabinet - Compl with doors and stickers | ea |  | 1155 | 0
|  | 0 |  | 0 | 0
| 100mm Dual Pillar Hydrant Complete_ Flanged Base 1500 High w/landing Valves | ea |  | 365 | 0
| 100mm Dual Pillar Hydrant Complete_ RG Base 1500 High w/landing Valves_OPTION | ea |  | 365 | 0
| 65mm RG Landing Valve | ea |  | 90 | 0
| Red caps and chain - suit 65mm QLD Landing valve | ea |  | 5 | 0
| 36m Fire Hose Reel w/25mm isolation valve | ea |  | 125 | 0
| 25mm Isolation Ball Valve (for fire hose reel) valve only, with hose nozzle latch | ea |  | 39 | 0
|  | 0 |  | 0 | 0
| 150mm FL Testable Double Check Valve - Compl. w/Valves | ea |  | 3100.7 | 0
| 150mm FL RPZD Valve - Compl. w/Valves | ea |  | 4237.09 | 0
|  | 0 |  | 0 | 0
| 100mm FL Levered Butterfly Vlave | ea |  | 114.44 | 0
| 100mm Copper Crimp - TEE | ea |  | 219.36 | 0
| 100mm Copper Crimp - 90Deg Bend | ea |  | 135.09 | 0
| 100mm Copper Crimp - 45Deg Bend | ea |  | 125.77 | 0
| 100mm Copper Crimp - Straight Socket | ea |  | 83.25 | 0
| 100mm Copper Crimp - 100mm FL Adapter | ea |  | 52.25 | 0
| 80mm Copper Crimp - TEE | ea |  | 175.66 | 0
| 100mm*80mm Copper Crimp - REDUCER | ea |  | 164.08 | 0
|  | 0 |  | 0 | 0
| 32mm Fi Lockable Ball Valve | ea |  | 77.95 | 0
| 32mm Cu Crimp * 32mi Adapt | ea |  | 17.16 | 0
| 32mm Cu Crimp Coupling Straight | ea |  | 7.23 | 0
| 32mm Cu Crimp 90Deg Bend | ea |  | 14.31 | 0
| 32mm Cu Crimp 45Deg Bend | ea |  | 16.24 | 0
| 32mm*25mm Cu Crimp Reducer | ea |  | 14.36 | 0
| 25mm Fi Lockable Ball Valve | ea |  | 46.94 | 0
| 25mm Cu Crimp * 25mi Adapt | ea |  | 8.46 | 0
| 25mm Cu Crimp Coupling Straight | ea |  | 5.74 | 0
| 25mm Cu Crimp 90Deg Bend | ea |  | 7.7 | 0
| 25mm Cu Crimp 45Deg Bend | ea |  | 10.19 | 0
|  | 0 |  | 0 | 0
| 150mm Galv 2 Piece Weld-nut Bracket M12 | ea |  | 5.86 | 0
| 100mm Galv 2 Piece Weld-nut Bracket M12 | ea |  | 4.41 | 0
| 150 Galv 2 Piece Channel Clip | ea |  | 5.36 | 0
| 100 Galv 2 Piece Channel Clip | ea |  | 4.4 | 0
| 12mm Galv Threaded Rod | ea |  | 10.64 | 0
| Galv Braced Counter Lever Bracket - 450Long | ea |  | 20 | 0
| 003 Padlock | ea |  | 19.5 | 0
| 100mm DI*DI Gasket Kit Complete | ea |  | 20 | 0
FIRE SERVICES - Misc.
Description
| Decommisioning Material | ea |  | 1388 | 0
| Electrofusion PE Welder 25-250mmPE. Please detail Spec | ea |  | 0 | 0
| PE Butt Welder. Automatic. 125-250mmPE. Please detail Spec - HIRE | WEEK |  | 450 | 0
| Hand Roll Groover. 65-150mm. | ea |  | 0 | 0
| Delivery - To Rockhampton PIPE LENGTHS as quoted | ea |  | 2178.48 | 0
| Delivery - To Rockhampton Standard/Palletised items | ea |  | 2178.48 | 0
POTABLE WATER_MAINS & R'Ins
Description
| 125 HDPE PN16 SDR11 - BLUELINE | m |  | 34.5 | 0
| 75 HDPE PE100 PN 16 -Blueline | m |  | 12.31 | 0
| 63 HDPE PE100 PN 16 -Blueline | m |  | 9.66 | 0
| 63 HDPE PN12.5 SDR11 - BLUELINE | m |  | 4.63 | 0
| 50 HDPE PE100 PN 16 - BLUELINE | m |  | 5.4 | 0
| 40 HDPE PE100 PN16 Blue Line | m | 3.27 | 4.4 | 14.388 | 4 | ADOPTED qty per QUANTITY_RECONCILIATION TPS_PAM
| 40 HDPE PN12.5 SDR11 - BLUELINE | m |  | 2.3621 | 0
| 32 HDPE PE100 PN 16 -Blueline | m |  | 2.1 | 0
| 25 HDPE PE100 PN16 - BLUELINE | m |  | 1.22 | 0
| 25 HDPE PN12.5 SDR11 - BLUELINE | m |  | 2.43 | 0
| EF COUPLER 125MM (EA) | m |  | 22 | 0
| TEE EQUAL PE100 E/F 125MM | ea |  | 57.75 | 0
| TEE PE100 E/F 125*63MM | ea |  | 139 | 0
| EF REDUCER 125 X 90MM | ea |  | 104.15 | 0
| EF REDUCER 125 X 63MM | ea |  | 26.1 | 0
| EF REDUCER 75 X 63MM | ea |  | 37.5 | 0
| EF REDUCER 63 X 50MM | ea |  | 35.93 | 0
| EF REDUCER 50 X 40MM | ea |  | 35 | 0
| EF REDUCER 40 X 32MM | ea |  | 35 | 0
| EF REDUCER 40 X 25MM | ea |  | 35 | 0
| EF REDUCER 32 X 25MM | ea |  | 20 | 0
| ELBOW PE100 E/F 125MM X 45D | ea |  | 50 | 0
| ELBOW PE100 E/F 125MM X 90D | ea |  | 54 | 0
| HDPE 63MM X 90 D ELBOW | ea |  | 15.55 | 0
| HDPE 50MM X 90 D ELBOW | ea |  | 15 | 0
| HDPE 40MM X 90 D ELBOW | ea |  | 10.87 | 0
| Reducing Tee 125mm x 90mm | ea |  | 55 | 0
| Reducing Tee 125mm x 32mm | ea |  | 55 | 0
| Reducing Tee 75mm x 63mm | ea |  | 35 | 0
| Reducing Tee 75mm x 50mm | ea |  | 35 | 0
| Reducing Tee 75mm x 32mm | ea |  | 35 | 0
| Reducing Tee 63mm x 50mm | ea |  | 35 | 0
| Reducing Tee 63mm x 32mm | ea |  | 35 | 0
| Reducing Tee 50mm x 40mm | ea |  | 35 | 0
| Reducing Tee 40mm x 25mm | ea |  | 35 | 0
| Reducing Tee 32mm x 25mm | ea |  | 35 | 0
| EF Reducer 50mm x 25mm | ea |  | 26 | 0
| 50mm Tee | ea |  | 35 | 0
| 40mm Tee | ea |  | 10.87 | 0
| 32mm Tee | ea |  | 35 | 0
| HDPE 32mm X 90 D ELBOW | ea |  | 20 | 0
| HDPE 25mm X 90 D ELBOW | ea |  | 20 | 0
| HDPE 25mm X 45 D ELBOW | ea |  |  | 0
| 25mm Tee | ea |  | 35 | 0
| PE MAXI STUB FLANGE W/SS BK RING 125X 4" (EA) | ea |  | 102.5 | 0
| SLUICE VALVE PN16 T/D ACC FLNGD 100MM | ea |  | 235 | 0
| Valve Box - Cast Iron - Rectangle - Large - HD | ea |  | 100 | 0
| SADDLE TAPPING EF 125PE X 25PE | ea |  | 47.41 | 0
| SADDLE TAPPING EF 125PE X 32PE | ea |  | 41.69 | 0
| SADDLE TAPPING EF 125PE X 63PE | ea |  | 85.55 | 0
|  | ea |  |  | 0
| Detectable WATER Marker Tape - 250m | ea |  | 70 | 0
| WIPES WELDING PLASSON XL (120 PK) | ea |  | 19 | 0
| Paint Pen - WHITE | ea |  | 16 | 0
0
| 100 Cu Above Grnd | m |  | 46.5 | 0
| 50 Cu Above Grnd | m |  | 32 | 0
| 316SS press-fit tube 35mm (was 32 Cu) - WS2 conforming | m | 9.56 | 22.005 | 210.3678 | 10 | ADOPTED 9.56 m; RE-RATED 316SS press-fit 35mm - WS2 conforming base (>DN22); copper alternate in EBC_Alternates | 316SS press-fit BASE per WS2 (>DN22): pipe rate = Reece Q-459014431 316 tube rate set (project quote; no >35mm needed). PENDING RFQ PER GAP LIST (Gap #2). Copper alternate: EBC_Alternates.
| 316SS press: 32mm x25mm reducing tee | ea | 2 | 32.25 | 64.5 |  |  | 316SS press fitting benchmark = Cu press rate x1.5 (SS press fittings 1.4-1.6x Cu per supplier curves) - pending RFQ (Gap #2)
| 316SS press-fit tube 28mm (was 25 Cu) - WS2 conforming | m | 26.9 | 13.4383 | 361.4912 | 27 | ADOPTED 26.9 m; RE-RATED 316SS press-fit 28mm - WS2 conforming base (>DN22)
| 316SS press: B-PRESS WATER EQUAL TEE 32MM (EA) | ea | 1 | 22.5 | 22.5 |  |  | 316SS press fitting benchmark = Cu press rate x1.5 (SS press fittings 1.4-1.6x Cu per supplier curves) - pending RFQ (Gap #2)
| B-PRESS WATER ELBOW 90DEG X 25MM (EA) | ea |  | 7.17 | 0
| 316SS press: B-PRESS WATER EQUAL TEE 25MM (EA) | ea | 7 | 15.09 | 105.63 |  |  | 316SS press fitting benchmark = Cu press rate x1.5 (SS press fittings 1.4-1.6x Cu per supplier curves) - pending RFQ (Gap #2)
| 20 Cu Above Grnd | m | 0.96 | 9.785 | 9.3936 | 1 | ADOPTED qty per QUANTITY_RECONCILIATION TPS_PAM - 20 Cu 0.96 m (<=DN22 retained copper)
| B-PRESS WATER EQUAL TEE 20MM (EA) | ea |  | 5.61 | 0
| 50mm Cu 10mm Nut Clip | ea |  | 1.4 | 0
| 32mm Cu 10mm Nut Clip | ea |  | 1.38 | 0
| 25mm Cu 10mm Nut Clip | ea |  | 1.32 | 0
| 20mm Cu 10mm Nut Clip | ea |  | 1.24 | 0
| 10mm Zinc Threaded Rod | m |  | 5.1 | 0
| 316SS press: Kembla copper WATER ELBOW 90DEG X 32MM (EA) | EA | 1 | 21.465 | 21.465 |  |  | 316SS press fitting benchmark = Cu press rate x1.5 (SS press fittings 1.4-1.6x Cu per supplier curves) - pending RFQ (Gap #2)
| 316SS press: Kembla copper WATER ELBOW 90DEG X 25MM | ea | 15 | 10.755 | 161.325 |  |  | 316SS press fitting benchmark = Cu press rate x1.5 (SS press fittings 1.4-1.6x Cu per supplier curves) - pending RFQ (Gap #2)
| Kembla copper WATER ELBOW 90DEG X 20MM | ea | 2 | 3.76 | 7.52
0
| 316SS press: B-PRESS WATER REDUCING COUP 25X20MM (EA) | ea | 1 | 17.79 | 17.79 |  |  | 316SS press fitting benchmark = Cu press rate x1.5 (SS press fittings 1.4-1.6x Cu per supplier curves) - pending RFQ (Gap #2)
0
| 316SS press: 32mm Poly to 32mm Copper B Press Adapter | ea | 1 | 37.5 | 37.5 |  |  | 316SS press fitting benchmark = Cu press rate x1.5 (SS press fittings 1.4-1.6x Cu per supplier curves) - pending RFQ (Gap #2)
HIDDEN |  |  |  |  | 0
| 63mm E/F PE 90 Deg Elb |  |  |  | 0
| 63mm E/F PE 45 Deg Elb | ea |  | 13.5 | 0
| 63mm E/F PE TEE | ea |  | 13.5 | 0
| 63x40x63 E/F PE TEE | ea |  | 9.5 | 0
| 63x32x63 E/F PE TEE | ea |  | 18.5 | 0
| 63x25x63 E/F PE TEE | ea |  | 18.5 | 0
| 63mm E/F PE Coupling | ea |  | 6 | 0
| 63x40 E/F PE Reducer Coupling | ea |  | 5.5 | 0
| 63x32 E/F PE Reducer Coupling | ea |  | 17.5 | 0
| 63x25 E/F PE Reducer Coupling | ea |  | 16.5 | 0
| 63PEx50Fi E/F PE Adapter | ea |  | 2.5 | 0
| 63PEx50Mi E/F PE Adapter | ea |  | 43.5 | 0
| 63PEx50Fi E/F PE Tramsiton Union | ea |  | 43.5 | 0
| 63PEx50Mi E/F PE Transition Union | ea |  | 45.5 | 0
| 40mm E/F PE 90 Deg Elb | ea |  | 76 | 0
| 40mm E/F PE 45 Deg Elb | ea |  | 11.5 | 0
| 40mm E/F PE TEE | ea |  | 11.5 | 0
| 40x32x40 E/F PE TEE | ea |  | 12 | 0
| 40x25x40 E/F PE TEE | ea |  | 18.5 | 0
| 40mm E/F PE Coupling | ea |  | 19.5 | 0
| 40x32 E/F PE Reducer Coupling | ea |  | 4.5 | 0
| 40x25 E/F PE Reducer Coupling | ea |  | 10.5 | 0
| 40PEx32Fi E/F PE Adapter | ea |  | 14.5 | 0
| 40PEx32Mi E/F PE Adapter | ea |  | 28.5 | 0
| 40PEx32Fi E/F PE Tramsiton Union | ea |  | 29.5 | 0
| 40PEx32Mi E/F PE Transition Union | ea |  | 36 | 0
| 32mm E/F PE 90 Deg Elb | ea |  | 54 | 0
| 32mm E/F PE 45 Deg Elb | ea |  | 10.5 | 0
| 32mm E/F PE TEE | ea |  | 10 | 0
| 32x25x32 E/F PE TEE | ea |  | 5.5 | 0
| 32mm E/F PE Coupling | ea |  | 18 | 0
| 32x25 E/F PE Reducer Coupling | ea |  | 4.5 | 0
| 32PEx25Fi E/F PE Adapter | ea |  | 6.5 | 0
| 32PEx25Mi E/F PE Adapter | ea |  | 25.5 | 0
| 32mm E/F PE End Cap | ea |  | 22.5 | 0
| 32mm E/F PE End Plug | ea |  | 8.5 | 0
| 25mm E/F PE 90 Deg Elb | ea |  | 6.5 | 0
| 25mm E/F PE 45 Deg Elb | ea |  | 10.5 | 0
| 25mm E/F PE TEE | ea |  | 0 | 0
| 25mm E/F PE Coupling | ea |  | 4.5 | 0
| 25PEx25Fi E/F PE Adapter | ea |  | 4 | 0
| 25PEx25Mi E/F PE Adapter | ea |  | 17 | 0
| 25PEx20Fi E/F PE Adapter | ea |  | 17.5 | 0
| 25PEx20Mi E/F PE Adapter | ea |  | 4.5 | 0
| 25mm E/F PE End Cap | ea |  | 2 | 0
| 25mm E/F PE End Plug | ea |  | 8.5 | 0
HIDDEN |  | ea |  | 4 | 0
| 100mm CU Crimp 90 DEG FxF Elbow |  |  |  | 0
| 100mm CU Crimp 45 DEG FxF Elbow | ea |  | 137 | 0
| 100mm CU Crimp Tee | ea |  | 139.5 | 0
| 100x50x100 CU Crimp Tee | ea |  | 183 | 0
| 100x50 CU Crimp Reducer | ea |  | 184.5 | 0
| 100mm CU Crimp Repair Coupling | ea |  | 56 | 0
| 100mm CU Crimp Coupling | ea |  | 103 | 0
| 100Cu x 100Flange CU Crimp Coupling | ea |  | 95 | 0
| 50mm CU Crimp 90 DEG FxF Elbow | ea |  | 45.02 | 0
| 50mm CU Crimp 45 DEG FxF Elbow | ea |  | 33.5 | 0
| 50mm CU Crimp Tee | ea |  | 33 | 0
| 50x40x50 CU Crimp Tee | ea |  | 60.5 | 0
| 50x40x40 CU Crimp Tee | ea |  | 61 | 0
| 50x32x50 CU Crimp Tee | ea |  | 65 | 0
| 50x32x32 CU Crimp Tee | ea |  | 65 | 0
| 50x32x40 CU Crimp Tee | ea |  | 65 | 0
| 50x25x50 CU Crimp Tee | ea |  | 65 | 0
| 50x20x50 CU Crimp Tee | ea |  | 45 | 0
| 50x15x50 CU Crimp Tee | ea |  | 55 | 0
| 50x40 CU Crimp Reducer | ea |  | 55 | 0
| 50x32 CU Crimp Reducer | ea |  | 21.5 | 0
| 50x25 CU Crimp Reducer | ea |  | 25 | 0
| 50x20 CU Crimp Reducer | ea |  | 22 | 0
| 50x15 CU Crimp Reducer | ea |  | 22 | 0
| 50Cu x 50Mi CU Crimp Adapter | ea |  | 22 | 0
| 50Cu x 50Fi CU Crimp Adapter | ea |  | 78 | 0
| 50mm CU Crimp Repair Coupling | ea |  | 89 | 0
| 50mm CU Crimp Coupling | ea |  | 21 | 0
| 50Cu x 50Flange CU Crimp Coupling | ea |  | 21 | 0
| 50mm CU Crimp Cap | ea |  | 0 | 0
| 50Cu x W69/Barrell Barrell Union CU Crimp | ea |  | 0 | 0
| 40mm CU Crimp 90 DEG FxF Elbow | ea |  | 0 | 0
| 40mm CU Crimp 45 DEG FxF Elbow | ea |  | 0 | 0
| 40mm CU Crimp 90 DEG MxF Elbow | ea |  | 0 | 0
| 40mm CU Crimp 45 DEG MxF Elbow | ea |  | 0 | 0
| 40mm CU Crimp Tee | ea |  | 0 | 0
| 40x32x40 CU Crimp Tee | ea |  | 0 | 0
| 40x32x32 CU Crimp Tee | ea |  | 0 | 0
| 40x32x25 CU Crimp Tee | ea |  | 0 | 0
| 40x25x40 CU Crimp Tee | ea |  | 0 | 0
| 40x25x20 CU Crimp Tee | ea |  | 0 | 0
| 40x20x40 CU Crimp Tee | ea |  | 0 | 0
| 40x15x40 CU Crimp Tee | ea |  | 0 | 0
| 40x32 CU Crimp Reducer | ea |  | 0 | 0
| 40x25 CU Crimp Reducer | ea |  | 0 | 0
| 40x20 CU Crimp Reducer | ea |  | 0 | 0
| 40x15 CU Crimp Reducer | ea |  | 0 | 0
| 40Cu x 40Mi CU Crimp Adapter | ea |  | 0 | 0
| 40Cu x 40Fi CU Crimp Adapter | ea |  | 0 | 0
| 40mm CU Crimp Repair Coupling | ea |  | 0 | 0
| 40mm CU Crimp Coupling | ea |  | 0 | 0
| 40Cu x 40Flange CU Crimp Coupling | ea |  | 0 | 0
| 40mm CU Crimp Cap | ea |  | 0 | 0
| 40Cu x W69/Barrell Barrell Union CU Crimp | ea |  | 0 | 0
| 32mm CU Crimp 90 DEG FxF Elbow | ea |  | 0 | 0
| 32mm CU Crimp 45 DEG FxF Elbow | ea |  | 0 | 0
| 32mm CU Crimp 90 DEG MxF Elbow | ea |  | 0 | 0
| 32mm CU Crimp 45 DEG MxF Elbow | ea |  | 0 | 0
| 32mm CU Crimp Tee | ea |  | 0 | 0
| 32x25x32 CU Crimp Tee | ea |  | 18.54 | 0
| 32x25x20 CU Crimp Tee | ea |  | 0 | 0
| 32x20x32 CU Crimp Tee | ea |  | 0 | 0
| 32x20x20 CU Crimp Tee | ea |  | 18.35 | 0
| 32x20x15 CU Crimp Tee | ea |  | 0 | 0
| 32x15x32 CU Crimp Tee | ea |  | 0 | 0
| 32x15x25 CU Crimp Tee | ea |  | 0 | 0
| 32x15x20 CU Crimp Tee | ea |  | 0 | 0
| 32x15x15 CU Crimp Tee | ea |  | 0 | 0
| COUPLING RED CU KEMPRESS WATER 32MM X 25MM | ea |  | 0 | 0
| 32x20 CU Crimp Reducer | ea |  | 16.33 | 0
| 32x15 CU Crimp Reducer | ea |  | 0 | 0
| 32Cu x 32Mi CU Crimp Adapter | ea |  | 0 | 0
| 32Cu x 32Fi CU Crimp Adapter | ea |  | 0 | 0
| 32mm CU Crimp Repair Coupling | ea |  | 0 | 0
| 32mm CU Crimp Coupling | ea |  | 0 | 0
| 32mm CU Crimp Cap | ea |  | 0 | 0
| 32Cu x W69/Barrell Barrell Union CU Crimp | ea |  | 0 | 0
| 25mm CU Crimp 90 DEG FxF Elbow | ea |  | 0 | 0
| 25mm CU Crimp 45 DEG FxF Elbow | ea |  | 0 | 0
| 25mm CU Crimp 90 DEG MxF Elbow | ea |  | 0 | 0
| 25mm CU Crimp 45 DEG MxF Elbow | ea |  | 0 | 0
| 25mm CU Crimp Tee | ea |  | 0 | 0
| 25x20x25 CU Crimp Tee | ea |  | 0 | 0
| 25x20x20 CU Crimp Tee | ea |  | 0 | 0
| 25x20x15 CU Crimp Tee | ea |  | 0 | 0
| 25x15x25 CU Crimp Tee | ea |  | 0 | 0
| 25x15x20 CU Crimp Tee | ea |  | 0 | 0
| 25x15x15 CU Crimp Tee | ea |  | 0 | 0
| 25x20 CU Crimp Reducer | ea |  | 0 | 0
| 25x15 CU Crimp Reducer | ea |  | 0 | 0
| 25Cu x 25Mi CU Crimp Adapter | ea |  | 0 | 0
| 25Cu x 25Fi CU Crimp Adapter | ea |  | 0 | 0
| 25mm CU Crimp Repair Coupling | ea |  | 0 | 0
| 25mm CU Crimp Coupling | ea |  | 0 | 0
| 25mm CU Crimp Cap | ea |  | 0 | 0
| 25Cu x W69/Barrell Barrell Union CU Crimp | ea |  | 0 | 0
| 20mm CU Crimp 90 DEG FxF Elbow | ea |  | 0 | 0
| 20mm CU Crimp 45 DEG FxF Elbow | ea |  | 0 | 0
| 20mm CU Crimp 90 DEG MxF Elbow | ea |  | 0 | 0
| 20mm CU Crimp 45 DEG MxF Elbow | ea |  | 0 | 0
| 20mm CU Crimp Tee | ea |  | 0 | 0
| 20x15x20 CU Crimp Tee | ea |  | 5.61 | 0
| 20x15x15 CU Crimp Tee | ea |  | 0 | 0
| 20x15 CU Crimp Reducer | ea |  | 0 | 0
| 20Cu x 20Mi CU Crimp Adapter | ea |  | 0 | 0
| 20Cu x 20Fi CU Crimp Adapter | ea |  | 0 | 0
| 20mm CU Crimp Repair Coupling | ea |  | 0 | 0
| 20mm CU Crimp Coupling | ea |  | 0 | 0
| 20mm CU Crimp Cap | ea |  | 0 | 0
| 20Cu x W69/Barrell Barrell Union CU Crimp | ea |  | 0 | 0
| 15mm CU Crimp 90 DEG FxF Elbow | ea |  | 0 | 0
| 15mm CU Crimp 45 DEG FxF Elbow | ea |  | 0 | 0
| 15mm CU Crimp 90 DEG MxF Elbow | ea |  | 0 | 0
| 15mm CU Crimp 45 DEG MxF Elbow | ea |  | 0 | 0
| 15mm CU Crimp Tee | ea |  | 0 | 0
| 15Cu x 15Mi CU Crimp Adapter | ea |  | 0 | 0
| 15Cu x 15Fi CU Crimp Adapter | ea |  | 0 | 0
| 15Cu Fi BP, wall elbow | ea |  | 0 | 0
| 15Cu Mi BP, Wall elbow - 90 Long | ea |  | 0 | 0
| 15Cu Mi BP, Wall elbow - 120+ Long | ea |  | 0 | 0
| 15mm CU Crimp Repair Coupling | ea |  | 0 | 0
| 15mm CU Crimp Coupling | ea |  | 0 | 0
| 15mm CU Crimp Cap | ea |  | 0 | 0
| 15Cu x W69/Barrell Barrell Union CU Crimp | ea |  | 0 | 0
| 50mm Ball Valve Fi | ea |  | 0 | 0
| 40mm Ball Valve Fi | ea |  | 0 | 0
| 32mm Ball Valve Fi | ea |  | 0 | 0
| 25mm Ball Valve Fi | ea |  | 26.25 | 0
| 20mm Ball Valve Fi | ea |  | 0 | 0
| 15mm Ball Valve Fi | ea |  | 0 | 0
| 50mm Mi BRS Nipple | ea |  | 0 | 0
| 50mm Fi BRS Socket | ea |  | 0 | 0
| 50mm Mi BRS Union | ea |  | 0 | 0
| 50mm Fi BRS Union | ea |  | 0 | 0
| 50mm BRS Plug | ea |  | 0 | 0
| 50mm BRS Cap | ea |  | 0 | 0
| 40mm Mi BRS Nipple | ea |  | 0 | 0
| 40mm Fi BRS Socket | ea |  | 0 | 0
| 40mm Mi BRS Union | ea |  | 0 | 0
| 40mm Fi BRS Union | ea |  | 0 | 0
| 40mm BRS Plug | ea |  | 0 | 0
| 40mm BRS Cap | ea |  | 0 | 0
| 32mm Mi BRS Nipple | ea |  | 0 | 0
| 32mm Fi BRS Socket | ea |  | 0 | 0
| 32mm Mi BRS Union | ea |  | 0 | 0
| 32mm Fi BRS Union | ea |  | 0 | 0
| 32mm BRS Plug | ea |  | 0 | 0
| 32mm BRS Cap | ea |  | 0 | 0
| 25mm Mi BRS Nipple | ea |  | 0 | 0
| 25mm Fi BRS Socket | ea |  | 0 | 0
| 25mm Mi BRS Union | ea |  | 0 | 0
| 25mm Fi BRS Union | ea |  | 0 | 0
| 25mm BRS Plug | ea |  | 0 | 0
| 25mm BRS Cap | ea |  | 0 | 0
|  | ea |  | 0 | 0
| 20mm pex Pipe - Black | m | 18.86 | 2.17 | 40.9262 | 19 | ADOPTED qty per QUANTITY_RECONCILIATION TPS_PAM
| 20mm pex Pipe - Red | m | 5.89 | 2.3 | 13.547 | 6 | ADOPTED qty per QUANTITY_RECONCILIATION TPS_PAM
| 15mm Pex pipe - Black | m |  | 0 | 0
| 15mm Pex pipe - Red | ea |  | 0 | 0
| 20 pex Elbow | ea | 16 | 5.15 | 82.4
| 20 Pex TEE | ea | 7 | 7.49 | 52.43
| 20x15 Pex TEE | ea |  | 0 | 0
| 20 PEX Mi Adapter | ea |  | 0 | 0
| 20 PEX Fi Adapter | ea |  | 0 | 0
| 20x15 Pex Reducer | ea |  | 0 | 0
| PEX - 32 Cu Crimp Adapter | ea | 2 | 20 | 40
| PEX - 25 Cu Crimp Adapter | ea | 1 | 14 | 14
| 20 PEXxCU Crimp conversion coupling | ea | 1 | 10.05 | 10.05
| 20 PEX Straight coupling | ea |  | 0 | 0
| 15 Pex Elbow | ea |  | 0 | 0
| 15 Pex TEE | ea |  | 0 | 0
| 15 PEXMi Adapter | ea |  | 0 | 0
| 15 PEX Fi Adapter | ea |  | 0 | 0
| 15 PEX Fi BP, wall elbow | ea |  | 0 | 0
| 15 PEX Mi BP, Wall elbow - 90 Long | ea |  | 0 | 0
| 15 PEX Mi BP, Wall elbow - 120+ Long | ea |  | 0 | 0
| 15 PEXxCU Crimp conversion coupling | ea |  | 0 | 0
| 15 PEX Straight coupling | ea |  | 0 | 0
|  | ea |  | 0 | 0
| Hose Taps Complete | ea | 1 | 56 | 56
| 100 FL DICL SLUICE VALVE | ea |  | 202.94 | 0
| 125PE*4" (100mm) - MaxiStub W/Stainless Steel Backing Ring | ea |  | 92.67 | 0
| 100mm PE*DI Gasket Kit Complete Parts & Labour | ea |  | 24.71 | 0
| 100mm DI*DI Gasket Kit Complete | ea |  | 20 | 0
| Valve Spindle Riser - 600Long | ea |  | 136.94 | 0
| 100mm Dual Pillar Hydrant Complete_ RG Base 1500 High w/landing Valves_OPTION | ea |  | 365 | 0
| 125mm PE x 100mm GALV ADAPTER - Acutech Brand | ea |  | 201.43 | 0
| Red caps and chain - suit 65mm QLD Landing valve | ea |  | 5 | 0
| RPZD 32mm | ea |  | 853 | 0
| RPZD 20mm | ea |  | 503 | 0
| RPZD 100mm | ea |  | 1809.63 | 0
| Office - Water & Rough IN | ea |  | 1650 | 0
| Ofice - NOGINS & Fixings | ea |  | 160 | 0
| Safety shr fittings | ea |  | 750 | 0
| In Grnd Fittings misc | ea |  | 450 | 0
| Abv Grnd Fittings misc | ea |  | 1250 | 0
| HWU quickie kit | ea |  | 190 | 0
| TMV | ea |  | 412.59 | 0
| 20mm Isolavtive valve | ea |  | 50 | 0
| 450 SQ PIT | ea |  | 30 | 0
| Dock Office Water Mat | ea |  | 1850 | 0
| 25mm RPZD | ea |  | 1800 | 0
| misc. | ea |  | 3800 | 0
| 150mm isolation valve in valve pit (connect to authority watermain ) | ea |  | 371.37 | 0
| 25mm DCW Isolation vlave in valve pit with path box cover | ea |  | 469.04 | 0
| 32 domestic watre meter assembly | ea | 1 | 949 | 949
| 25mm water meter in tamper steel cage with isolative valves in both side | ea |  | 659.8 | 0
| TMV in Box | ea | 1 | 587.96 | 587.96
| 100 mm Water meter | ea |  | 641.58 | 0
| 63 Valve in Pit | ea |  | 80 | 0
| 32 valve in pit | ea |  | 50 | 0
| 50mm control valve | ea |  | 31.71 | 0
| TLV under basin | ea |  | 146.09 | 0
| AUTOMATIC TRAP PRIMER | ea |  | 99.49 | 0
SEWER DRAINAGE -
Description
| PIPE DWV PVC S/WELD 150MM - In Grnd | m |  | 14.49 | 0
| PIPE DWV SN8 PVC S/WELD 100MM | m | 61.16 | 9.5496 | 584.0535 | 62 | ADOPTED qty per QUANTITY_RECONCILIATION TPS_PAM
| 150MM * 45D PVC JUNCTION | ea |  | 9.66 | 0
| 100MM * 45D PVC JUNCTION | ea | 22 | 4.7886 | 105.3492
| 150MM X 100MM 45D PVC JUNCTION | ea |  | 13.8 | 0
| 100*50 PVC DWV JUNCTION | ea |  | 6.5274 | 0
| 100MM * 65 PVC PVC JUNCTION | ea |  | 8.5974 | 0
| 150MM X 45 Deg Bend | ea |  | 6.9 | 0
| 150MM X 90 Deg Bend | ea |  | 6.9 | 0
| 100MM X 90Deg Bend | ea | 21 | 2.5668 | 53.9028
| 100MM X 45Deg Bend | ea | 21 | 2.3308 | 48.9472
| DWV PIPE REDUCER 150X100mm | ea |  | 5.52 | 0
| DWV PIPE REDUCER 100 X 65mm | ea | 1 | 5 | 5
| DWV PIPE REDUCER 100 X 50mm | ea | 1 | 2.6772 | 2.6772
| PIPE DWV PVC S/WELD 100MM - In Grnd | m |  | 6.9 | 0
| PIPE DWV PVC S/WELD 65MM - In Grnd | m |  | 5.52 | 0
| 63 HDPE PN12.5 SDR11 - BLACK or CREAM - In Grnd | m |  | 8.7354 | 0
| PIPE DWV PVC S/WELD 50mm | m | 6.93 | 3.726 | 25.8212 | 7 | ADOPTED qty per QUANTITY_RECONCILIATION TPS_PAM
| PIPE DWV PVC S/WELD 40mm | m |  | 2.898 | 0
| DWV BEND 65X 90 DEG | ea |  | 2.3322 | 0
| DWV BEND 40 X 85 DEG | ea |  | 4.14 | 0
| DWV BEND 50 X 45 DEG | ea | 2 | 0.9384 | 1.8768
| DWV BEND 50 X85 DEG | ea | 4 | 11.7162 | 46.8648
| 50mm Condensate INSULATION | m |  | 14 | 0
| 100mm Condensate INSULATION | m |  | 6 | 0
0
| 150mm - Gas Tight H/D Cast Iron Clearout (Peepeye) | ea | 7 | 40 | 280 | 6 | ADOPTED qty per QUANTITY_RECONCILIATION TPS_PAM - 100mm CO adopted 7 (7 'CO' annotations vs 6 counted; H002 n.15 adopt higher)
| 150mm Clear Out Cover - L/D - Brass | ea | 7 | 30 | 210 | 6 | ADOPTED qty per QUANTITY_RECONCILIATION TPS_PAM - CO covers follow CO count 7
| 100mm - Gas Tight H/D Cast Iron Clearout (Peepeye) | ea |  | 33 | 0
| 100mm Clear Out Cover - L/D - Brass | ea |  | 23.26 | 0
| 100 mm Inspection Opening | ea |  | 50 | 0
| 100mm Trapped point - 100mm Gully Trap | ea |  | 7.65 | 0
| FWG - 100mm Gully Trap | ea |  | 7.65 | 0
| FWG - 100mm 4-way Riser | ea | 2 | 13.59 | 27.18
| FWG - Grate - Tile Insert 100*100 Chrome Plated | ea |  | 0 | 0
| In-Wall TD & View Panel - SS | ea | 2 | 75 | 150
0
| 100mm PVC 10mm nut hanging clip | ea |  | 2 | 0
| 50mm PVC 10mm nut hanging clip | ea |  | 1.5 | 0
| 10mm Zinc Threaded Rod | m |  | 0 | 0
0
| Glue - Blue - 4Ltr | ea |  | 26.4 | 0
| Primer - Red - 4Ltr | ea |  | 23 | 0
| Detectable SEWER Marker Tape - 250m | ea |  | 75 | 0
| 100mm AbleFlex Roll | ea |  | 22 | 0
| Concrete Mix bag | ea |  | 10 | 0
0
| External Sewer Mains fitting | ea |  | 520 | 0
| Vents Complete | ea |  | 230 | 0
| Office Drainage mat | ea |  | 2800 | 0
| Dock Office Drainage Mat | ea |  | 950 | 0
| misc. | ea |  | 1250 | 0
| Overflow Gully | ea | 1 | 200 | 200
| COS | ea |  | 120 | 0
| Articulation/expansion joint hardware - H1 'P' adder (PAM) | item | 1 | 750 | 750 |  | NewItems #12 allowance ~7 joints @ ~$100 - pending Storm Plastics RFQ; as NBC basis
| SIVEL EXPANSION JOINT | ea | 1 | 100 | 100
| FWG | ea | 4 | 250 | 1000 | 3 | ADOPTED qty per QUANTITY_RECONCILIATION TPS_PAM - FWG 4 drawn on H-PAM-100 (adopt higher)
| Fire Collars & Misc | ea |  | 300 | 0
| plaster /slip trap | ea |  | 1200 | 0
Vent
| DWV PVC PIPE 65MM SN 6 | m | 1.93 | 5.25 | 10.1325 | 2 | ADOPTED qty per QUANTITY_RECONCILIATION TPS_PAM - 65 vent horizontal 1.93 m (vertical riser added below)
| DWV BEND 65X90 DEG | ea | 1 | 3 | 3
| DWV BEND 65 X 45 DEG | ea | 1 | 2.5 | 2.5
| Vertical vent riser O65 VP to above roof - height + flashing allowance | EA | 1 | 85 | 85 |  | NewItems #8 allowance - single riser, height from section at Phase 6
STORMWATER DRAINAGE
Description
| Roof-DP in-ground connection stub (allow 2 m O100 DWV + bend + coupling) | EA | 4 | 40 | 160 |  | ADOPTED 4 EA (NewItems #6); PAM sheets show NO 'connect to civil' note - connection point undefined, RFI CL C8; civil beyond is TCS
| PIPE 600MM - RIBBED | m |  | 165.6 | 0
| PIPE 450MM - RIBBED | m |  | 89.7 | 0
| PIPE 375MM - RIBBED BLACK MAX | m |  | 66.24 | 0
| PIPE 300MM - RIBBED BLACK MAX | m |  | 0 | 0
| PIPE DWV SN8 PVC S/WELD 375MM | m |  | 85.1046 | 0
| PIPE DWV SN8 PVC S/WELD 300MM | m |  | 84.18 | 0
| PIPE DWV SN4 PVC S/WELD 300MM | m |  | 68.77 | 0
| PIPE SW H/D PVC S/WELD 300MM | m |  | 55.2 | 0
| PIPE DWV SN8 PVC S/WELD 225MM | m |  | 55.2 | 0
| PIPE DWV SN4 PVC S/WELD 225MM | m |  | 42.78 | 0
| PIPE SW H/D PVC S/WELD 225MM | m |  | 32.66 | 0
| PIPE DWV SN8 PVC S/WELD 150MM | m |  | 19.55 | 0
| PIPE DWV SN4 PVC S/WELD 150MM | m |  | 16.1 | 0
| PIPE DWV SN8 PVC S/WELD 150MM - Suspended | m |  | 19.55 | 0
| PIPE DWV SN4 PVC S/WELD 150MM | m |  | 16.56 | 0
| PIPE DWV SN8 PVC S/WELD 100MM | m |  | 6.693 | 0
| PIPE DWV SN4 PVC S/WELD 100MM | m |  | 6.9 | 0
| PIPE DWV SN8 PVC S/WELD 50MM | m |  | 6.693 | 0
|  |  |  | 0 | 0
| DWV Grade Option |  |  | 0 | 0
|  | ea |  | 0 | 0
| 600*225 Ribbed Saddle | ea |  | 676.2 | 0
| 600*45Deg RIBBED Bend | ea |  | 897 | 0
| 600*450 Ribbed Reducer | ea |  | 1518 | 0
| 450*375 Ribbed*PVC Reducer | ea |  | 634.8 | 0
| 450 45 Deg ribbed Bend | ea |  | 800.4 | 0
| 450 * 225 Ribbed Saddle | ea |  | 441.6 | 0
| 375mm X 45Deg Junction | ea |  | 579.6 | 0
| 375X300X45D PVC JUNCTION | ea |  | 776.0982 | 0
| 375X225X45D PVC JUNCTION | ea |  | 777.4782 | 0
| 375MM X 300MM Reducer | ea |  | 524.4 | 0
| 375MM X 225MM Reducer | ea |  | 496.8 | 0
| 375MM X 90Deg Bend | ea |  | 745.2 | 0
| 375MM X 45Deg Bend | ea |  | 621 | 0
| 300MM * 45D PVC JUNCTION | ea |  | 496.8 | 0
| 300X225X45D PVC JUNCTION | ea |  | 441.6 | 0
| 300MM X 225MM Reducer | ea |  | 262.2 | 0
| 300MM X 90Deg Bend | ea |  | 345 | 0
| 300MM X 45Deg Bend | ea |  | 262.2 | 0
| 300MM X 150 Junction | ea |  | 455.4 | 0
| 225MM * 45D PVC JUNCTION | ea |  | 117.645 | 0
| 225X150X45D PVC JUNCTION | ea |  | 289.8 | 0
| 225MM X 90Deg Bend | ea |  | 85.56 | 0
| 225MM X 45Deg Bend | ea |  | 84.18 | 0
| 225MM X 150MM Reducer | ea |  | 62.1 | 0
| 150 PVC DWV 45Deg Junct | ea |  | 24.84 | 0
| 150MM X 90Deg Bend | ea |  | 22.08 | 0
| 150MM X 45Deg Bend | ea |  | 16.56 | 0
| 150X100X45D PVC JUNCTION | ea |  | 22.08 | 0
| PVC PIPE REDUCER 150X 100 mm | ea |  | 22.08 | 0
| 100MM * 45D PVC JUNCTION | ea |  | 6.486 | 0
| 100X50 X45D PVC JUNCTION | ea |  | 22.08 | 0
| PVC PIPE REDUCER 100X 50 mm | ea |  | 22.08 | 0
| 100MM X 90Deg Bend | ea |  | 16.56 | 0
| 100MM X 45Deg Bend | ea |  | 16.56 | 0
| 50 PVC X 45D PVC JUNCTION | ea |  | 19.32 | 0
| 50MM X 90Deg PVC Bend | ea |  | 0.897 | 0
| 50MM X 45Deg PVC Bend | ea |  | 0.897 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
| 150mm PVC 10mm nut hanging clip | ea |  | 2.622 | 0
| 10mm Zinc Threaded Rod | m |  | 2.76 | 0
| Glue - Blue - 4Ltr | ea |  | 36.432 | 0
| Primer - Red - 4Ltr | ea |  | 31.74 | 0
|  |  |  | 0 | 0
| SW_RRJ (RIBBED) Fittings |  |  | 0 | 0
|  |  |  | 0 | 0
| 375MM X 45Deg Bend | ea |  | 362.1396 | 0
| DN 375 X DN150 45 DEG BLACKMAX REDUCING JUNCTION (PVC FAB) | ea |  | 828 | 0
| DN375 x dn225 BlackMax® Reducing Adaptor FF RRJ x DWV SWJ (PVC Fab) | ea |  | 552 | 0
|  |  |  | 0 | 0
| DN 300 X DN150 45 DEG BLACKMAX REDUCING JUNCTION (PVC FAB) | ea |  | 690 | 0
| DN300 BLACK MAX 45 DEG BEND | ea |  | 414 | 0
| DN300 x dn225 BlackMax® Reducing Adaptor FF RRJ x DWV SWJ (PVC Fab) | ea |  | 414 | 0
| DN300 BLACK MAX 45 DEG BEND | ea |  | 414 | 0
|  | ea |  | 0 | 0
| 150mm Cap | ea |  | 20.7 | 0
| 150mm expansion coupler | ea |  | 110.4 | 0
| 450X450 GRATED SW GULLY | ea |  | 180 | 0
FITOFF
| Fit-Off consumable material - per adopted fixture (allow $30/EA x 15) | ea | 15 | 30 | 450 | - | Fit-off consumable basis: 15 adopted PAM fixtures x $30/EA
| Fit-Off Material; Ground & First Floor - | ea |  | 0 | 0
| Seismic restraint hardware - AS1170.4 EDC 2 (PAM minor - HWU strap + hanger braces) | item | 1 | 500 | 500 |  | Gap #3 allowance; install within rough-in/fit-off days; layout drafting only (CL C7)
| HWU mounting - 316 SS plinth/stand + fixings per H-PAM-301 detail (1x Rheem 50L) | EA | 1 | 260 | 260 |  | RULE 4 GAP CLOSED: as NBC - safe tray priced at W26, seismic strap in r853, plinth/stand priced nowhere. Estimator basis as NBC. Install labour already in T4-06 - materials only here.
SUB TOTALS
90803.0499
|  |  |  | Contingency | 1.18
|  |  |  | Deliveries | 2500
TOTALS
109647.5988
Excavation/Quarry/Misc/ Takeoff.
|  | Qty | Unit
| Avrg Trench = .900D*.450W | 71.36 | m
| L/M Of Asphalt Reinstate | 0 | m
| M2 Of Asphalt Reinstate | 0 | m2
| L/M Of CBR Reinstate | 0 | m
| L/M of Inground Pipe (Average Depth) | 71.36 | m
| L/M of Inground Pipe (Deeper Than Average Depth) |  | m
| Avergage of trtenches 'Shared'…. Shared trench Factor | 0.1 | m
| SEWER / SW / TW - InGrnd |  | m | 0%
| WAT / FIRE - InGrnd |  | m | 0%
| SPK - InGrnd |  | m | 0%
|  | D | W | L | Spoil/Compact Factor; | Shared Trench Factor | Total m3 - EXCAVATED | Total M3 - Bed, Pipe, Cover reduction | Total M3 - Backfill Req (Less Bed&Pipe) | Total M3 - Spoil - REMOVE | TCS Load - Haulage & dump rate only
| L/M of Inground Pipe (Average Depth) | 0.95 | 0.6 | 71.36 | 1.3 | 0.1 | 48.8102
| L/M of Inground Pipe (Deeper Than Average Depth) | 1.1 | 0.5 | 0 | 1.3 | 0 | 0
| L/M of Bed, Pipe, Cover material reduction (Average Depth) | 0.35 | 0.6 | 71.36 | 0 | 0.1 |  | 13.487
| L/M of Bed, Pipe, Cover material reduction (Deeper Than Average Depth) | 0.2 | 0.5 | 0 | 0 | 0 |  | 0
| L/M of BACKFILL required (Average Depth) | 0.95 | 0.6 | 71.36 | 1.3 | 0.1 |  |  | 35.3232
| L/M of BACKFILL required (Deeper Than Average Depth) | 1.1 | 0.5 | 0 | 1.3 | 0 |  |  | 0
[10 empty] | QTY | Rate | Total
[7 empty] | 48.8102 | 13.487 | 35.3232 | 13.487 | 15 | 202.3056
| Thrust Block Concrete | m3/TB | Qty | Total m3 | Contingency | Total m3 | Total Cost
|  | 0.1 |  | 0 | 1.1 | 0 | 0
Quarry & Concrete Product
1.4
| Description | Unit/LM | Unit | Rate | Rate/LM |  |  | QTY | Shared Trench Factor | Total Req. | Total | Contingency | TOTAL | Drainage Use | Fire/WAT Use | SPK Use
| 5-7mm Stone | 0.203 | Ton | 62 | 12.586 |  |  | 14.4861 | 0.1 | 13.0375 | 808.3233 | 323.3293 | 1131.6526 | 0
| 5-7mm Stone | 0.14 | m3 | 62 | 16.926
| 10-12mm Stone | 0.45 | Ton | 62 | 27.9 |  |  | 0 |  |  | 0 |  | 0
| 80-110mm Stone | 0 | Ton | 25 | 0 |  |  | 0 |  |  | 0 |  | 0
| Medium River / Bed Sand | 0.225 | Ton | 62 | 13.95 |  |  | 16.056 | 0.1 | 14.4504 | 895.9248 | 358.3699 | 1254.2947 |  | 0 | 0
| Medium River / Bed Sand | 0.14 | m3 | 62 | 13.02
| CBR15 Road Base | 0.36 | Ton | 27 | 9.72 |  |  | 0 |  |  | 0 |  | 0
| CBR45 | 0.36 | Ton | 30 | 10.8 |  |  | 0 |  |  | 0 |  | 0
| LEANMIX | 0.3 | m3 | 0 | 0 |  |  | 0 |  |  | 0 |  | 0
|  |  |  | TCS | Q2
| Description |  | Unit | Rate | Rate
| 5-7mm Stone |  | T | 62 | 31
| 10-12mm Stone |  | T | 62 | 39
| 80-110mm Stone |  | T | 25 | 29
| Medium River / Bed Sand |  | T | 62 | 26
| CBR15 Road Base |  | T | 48 | 27
| CBR45 |  | T | 50 | 30
| LEANMIX_20mm-12:1 |  | M3 | 168 | 0
| Concrete_25/20/80 |  | M3 | 153 | 0

## Siteworks
Project:
Tricore -
Stage 1 Version 1
Item
1 | Complete -
Labour
[6 empty] | Denis qty | Qty / rate source note
| DAY | [7 empty] | april 2026 direct impact Increase % (not contigency)
| TRADESMAN_LEADING HAND | Day |  | 1329.6343 | 0
| TRADESMAN_PLUMBER_OPERATOR | Day |  | 1016.4579 | 0 |  |  |  |  | PE Pipe & Fitting | 38% | 1.38
| T/A & Apprentice | Day |  | 829.5103 | 0 |  |  |  |  | PVC Pipe & Fittings | 38% | 1.38
| Crew #1 - InGround Drainage | Day | 23 | 2862.4261 | 65835.8003 |  | Phase 7 Crew 1 site: T1-01..T1-05 + T1-11 + T1-12 = 23 crew-days (T1-06 rising main EBC excluded) |  |  | Subby Rates | 15% | 1.15
| Crew #2 - InGround Water/Fire | Day | 35 | 2862.4261 | 100184.9135 |  | Phase 7 Crew 2 site: T2-01..T2-08 + T2-10 = 35 crew-days |  |  | Delivey Rate | 20% | 1.2
| Crew #3 - Above Ground Drainage | Day |  | 2862.4261 | 0
| Crew #4 - Above Ground WATER/FIRE | Day |  | 2862.4261 | 0
| Crew #5 - Above Ground FitOff / Misc | Day |  | 2862.4261 | 0
| Crew #6 - DEMO | Day |  | 1845.9682 | 0
HOUR
| TRADESMAN_LEADING HAND | HR | 489.2 | 132.9634 | 65045.7093 |  | Phase 7 LH supervision - site activities 489.2 hr (of 1,400 hr / 140 d total)
| TRADESMAN_PLUMBER_OPERATOR | HR | 0 | 101.6458 | 0
| T/A & Apprentice | HR | 0 | 82.951 | 0
| Crew #1 - InGround Drainage | HR | 0 | 286.2426 | 0
| Crew #2 - InGround Water/Fire | HR | 0 | 286.2426 | 0
Demolition & Reinstatement
DEMO
| Asphalt Cutting | m |  | 15.525 | 0
| Concrete Cutting | m |  | 18.4 | 0
| Con Cut Establishemnt Fee | ea |  | 92 | 0
REINSTATE - CONCRETE
| Road/Drveway Reinstate; 1mW x 150 Thck, N25/20/80, Incl Reinforcement | m |  | 145 | 0
| Kerb & Channel - 1m Wide | ea |  | 155 | 0
| Footpath - 1.5mW, N25/20/80, Incl Reinforcement | lm |  | 180 | 0
| Footpath - 1.5mW, EXPOSED AGG, N25/20/80, Incl Reinforcement | lm |  | 185 | 0
REINSTATE - ASPHALT
| 50mm Thck - Trench Reinstatement Through Road/Driveway | m2 |  | 97 | 0
| 50mm Thck - 1.5-2m Wide Footpath reinstatements | m2 |  | 97 | 0
| Establishment Fee (1 per stage) | Ea |  | 5500 | 0
Equipment & Hire - INCL WET PLANT HIRE
PLANT HIRE - WET
| 1.8T Excavator | Hr |  | 100 | 0
| 3-5 ton Excavator | Hr |  | 115 | 0
| 3-5T Combo | Hr |  | 154 | 0
| Hammer attachment 3.5-4T | Hr |  | 21 | 0
| Ripper 3.5-4T | Hr |  | 10 | 0
| 5t Excavator | Hr |  | 150 | 0
| Hammer attachment 5T | Hr |  | 50 | 0
| Skid steer | Hr |  | 140 | 0
| 8T Excavator | Hr |  | 128 | 0
| Hammer attachment 8T | Hr |  | 26 | 0
| Ripper 8T | Hr |  | 10 | 0
| 13-15T Excavator | Hr |  | 153 | 0
| Hammer attachment 14T | Hr |  | 36 | 0
| Ripper 14T | Hr |  | 10 | 0
| 3000L Hydro Excavation Truck | Hr | 20 | 190 | 3800 |  | Hydro-ex 3000L: T1-04 1 d + T2-02 1 d = 20 hr wet @ $190
| 4500L Hydro Excavation Truck | Hr |  | 220 | 0
| 6300L Hydro Excavation Truck | Hr |  | 250 | 0
| Water Truck allow for water at cost | Hr | 30 | 110 | 3300 |  | Water truck: T1-11 1 d + T2-10 2 d = 30 hr wet @ $110 (test/flush cartage)
| 12t Body Truck Tipper | Hr |  | 110 | 0
HIRE - DRY
| Skid Steer Loader_Tracked (CAT249+) | Day |  | 225.4333 | 0
| Skid Steer Loader_Wheeled (CAT226+) | Day |  | 163.9667 | 0
| Mini Loader, Stand-on Type | Day |  | 180 | 0
|  |  |  | 0 | 0
| 1.5-1.8 Ton_Excavator | Day | 2 | 137.1429 | 274.2857 |  | Phase 7 plant: 1.8T: T2-06 2
| 1.7-2Ton_Excavator | Day |  | 0 | 0
| 3-5Ton_Excavator | Day | 11 | 238.6667 | 2625.3333 |  | Phase 7 plant: 3-5T: T1-03 6 + T1-04 3 + T1-05 2
| 8Ton_Excavator | Day | 6 | 261.1667 | 1567 |  | Phase 7 plant: 8T: T2-02 3 + T2-03 2 + T2-08 1
| 10-12Ton_Excavator | Day |  | 0 | 0
| 13-16Ton_Excavator | Day | 16 | 317.2 | 5075.2 |  | Phase 7 plant: 13-16T: T2-01 5 + T2-04 6 + T2-07 5
| 20-24Ton_Excavator | Day |  | 314.2857 | 0
|  |  |  | 0 | 0
| Ripper_1.7-2T | Day |  | 0 | 0
| Ripper_1.5-4T | Day |  | 32.74 | 0
| Ripper_3-5T | Day |  | 0 | 0
| Ripper_8T | Day |  | 40.38 | 0
| Breaker_1.7-2T | Day |  | 123.33 | 0
| Breaker_3-5T | Day |  | 165.89 | 0
| Breaker_8T | Day |  | 165.89 | 0
| Breaker_10-12T | Day |  | 0 | 0
| Breaker_13-15T | Day |  | 203 | 0
| Auger Drive_10-12T |  |  | 0 | 0
| 300Dia Auger Drill |  |  | 0 | 0
|  |  |  | 0 | 0
| 1.25T_Tipper Truck | Day |  | 205 | 0
| 2-4T_Tipper Truck | Day |  | 166.98 | 0
| <6T_Tipper Truck | Day | 18 | 171.4286 | 3085.7143 |  | Phase 7 plant: <6T tipper - Phase 7 roll-up 18 d
|  |  |  | 0 | 0
| <10T_Articulated Site Tipper | Day |  | 0 | 0
| Upright Rammer_Wacker | Day | 14 | 34.2857 | 480 |  | Phase 7 plant: Wacker - site share of Phase 7 roll-up 28 d
| Trench Roller_Dbl Drum_Remote | Day | 22 | 165 | 3630 |  | Phase 7 plant: Trench roller: T1-03 6 + T2-01 5 + T2-04 6 + T2-07 5
| <26Ft_Scissor Lift - Diesel | Day |  | 0 | 0
| <26Ft_Scissor Lift - Elec | Day |  | 300 | 0
| <34Ft_Boom Lift - Diesel | Day |  | 0 | 0
| <34Ft_Boom Lift - Elec | Day |  | 0 | 0
|  |  |  | 0 | 0
| Porta Loo_No Tank | Day |  | 5.46 | 0
| 6*3m Demantable Lunchroom - COMPLETE | Day |  | 23 | 0
| 6*3m Demantable Office - COMPLETE | Day |  | 23 | 0
| 20Ft Shipping Container | Day |  | 0 | 0
| Quick Cut Demo Saw | Day |  | 0 | 0
| Sngl Ph_6KVA Genset | Day |  | 0 | 0
| Diesel Air Compressor_Trailer | Day |  | 0 | 0
| Air Breaker - Heavy | Day |  | 0 | 0
| Air Hose <10m | Day |  | 0 | 0
| Elec Breaker/Jachammer | Day |  | 0 | 0
| Flexdrive Motor Unit | Day |  | 0 | 0
| Flexdrive_Pump Shaft | Day |  | 0 | 0
| Temporary Power Board | Day |  | 0 | 0
|  |  |  | 0 | 0
| Dual CabUte | Day |  | 0 | 0
| 3m3 Skip Bbin | per serive |  | 230 | 0
| plus disposal | Tonne |  | 309 | 0
| site fee | Week |  | 35 | 0
| ~4m3_Skip Bin | per change over |  | 229.9 | 0
| ~6m3_Skip Bin | per change over |  | 239.8 | 0
| Plus disposal | Tonne |  | 309 | 0
| Site fee | Week |  | 35 | 0
| Vacuum Excavator - Vermeer VT250D | Day |  | 295.77 | 0
| Vac Trailer – Dry Hire | Day | 1 | 355 | 355 |  | Phase 7 plant: Vac trailer: T1-02 1 d
|  |  |  | 0 | 0
| TRANSPORT_Ex BRIS - Return | Day |  | 0 | 0
| TRANSPORT_Ex ROK - Return | Hour |  | 180 | 0
| 0-4T Per Hour Delivery Rate | Hour |  | 125 | 0
| 5 - 9t Transport Hourly Rate | Hour |  | 160 | 0
| 10 - 19t Low Loader Hourly rate - Minimum 2 Hour Charge | Hour |  | 200 | 0
| PE butt welder + EF processor - ALLOWANCE (not in hire registers - quote at Phase 6) | Day | 16 | 350 | 5600 |  | Phase 7: O200 main 5 d + CW spine 6 d + fire main 5 d
| FUEL - Average_Candle | Week |  | 1850 | 1850
Subbies & Misc
| Surveyor | ea | 16 | 180 | 2880 |  | T5-07 as-cons/ADAC surveyor attendance 2 d x 8 h @ $180/hr
| Services Locator | ea | 10 | 130 | 1300 |  | T1-02 services locator 1 d x 10 h @ $130/hr (live O300 main)
| Compaction Testing - TEST | ea | 36 | 115 | 4140 |  | DERIVED 27 Jul 2026 on the NBC basis (Director decision: compaction testing included). NBC carries 15 tests against its own adopted trench length 387.68 m ('ClubHouse (NBC )'!C955) = 1 test per 25.8 m. That frequency is corroborated by VOL 38 spec cl 3.62 (compaction schedule), which mandates 1 test per 25 m in vehicular locations / 1 per 50 m elsewhere, 2 per layer at pits. Quantity is a live formula = this sheet's own trench metres x NBC tests / NBC trench metres, rounded up. Rate unchanged (Misc Subbie Rates_Master D72, $115/ea). Siteworks adopted trench length 924.56 m (C886) -> 924.56 x 15/387.68 = 35.77 -> 36 tests. Siteworks holds the longest runs in the package (O200 main, 236.88 m CW spine, 217.73 m fire main, 207.53 m gravity sewer) so its count correctly exceeds NBC's 15.
| Compaction Testing - Site Establishment | ea | 10 | 90 | 900 |  | DERIVED SEPARATELY 27 Jul 2026 - establishment is a per-VISIT mobilisation charge, it does NOT scale with metres. Basis = NBC's own batching ratio: 15 tests over 4 establishments = 3.75 tests presented per lab visit. Quantity = this sheet's test count / 3.75, rounded up. Cross-check: the same result is obtained from NBC's visit density (387.68 m / 4 visits = 1 visit per 96.9 m of trench). Consistent with the programme's mobilisation logic (PROGRAMME_LABOUR_PLANT TPS_Activities T1-12: separate mobilisations assumed for site mains / rough-in / fit-off). Rate unchanged (Misc Subbie Rates_Master D73, $90/ea). Siteworks 36 tests / 3.75 = 9.60 -> 10 establishment visits.
| CCTV of TPS in-ground drainage - independent approved firm, Superintendent present (VOL38 3.56) | item | 1 | 5000 | 5000 |  | Allowance ~385 m @ ~$10/m + establishment + reporting + attendance; each entity its own assets (L15)
| Temporary potable water purchase - testing/flushing/disinfection (carted, no site water ITT S17.3) | item | 1 | 1500 | 1500 |  | Allowance; cartage priced at water-truck row (30 hr)
| FIRE TESTING / CERT | ea | 1 | 3560 | 3560 |  | Boost/fire test $3,560 (Misc Subbie Rates) - booster commissioning; existing label row
| FULL Hydro Test - Per Test (6.5Hr 1 x fitter, 1 x apprentice, 1 day Test gear) | ea | 3 | 1945 | 5835 |  | 3 site systems full hydro test per T2-10 @ $1,945
| Provision of Form 72 | ea | 1 | 350 | 350 |  | Form 72 provision - site
| Crane truck / HIAB - booster set + deliveries (allowance) | Hr | 10 | 180 | 1800 |  | Phase 7 allowance ~$180/hr - not in hire registers
| Long-lead equipment storage & double-handling allowance (booster, 316SS, HWUs, Stoddart specials) | item | 1 | 1200 | 1200 |  | RULE 4 GAP CLOSED - 'storage' is a separate Rule 4 determination and was priced nowhere. Long leads per Phase 7: 316SS press 10-14 wks, booster + cabinet 10-12 wks, Rheem 4-6 wks, Stoddart s/s fixtures + in-wall cisterns 8-12 wks. Supplier storage charges bite after 30 days (Humes Service Fees basis). Estimator allowance. NOT a duplicate of the 20 ft site container (Prelim & OH B80), which is the on-site store - this covers off-site holding and the extra handling movement.
Material - Quarry, Misc
| Bedding / Fill Sand | m3 | 174.7418 | 39.75 | 6945.9881 |  | Bedding/pipe-surround import = helper I902 (bed/pipe/cover m3, auto from adopted pipe lengths)
| CBR 45/2.5 Roadbase | m3 |  | 41.9 | 0
| Turf Underlay/Topsoil | m3 |  | 45.25 | 0
| Standard Garden Woodchip | m3 |  | 87 | 0
| Turf - Standard Couch or Similar | Slab (.5m2) |  | 6.48 | 0
| Spoil haulage & dump (take-off helper M902 @ $15/m3) | item | 1 | 2621.1276 | 2621.1276 |  | Auto from helper block (excavated less backfill re-use)
| Cement Stabalized Sand (3-5%) | m3 |  | 169 | 0
| Exposed Agg Concrete - Standard/Cheapest Exposed Agg Stone | m3 |  | 252 | 0
| N25 20mm 80 Slump Concrete | m3 |  | 263 | 0
| Consumables & small tools - site crews (allowance) | item | 1 | 2500 | 2500 |  | Phase 7 consumables flag - site activities
| Valve Margin strips; Concrete slab, 1 directions sign, 3 x valve No sign. | ea |  | 380 | 0
FIRE SERVICES - INGROUND
| 200 HDPE PN16 SDR11 - REDLINE | m |  | 46.8107 | 0
| 180 HDPE PN16 SDR11 - REDLINE | m |  | 35.144 | 0
| 125 HDPE PN16 SDR11 - REDLINE | m | 217.73 | 16.9936 | 3700.0056 | 218 | ADOPTED qty per QUANTITY_RECONCILIATION TPS_Site (vector-verified H003) - fire main 217.73 m
| 32 HDPE PN16 SDR11 - BLUELINE | m |  | 1.6779 | 0
0
| 200 EF Coupler | ea |  | 60.8028 | 0
| 180 EF Coupler | ea |  | 35.4936 | 0
| 125 EF Coupler | ea | 1 | 19.4718 | 19.4718
| 200 EF 45DFeg Bend | ea |  | 150.6408 | 0
| 180 EF 45DFeg Bend | ea |  | 135.1986 | 0
| 125 EF 45DFeg Bend | ea |  | 61.6722 | 0
| 200 EF 90DFeg Bend | ea |  | 150.6408 | 0
| 180 EF 90DFeg Bend | ea |  | 134.9778 | 0
| 125 EF 90DFeg Bend | ea | 6 | 70 | 420
| 125 EF 45DFeg Bend | ea | 3 | 62 | 186
| 200 EF TEE | ea |  | 151.455 | 0
| 180 EF TEE | ea |  | 157.7064 | 0
| 125 EF TEE | ea | 1 | 67.965 | 67.965
| 200*180 EF TEE | ea |  | 289.0686 | 0
| 200*125 EF TEE | ea |  | 301.4196 | 0
| 180*125 EF TEE | ea |  | 168.5394 | 0
| 200*180 EF Reducer | ea |  | 173.3556 | 0
| 180*125 EF Reducer | ea |  | 82.938 | 0
| 200PE*8"(200m) - MaxiStub W/Backing Ring | ea |  | 472.443 | 0
| 180PE*6"(150mm) - MaxiStub W/Backing Ring | ea |  | 179.0826 | 0
| 125PE*4" (100mm) - MaxiStub W/Backing Ring | ea |  | 127.8846 | 0
| 180mm PE x 150mm GALV ADAPTER - PLASSON Brand | ea |  | 432.2022 | 0
| 125mm PE x 100mm GALV ADAPTER - PLASSON Brand | ea | 1 | 281.6718 | 281.6718
|  | 0 |  | 0 | 0
| 180mm PE x 150mm GALV ADAPTER | ea |  | 435.6798 | 0
| 125mm PE x 100mm GALV ADAPTER | ea |  | 277.9734 | 0
| 200 Long SPIG 45DFeg Bend | ea |  | 94.5852 | 0
| 180 Long SPIG 45DFeg Bend | ea |  | 88.9548 | 0
| 125 Long SPIG 45DFeg Bend | ea |  | 53.4888 | 0
| 200 Long SPIG 90DFeg Bend | ea |  | 118.9146 | 0
| 180 Long SPIG 90DFeg Bend | ea |  | 93.9918 | 0
| 125 Long SPIG 90DFeg Bend | ea |  | 43.677 | 0
| 200 Long SPIG TEE | ea |  | 176.1432 | 0
| 180 Long SPIG TEE | ea |  | 157.6236 | 0
| 125 Long SPIG TEE | ea |  | 52.7988 | 0
| 200*180 Long SPIG TEE | ea |  | 253.2024 | 0
| 200*125 Long SPIG TEE | ea |  | 265.5534 | 0
| 180*125 Long SPIG TEE | ea |  | 256.2798 | 0
| 200*180 Long SPIG Reducer | ea |  | 77.0592 | 0
| 180*125 Long SPIG Reducer | ea |  | 54.9654 | 0
|  | 0 |  | 0 | 0
| 200 FL DICL Sluice Valve | ea |  | 679.41 | 0
| 150 FL DICL Sluice Valve | ea |  | 323.53 | 0
| 100 FL DICL Sluice Valve | ea |  | 202.94 | 0
| Valve Spindle Riser - 600Long | ea |  | 136.94 | 0
| Valve Box - Cast Iron Trafficable - Rectangle Type "V" | ea |  | 123.53 | 0
| Valve Box - Non-Trafficable - Plastic Surround with CI Drop In "V" | ea |  | 98.82 | 0
|  | 0 |  | 0 | 0
| 200*150mm DICL FL Reducer | ea |  | 291.18 | 0
| 200*100mm DICL FL Reducer | ea |  | 330 | 0
| 150*100mm DICL FL Reducer | ea |  | 156 | 0
| 150mm DICL FL * SP Adapter | ea |  | 106.24 | 0
| 100mm DICL FL * SP Adapter | ea |  | 70.59 | 0
| 200mm DICL FL 90Deg Bend | ea |  | 516.35 | 0
| 150mm DICL FL 90Deg Bend | ea |  | 198.88 | 0
| 100mm DICL FL 90Deg Bend | ea |  | 108.71 | 0
| 200mm DICL FL TEE | ea |  | 672.65 | 0
| 150mm DICL FL TEE | ea |  | 228.24 | 0
| 100mm DICL FL TEE | ea |  | 128.24 | 0
| 200*150*200 DICL FL TEE | ea |  | 536.76 | 0
| 200*100*200 DICL FL TEE | ea |  | 576.47 | 0
| 150-100-150 DICL FL TEE | ea |  | 198.82 | 0
| 200mm DICL FL Pipe @ 1000 | ea |  | 898.82 | 0
| 200mm DICL FL Pipe @ 600 | ea |  | 640 | 0
| 200mm DICL FL Pipe @ 300 | ea |  | 355.29 | 0
| 150mm DICL FL Pipe @ 1000 | ea |  | 534.41 | 0
| 150mm DICL FL Pipe @ 600 | ea |  | 280 | 0
| 150mm DICL FL Pipe @ 450 | ea |  | 236.47 | 0
| 150mm DICL FL Pipe @ 300 | ea |  | 178.8 | 0
| 100mm DICL FL Pipe @ 1000 | ea |  | 362.35 | 0
| 100mm DICL FL Pipe @ 600 | ea |  | 144.71 | 0
| 100mm DICL FL Pipe @ 450 | ea |  | 135.88 | 0
| 100mm DICL FL Pipe @ 300 | ea |  | 76.47 | 0
| 150mm DICL FL Deadplate | ea |  | 67.65 | 0
| 100mm DICL FL Deadplate | ea |  | 43.53 | 0
|  | 0 |  | 0 | 0
| 200mm PE*DI Gasket Kit Complete | ea |  | 67.06 | 0
| 200mm DI*DI Gasket Kit Complete | ea |  | 46.71 | 0
| 150mm PE*DI Gasket Kit Complete | ea |  | 60 | 0
| 150mm DI*DI Gasket Kit Complete | ea |  | 42.35 | 0
| 100mm PE*DI Gasket Kit Complete | ea |  | 24.71 | 0
| 100mm DI*DI Gasket Kit Complete | ea |  | 20 | 0
|  | 0 |  | 0 | 0
| 150mm SS Gibault Adapter Coupling | ea |  | 108.71 | 0
| 100mm SS Gibault Adapter Coupling | ea |  | 87.06 | 0
| 180mm PE GRIPPER Adapter Coupling | ea |  | 305.88 | 0
| 125mm PE GRIPPER Adapter Coupling | ea |  | 182.35 | 0
| 180mm PE GRIPPER * 150FL Adapter Coupling | ea |  | 229.41 | 0
| 125mm PE GRIPPER * 100FL Adapter Coupling | ea |  | 152.94 | 0
| 180mm PE GRIPPER Sluice Valve | ea |  | 690 | 0
| 125mm PE GRIPPER Sluice Valve | ea |  | 408.47 | 0
|  | 0 |  | 0 | 0
| Detectable Tape - Fire x 250m | ea |  | 90 | 0
| Alcohol Weld Wipes | ea |  | 13.5 | 0
| Denzo Tape 100mm roll | ea |  | 27.14 | 0
| Black over-wrap tape - roll | ea |  | 27.14 | 0
0
| FIRE SERVICES - ABOVE GROUND |  |  |  | 0
| Description | Unit
| 150mm MED DUTY Galv Pipe | m |  | 43.8462 | 0
| 100mm MED DUTY Galv Pipe w/RG Ends | m |  | 28.4615 | 0
| 100mm Class B Copper Pipe | m |  | 106.2417 | 0
| 25mm Class B Copper Pipe | m |  | 59.82 | 0
|  | 0 |  | 0 | 0
| 150mm Galv RG Coupling | ea |  | 12.83 | 0
| 100mm Galv RG Coupling | ea |  | 7.55 | 0
| 150mm Galv RG TEE | ea |  | 35.5 | 0
| 100mm Galv RG TEE | ea |  | 16.93 | 0
| 150mm Galv RG BEND 90Deg | ea |  | 22.85 | 0
| 100mm Galv RG BEND 90Deg | ea |  | 10.62 | 0
| 150mm Galv RG BEND 45Deg | ea |  | 23.5 | 0
| 100mm Galv RG BEND 45Deg | ea |  | 11.4 | 0
| 150mm Galv RG x 100mm FLANGE Adapt | ea |  | 30.75 | 0
| 100mm Galv RG x 100mm FLANGE Adapt | ea |  | 23.21 | 0
| 150mm RG Butterfly Valve Geared Wheel | ea |  | 217.8 | 0
| 100mm RG Butterfly Valve Geared Wheel | ea |  | 169.4 | 0
|  | 0 |  | 0 | 0
| 150mm H-Pattern Booster Assembly Complete | ea | 1 | 2350 | 2350
| Booster Cabinet - Compl with doors and stickers | ea | 1 | 1155 | 1155
|  | 0 |  | 0 | 0
| 100mm Dual Pillar Hydrant Complete_ Flanged Base 1500 High w/landing Valves | ea | 1 | 365 | 365
| 100mm Dual Pillar Hydrant Complete_ RG Base 1500 High w/landing Valves_OPTION | ea |  | 365 | 0
| 65mm RG Landing Valve | ea |  | 90 | 0
| Red caps and chain - suit 65mm QLD Landing valve | ea |  | 5 | 0
| 36m Fire Hose Reel w/25mm isolation valve | ea |  | 125 | 0
| 25mm Isolation Ball Valve (for fire hose reel) valve only, with hose nozzle latch | ea |  | 39 | 0
|  | 0 |  | 0 | 0
| 150mm FL Testable Double Check Valve - Compl. w/Valves | ea |  | 3100.7 | 0
| 150mm FL RPZD Valve - Compl. w/Valves | ea |  | 4237.09 | 0
|  | 0 |  | 0 | 0
| 100mm FL Levered Butterfly Vlave | ea |  | 114.44 | 0
| 100mm Cu Copper Pipe | m |  | 122.6667 | 0
| 100mm Copper Crimp - TEE | ea |  | 219.36 | 0
| 100mm Copper Crimp - 90Deg Bend | ea |  | 155.6 | 0
| 100mm Copper Crimp - 45Deg Bend | ea |  | 125.77 | 0
| 100mm Copper Crimp - Straight Socket | ea |  | 83.25 | 0
| 100mm Copper Crimp - 100mm FL Adapter | ea |  | 52.25 | 0
| 80mm Copper Crimp - TEE | ea |  | 175.66 | 0
| 100mm*80mm Copper Crimp - REDUCER | ea |  | 164.08 | 0
|  | 0 |  | 0 | 0
| 32mm Fi Lockable Ball Valve | ea |  | 77.95 | 0
| 32mm Cu Crimp * 32mi Adapt | ea |  | 17.16 | 0
| 32mm Cu Crimp Coupling Straight | ea |  | 7.23 | 0
| 32mm Cu Crimp 90Deg Bend | ea |  | 14.31 | 0
| 32mm Cu Crimp 45Deg Bend | ea |  | 16.24 | 0
| 32mm*25mm Cu Crimp Reducer | ea |  | 14.36 | 0
| 25mm Fi Lockable Ball Valve | ea |  | 46.94 | 0
| 25mm Cu Crimp * 25mi Adapt | ea |  | 8.46 | 0
| 25mm Cu Crimp Coupling Straight | ea |  | 5.74 | 0
| 25mm Cu Crimp 90Deg Bend | ea |  | 7.7 | 0
| 25mm Cu Crimp 45Deg Bend | ea |  | 10.19 | 0
|  | 0 |  | 0 | 0
| 150mm Galv 2 Piece Weld-nut Bracket M12 | ea |  | 5.86 | 0
| 100mm Galv 2 Piece Weld-nut Bracket M12 | ea |  | 4.41 | 0
| 150 Galv 2 Piece Channel Clip | ea |  | 5.36 | 0
| 100 Galv 2 Piece Channel Clip | ea |  | 4.4 | 0
| 12mm Galv Threaded Rod | ea |  | 10.64 | 0
| Galv Braced Counter Lever Bracket - 450Long | ea |  | 20 | 0
| 003 Padlock | ea |  | 19.5 | 0
| 100mm DI*DI Gasket Kit Complete | ea |  | 20 | 0
FIRE SERVICES - Misc.
Description
| Decommisioning Material | ea |  | 1388 | 0
| Electrofusion PE Welder 25-250mmPE. Please detail Spec | ea |  | 0 | 0
| PE Butt Welder. Automatic. 125-250mmPE. Please detail Spec - HIRE | WEEK |  | 450 | 0
| Hand Roll Groover. 65-150mm. | ea |  | 0 | 0
| Delivery - To Rockhampton PIPE LENGTHS as quoted | ea |  | 2178.48 | 0
| Delivery - To Rockhampton Standard/Palletised items | ea |  | 2178.48 | 0
POTABLE WATER_MAINS & R'Ins
Description
| O200 ID HDPE PE100 SDR11 DN250 potable main (BASE OFFER per SS5.5) | m | 134.63 | 171.718 | 23118.3881 | 135 | ADOPTED 134.63 m (vector-verified). RE-RATED: base offer O200 ID HDPE PE100 SDR11 DN250 per locked SS5.5 / VOL38 s10.1 equivalence (Opens #12) | BENCHMARK-DERIVED PENDING RFQ (Gap #5): Reece Q-459014437 (NAS, Jul-26) PE100 PN16 125 @ $186.65/6m = $31.1083/m x (250/125)^2 weight ratio = $124.4333/m; x1.38 PE escalation-to-2027 applied once via $M$16 (source pre-escalation per KeyRates). Copper build-up (134.63 m @ $2,015/6m Tradelink 6595064) retained as ALTERNATE - see EBC_Alternates; copper tapping-cluster fittings remain in base per adopted counts.
| 200mm copper tee | ea | 2 | 390 | 780
| 200mm copper 90 deg bend | ea | 1 | 420 | 420
| 200mm copper connection point | ea | 1 | 800 | 800
| 125 HDPE PN16 SDR11 - BLUELINE | m | 236.88 | 34.5 | 8172.36 | 237 | ADOPTED qty per QUANTITY_RECONCILIATION TPS_Site (vector-verified H003) - CW spine 236.88 m
| 75 HDPE PE100 PN 16 -Blueline | m |  | 12.31 | 0
| 63 HDPE PE100 PN 16 -Blueline | m |  | 9.66 | 0
| 63 HDPE PN12.5 SDR11 - BLUELINE | m |  | 4.63 | 0
| 50 HDPE PE100 PN 16 - BLUELINE | m |  | 5.4 | 0
| 40 HDPE PE100 PN16 Blue Line | m |  | 4.4 | 0
| 40 HDPE PN12.5 SDR11 - BLUELINE | m |  | 2.3621 | 0
| 32 HDPE PE100 PN 16 -Blueline | m | 37.26 | 2.1 | 78.246 | 38 | ADOPTED qty per QUANTITY_RECONCILIATION TPS_Site (vector-verified H003) - 32 PE 37.26 m (O25->32 convention, Opens #11)
| 25 HDPE PE100 PN16 - BLUELINE | m | 74.25 | 1.22 | 90.585 | 75 | ADOPTED qty per QUANTITY_RECONCILIATION TPS_Site (vector-verified H003) - 25 PE 74.25 m (O20->25 convention - no O20 item exists)
| 25 HDPE PN12.5 SDR11 - BLUELINE | m |  | 2.43 | 0
| EF COUPLER 125MM (EA) | m |  | 1.38 | 0
| TEE EQUAL PE100 E/F 125MM | ea | 8 | 22 | 176
| TEE PE100 E/F 125*63MM | ea |  | 57.75 | 0
| EF REDUCER 125 X 90MM | ea |  | 139 | 0
| EF REDUCER 125 X 63MM | ea |  | 104.15 | 0
| EF REDUCER 75 X 63MM | ea |  | 26.1 | 0
| EF REDUCER 63 X 50MM | ea |  | 37.5 | 0
| EF REDUCER 50 X 40MM | ea |  | 35.93 | 0
| EF REDUCER 40 X 32MM | ea |  | 35 | 0
| EF REDUCER 40 X 25MM | ea |  | 35 | 0
| EF REDUCER 32 X 25MM | ea | 2 | 35 | 70
| ELBOW PE100 E/F 125MM X 45D | ea | 2 | 20 | 40
| ELBOW PE100 E/F 125MM X 90D | ea | 5 | 50 | 250
| HDPE 75mm X 90 D ELBOW | ea |  | 54 | 0
| HDPE 63MM X 90 D ELBOW | ea |  |  | 0
| HDPE 50MM X 90 D ELBOW | ea |  | 15.55 | 0
| HDPE 40MM X 90 D ELBOW | ea |  | 15 | 0
| Reducing Tee 125mm x 90mm | ea |  | 10.87 | 0
| Reducing Tee 125mm x 32mm | ea | 3 | 55 | 165
| 125mm x 25mm reducing Tee | ea | 1 | 35 | 35
| Reducing Tee 75mm x 63mm | ea |  | 55 | 0
| Reducing Tee 75mm x 50mm | ea |  | 35 | 0
| Reducing Tee 75mm x 32mm | ea |  | 35 | 0
| Reducing Tee 63mm x 32mm | ea |  | 35 | 0
| Reducing Tee 50mm x 40mm | ea |  | 35 | 0
| Reducing Tee 40mm x 25mm | ea |  | 35 | 0
| Reducing Tee 32mm x 25mm | ea |  | 35 | 0
| EF Reducer 50mm x 25mm | ea |  | 35 | 0
| 50mm Tee | ea |  | 26 | 0
| 40mm Tee | ea |  | 35 | 0
| 32mm Tee | ea |  | 10.87 | 0
| HDPE 32mm X 90 D ELBOW | ea | 2 | 35 | 70
| HDPE 25mm X 90 D ELBOW | ea | 1 | 20 | 20
| HDPE 25mm X 45 D ELBOW | ea |  | 20 | 0
| 25mm Tee | ea | 2 | 25 | 50
| PE MAXI STUB FLANGE W/SS BK RING 125X 4" (EA) | ea |  | 35 | 0
| SLUICE VALVE PN16 T/D ACC FLNGD 100MM | ea |  | 102.5 | 0
| Valve Box - Cast Iron - Rectangle - Large - HD | ea |  | 235 | 0
| SADDLE TAPPING EF 125PE X 25PE | ea |  | 100 | 0
| SADDLE TAPPING EF 125PE X 32PE | ea | 1 | 47.41 | 47.41
| SADDLE TAPPING EF 125PE X 63PE | ea |  | 41.69 | 0
|  | ea |  | 85.55 | 0
0
| Detectable WATER Marker Tape - 250m | ea |  | 70 | 0
| WIPES WELDING PLASSON XL (120 PK) | ea |  | 19 | 0
| Paint Pen - WHITE | ea |  | 16 | 0
| 100 Cu Above Grnd | m |  | 40.21 | 0
| 50 Cu Above Grnd | m |  | 32 | 0
| 32 Cu Above Grnd | m |  | 19.98 | 0
| 32mm x25mm reducing tee | ea |  | 16.33 | 0
| 25 Cu Above Grnd | m |  | 17.52 | 0
| B-PRESS WATER EQUAL TEE 32MM (EA) | ea |  | 15 | 0
| B-PRESS WATER ELBOW 90DEG X 25MM (EA) | ea |  | 7.17 | 0
| B-PRESS WATER EQUAL TEE 25MM (EA) | ea |  | 13.6667 | 0
| 20 Cu Above Grnd | m |  | 13.6667 | 0
| B-PRESS WATER EQUAL TEE 20MM (EA) | ea |  | 6.88 | 0
| 50mm Cu 10mm Nut Clip | ea |  | 1.4 | 0
| 32mm Cu 10mm Nut Clip | ea |  | 1.38 | 0
| 25mm Cu 10mm Nut Clip | ea |  | 1.32 | 0
| 20mm Cu 10mm Nut Clip | ea |  | 1.24 | 0
| 10mm Zinc Threaded Rod | m |  | 5.1 | 0
0
0
| Kembla copper WATER ELBOW 90DEG X 32MM (EA) | ea |  | 14.31 | 0
| Kembla copper WATER ELBOW 90DEG X 25MM | ea |  | 4.58 | 0
| Kembla copper WATER ELBOW 90DEG X 20MM | ea |  | 4.58 | 0
0
0
0
HIDDEN |  |  |  |  | 0
| 63mm E/F PE 90 Deg Elb |  |  |  | 0
| 63mm E/F PE 45 Deg Elb | ea |  | 13.5 | 0
| 63mm E/F PE TEE | ea |  | 13.5 | 0
| 63x40x63 E/F PE TEE | ea |  | 9.5 | 0
| 63x32x63 E/F PE TEE | ea |  | 18.5 | 0
| 63x25x63 E/F PE TEE | ea |  | 18.5 | 0
| 63mm E/F PE Coupling | ea |  | 6 | 0
| 63x40 E/F PE Reducer Coupling | ea |  | 5.5 | 0
| 63x32 E/F PE Reducer Coupling | ea |  | 17.5 | 0
| 63x25 E/F PE Reducer Coupling | ea |  | 16.5 | 0
| 63PEx50Fi E/F PE Adapter | ea |  | 2.5 | 0
| 63PEx50Mi E/F PE Adapter | ea |  | 43.5 | 0
| 63PEx50Fi E/F PE Tramsiton Union | ea |  | 43.5 | 0
| 63PEx50Mi E/F PE Transition Union | ea |  | 45.5 | 0
| 40mm E/F PE 90 Deg Elb | ea |  | 76 | 0
| 40mm E/F PE 45 Deg Elb | ea |  | 11.5 | 0
| 40mm E/F PE TEE | ea |  | 11.5 | 0
| 40x32x40 E/F PE TEE | ea |  | 12 | 0
| 40x25x40 E/F PE TEE | ea |  | 18.5 | 0
| 40mm E/F PE Coupling | ea |  | 19.5 | 0
| 40x32 E/F PE Reducer Coupling | ea |  | 4.5 | 0
| 40x25 E/F PE Reducer Coupling | ea |  | 10.5 | 0
| 40PEx32Fi E/F PE Adapter | ea |  | 14.5 | 0
| 40PEx32Mi E/F PE Adapter | ea |  | 28.5 | 0
| 40PEx32Fi E/F PE Tramsiton Union | ea |  | 29.5 | 0
| 40PEx32Mi E/F PE Transition Union | ea |  | 36 | 0
| 32mm E/F PE 90 Deg Elb | ea |  | 54 | 0
| 32mm E/F PE 45 Deg Elb | ea |  | 10.5 | 0
| 32mm E/F PE TEE | ea |  | 10 | 0
| 32x25x32 E/F PE TEE | ea |  | 5.5 | 0
| 32mm E/F PE Coupling | ea |  | 18 | 0
| 32x25 E/F PE Reducer Coupling | ea |  | 4.5 | 0
| 32PEx25Fi E/F PE Adapter | ea |  | 6.5 | 0
| 32PEx25Mi E/F PE Adapter | ea |  | 25.5 | 0
| 32mm E/F PE End Cap | ea |  | 22.5 | 0
| 32mm E/F PE End Plug | ea |  | 8.5 | 0
| 25mm E/F PE 90 Deg Elb | ea |  | 6.5 | 0
| 25mm E/F PE 45 Deg Elb | ea |  | 10.5 | 0
| 25mm E/F PE TEE | ea |  | 0 | 0
| 25mm E/F PE Coupling | ea |  | 4.5 | 0
| 25PEx25Fi E/F PE Adapter | ea |  | 4 | 0
| 25PEx25Mi E/F PE Adapter | ea |  | 17 | 0
| 25PEx20Fi E/F PE Adapter | ea |  | 17.5 | 0
| 25PEx20Mi E/F PE Adapter | ea |  | 4.5 | 0
| 25mm E/F PE End Cap | ea |  | 2 | 0
| 25mm E/F PE End Plug | ea |  | 8.5 | 0
HIDDEN |  | ea |  | 4 | 0
| 100mm CU Crimp 90 DEG FxF Elbow |  |  |  | 0
| 100mm CU Crimp 45 DEG FxF Elbow | ea |  | 137 | 0
| 100mm CU Crimp Tee | ea |  | 139.5 | 0
| 100x50x100 CU Crimp Tee | ea |  | 183 | 0
| 100x50 CU Crimp Reducer | ea |  | 184.5 | 0
| 100mm CU Crimp Repair Coupling | ea |  | 56 | 0
| 100mm CU Crimp Coupling | ea |  | 103 | 0
| 100Cu x 100Flange CU Crimp Coupling | ea |  | 95 | 0
| 50mm CU Crimp 90 DEG FxF Elbow | ea |  | 99.5 | 0
| 50mm CU Crimp 45 DEG FxF Elbow | ea |  | 33.5 | 0
| 50mm CU Crimp Tee | ea |  | 33 | 0
| 50x40x50 CU Crimp Tee | ea |  | 60.5 | 0
| 50x40x40 CU Crimp Tee | ea |  | 61 | 0
| 50x32x50 CU Crimp Tee | ea |  | 65 | 0
| 50x32x32 CU Crimp Tee | ea |  | 65 | 0
| 50x32x40 CU Crimp Tee | ea |  | 65 | 0
| 50x25x50 CU Crimp Tee | ea |  | 65 | 0
| 50x20x50 CU Crimp Tee | ea |  | 45 | 0
| 50x15x50 CU Crimp Tee | ea |  | 55 | 0
| 50x40 CU Crimp Reducer | ea |  | 55 | 0
| 50x32 CU Crimp Reducer | ea |  | 21.5 | 0
| 50x25 CU Crimp Reducer | ea |  | 25 | 0
| 50x20 CU Crimp Reducer | ea |  | 22 | 0
| 50x15 CU Crimp Reducer | ea |  | 22 | 0
| 50Cu x 50Mi CU Crimp Adapter | ea |  | 22 | 0
| 50Cu x 50Fi CU Crimp Adapter | ea |  | 78 | 0
| 50mm CU Crimp Repair Coupling | ea |  | 89 | 0
| 50mm CU Crimp Coupling | ea |  | 21 | 0
| 50Cu x 50Flange CU Crimp Coupling | ea |  | 21 | 0
| 50mm CU Crimp Cap | ea |  | 0 | 0
| 50Cu x W69/Barrell Barrell Union CU Crimp | ea |  | 0 | 0
| 40mm CU Crimp 90 DEG FxF Elbow | ea |  | 0 | 0
| 40mm CU Crimp 45 DEG FxF Elbow | ea |  | 0 | 0
| 40mm CU Crimp 90 DEG MxF Elbow | ea |  | 0 | 0
| 40mm CU Crimp 45 DEG MxF Elbow | ea |  | 0 | 0
| 40mm CU Crimp Tee | ea |  | 0 | 0
| 40x32x40 CU Crimp Tee | ea |  | 0 | 0
| 40x32x32 CU Crimp Tee | ea |  | 0 | 0
| 40x32x25 CU Crimp Tee | ea |  | 0 | 0
| 40x25x40 CU Crimp Tee | ea |  | 0 | 0
| 40x25x20 CU Crimp Tee | ea |  | 0 | 0
| 40x20x40 CU Crimp Tee | ea |  | 0 | 0
| 40x15x40 CU Crimp Tee | ea |  | 0 | 0
| 40x32 CU Crimp Reducer | ea |  | 0 | 0
| 40x25 CU Crimp Reducer | ea |  | 0 | 0
| 40x20 CU Crimp Reducer | ea |  | 0 | 0
| 40x15 CU Crimp Reducer | ea |  | 0 | 0
| 40Cu x 40Mi CU Crimp Adapter | ea |  | 0 | 0
| 40Cu x 40Fi CU Crimp Adapter | ea |  | 0 | 0
| 40mm CU Crimp Repair Coupling | ea |  | 0 | 0
| 40mm CU Crimp Coupling | ea |  | 0 | 0
| 40Cu x 40Flange CU Crimp Coupling | ea |  | 0 | 0
| 40mm CU Crimp Cap | ea |  | 0 | 0
| 40Cu x W69/Barrell Barrell Union CU Crimp | ea |  | 0 | 0
| 32mm CU Crimp 90 DEG FxF Elbow | ea |  | 0 | 0
| 32mm CU Crimp 45 DEG FxF Elbow | ea |  | 0 | 0
| 32mm CU Crimp 90 DEG MxF Elbow | ea |  | 0 | 0
| 32mm CU Crimp 45 DEG MxF Elbow | ea |  | 0 | 0
| 32mm CU Crimp Tee | ea |  | 0 | 0
| 32x25x32 CU Crimp Tee | ea |  | 18.54 | 0
| 32x25x20 CU Crimp Tee | ea |  | 0 | 0
| 32x20x32 CU Crimp Tee | ea |  | 0 | 0
| 32x20x20 CU Crimp Tee | ea |  | 18.35 | 0
| 32x20x15 CU Crimp Tee | ea |  | 0 | 0
| 32x15x32 CU Crimp Tee | ea |  | 0 | 0
| 32x15x25 CU Crimp Tee | ea |  | 0 | 0
| 32x15x20 CU Crimp Tee | ea |  | 0 | 0
| 32x15x15 CU Crimp Tee | ea |  | 0 | 0
| COUPLING RED CU KEMPRESS WATER 32MM X 25MM | ea |  | 0 | 0
| 32x20 CU Crimp Reducer | ea |  | 16.33 | 0
| 32x15 CU Crimp Reducer | ea |  | 0 | 0
| 32Cu x 32Mi CU Crimp Adapter | ea |  | 0 | 0
| 32Cu x 32Fi CU Crimp Adapter | ea |  | 0 | 0
| 32mm CU Crimp Repair Coupling | ea |  | 0 | 0
| 32mm CU Crimp Coupling | ea |  | 0 | 0
| 32mm CU Crimp Cap | ea |  | 0 | 0
| 32Cu x W69/Barrell Barrell Union CU Crimp | ea |  | 0 | 0
| 25mm CU Crimp 90 DEG FxF Elbow | ea |  | 0 | 0
| 25mm CU Crimp 45 DEG FxF Elbow | ea |  | 0 | 0
| 25mm CU Crimp 90 DEG MxF Elbow | ea |  | 0 | 0
| 25mm CU Crimp 45 DEG MxF Elbow | ea |  | 0 | 0
| 25mm CU Crimp Tee | ea |  | 0 | 0
| 25x20x25 CU Crimp Tee | ea |  | 0 | 0
| 25x20x20 CU Crimp Tee | ea |  | 0 | 0
| 25x20x15 CU Crimp Tee | ea |  | 0 | 0
| 25x15x25 CU Crimp Tee | ea |  | 0 | 0
| 25x15x20 CU Crimp Tee | ea |  | 0 | 0
| 25x15x15 CU Crimp Tee | ea |  | 0 | 0
| 25x20 CU Crimp Reducer | ea |  | 0 | 0
| 25x15 CU Crimp Reducer | ea |  | 0 | 0
| 25Cu x 25Mi CU Crimp Adapter | ea |  | 0 | 0
| 25Cu x 25Fi CU Crimp Adapter | ea |  | 0 | 0
| 25mm CU Crimp Repair Coupling | ea |  | 0 | 0
| 25mm CU Crimp Coupling | ea |  | 0 | 0
| 25mm CU Crimp Cap | ea |  | 0 | 0
| 25Cu x W69/Barrell Barrell Union CU Crimp | ea |  | 0 | 0
| 20mm CU Crimp 90 DEG FxF Elbow | ea |  | 0 | 0
| 20mm CU Crimp 45 DEG FxF Elbow | ea |  | 0 | 0
| 20mm CU Crimp 90 DEG MxF Elbow | ea |  | 0 | 0
| 20mm CU Crimp 45 DEG MxF Elbow | ea |  | 0 | 0
| 20mm CU Crimp Tee | ea |  | 0 | 0
| 20x15x20 CU Crimp Tee | ea |  | 5.61 | 0
| 20x15x15 CU Crimp Tee | ea |  | 0 | 0
| 20x15 CU Crimp Reducer | ea |  | 0 | 0
| 20Cu x 20Mi CU Crimp Adapter | ea |  | 0 | 0
| 20Cu x 20Fi CU Crimp Adapter | ea |  | 0 | 0
| 20mm CU Crimp Repair Coupling | ea |  | 0 | 0
| 20mm CU Crimp Coupling | ea |  | 0 | 0
| 20mm CU Crimp Cap | ea |  | 0 | 0
| 20Cu x W69/Barrell Barrell Union CU Crimp | ea |  | 0 | 0
| 15mm CU Crimp 90 DEG FxF Elbow | ea |  | 0 | 0
| 15mm CU Crimp 45 DEG FxF Elbow | ea |  | 0 | 0
| 15mm CU Crimp 90 DEG MxF Elbow | ea |  | 0 | 0
| 15mm CU Crimp 45 DEG MxF Elbow | ea |  | 0 | 0
| 15mm CU Crimp Tee | ea |  | 0 | 0
| 15Cu x 15Mi CU Crimp Adapter | ea |  | 0 | 0
| 15Cu x 15Fi CU Crimp Adapter | ea |  | 0 | 0
| 15Cu Fi BP, wall elbow | ea |  | 0 | 0
| 15Cu Mi BP, Wall elbow - 90 Long | ea |  | 0 | 0
| 15Cu Mi BP, Wall elbow - 120+ Long | ea |  | 0 | 0
| 15mm CU Crimp Repair Coupling | ea |  | 0 | 0
| 15mm CU Crimp Coupling | ea |  | 0 | 0
| 15mm CU Crimp Cap | ea |  | 0 | 0
| 15Cu x W69/Barrell Barrell Union CU Crimp | ea |  | 0 | 0
| 50mm Ball Valve Fi | ea |  | 0 | 0
| 40mm Ball Valve Fi | ea |  | 0 | 0
| 32mm Ball Valve Fi | ea |  | 0 | 0
| 25mm Ball Valve Fi | ea |  | 26.25 | 0
| 20mm Ball Valve Fi | ea |  | 0 | 0
| 15mm Ball Valve Fi | ea |  | 0 | 0
| 50mm Mi BRS Nipple | ea |  | 0 | 0
| 50mm Fi BRS Socket | ea |  | 0 | 0
| 50mm Mi BRS Union | ea |  | 0 | 0
| 50mm Fi BRS Union | ea |  | 0 | 0
| 50mm BRS Plug | ea |  | 0 | 0
| 50mm BRS Cap | ea |  | 0 | 0
| 40mm Mi BRS Nipple | ea |  | 0 | 0
| 40mm Fi BRS Socket | ea |  | 0 | 0
| 40mm Mi BRS Union | ea |  | 0 | 0
| 40mm Fi BRS Union | ea |  | 0 | 0
| 40mm BRS Plug | ea |  | 0 | 0
| 40mm BRS Cap | ea |  | 0 | 0
| 32mm Mi BRS Nipple | ea |  | 0 | 0
| 32mm Fi BRS Socket | ea |  | 0 | 0
| 32mm Mi BRS Union | ea |  | 0 | 0
| 32mm Fi BRS Union | ea |  | 0 | 0
| 32mm BRS Plug | ea |  | 0 | 0
| 32mm BRS Cap | ea |  | 0 | 0
| 25mm Mi BRS Nipple | ea |  | 0 | 0
| 25mm Fi BRS Socket | ea |  | 0 | 0
| 25mm Mi BRS Union | ea |  | 0 | 0
| 25mm Fi BRS Union | ea |  | 0 | 0
| 25mm BRS Plug | ea |  | 0 | 0
| 25mm BRS Cap | ea |  | 0 | 0
|  | ea |  | 0 | 0
| 20mm pex Pipe - Black |  |  | 0 | 0
| 15mm Pex pipe - Black | m |  | 0 | 0
| 15mm Pex pipe - Red | m |  | 0 | 0
| 20 pex Elbow | m |  | 0 | 0
| 20 Pex TEE | ea |  | 0 | 0
| 20x15 Pex TEE | ea |  | 0 | 0
| 20 PEX Mi Adapter | ea |  | 0 | 0
| 20 PEX Fi Adapter | ea |  | 0 | 0
| 20x15 Pex Reducer | ea |  | 0 | 0
| 20 PEXxCU Crimp conversion coupling | ea |  | 0 | 0
| 20 PEX Straight coupling | ea |  | 0 | 0
| 15 Pex Elbow | ea |  | 0 | 0
| 15 Pex TEE | ea |  | 0 | 0
| 15 PEXMi Adapter | ea |  | 0 | 0
| 15 PEX Fi Adapter | ea |  | 0 | 0
| 15 PEX Fi BP, wall elbow | ea |  | 0 | 0
| 15 PEX Mi BP, Wall elbow - 90 Long | ea |  | 0 | 0
| 15 PEX Mi BP, Wall elbow - 120+ Long | ea |  | 0 | 0
| 15 PEXxCU Crimp conversion coupling | ea |  | 0 | 0
| 15 PEX Straight coupling | ea |  | 0 | 0
|  | ea |  | 0 | 0
| Hose Taps Complete | ea | 1 | 56 | 56
| 200mm x 8 Inch Full Faced Stub & Stainless Backing Ring AS4087 | ea | 6 | 472.44 | 2834.64
| 200 FL DICL Sluice Valve | ea | 3 | 679 | 2037
| 200 SS Gasket Kit EPDM DI-DI | ea | 6 | 47 | 282
| 100 FL DICL SLUICE VALVE | ea | 6 | 202.94 | 1217.64
| 100mm check valve | ea | 6 | 880 | 5280
| 125PE*4" (100mm) - MaxiStub W/Stainless Steel Backing Ring | ea | 12 | 92.67 | 1112.04
| 100mm PE*DI Gasket Kit Complete Parts & Labour | ea | 6 | 24.71 | 148.26
| 100mm DI*DI Gasket Kit Complete | ea | 6 | 20 | 120
| Valve Spindle Riser - 600Long | ea |  | 136.94 | 0
| 100mm Dual Pillar Hydrant Complete_ RG Base 1500 High w/landing Valves_OPTION | ea |  | 365 | 0
| 125mm PE x 100mm GALV ADAPTER - Acutech Brand | ea |  | 201.43 | 0
| Red caps and chain - suit 65mm QLD Landing valve | ea |  | 5 | 0
| RPZD 32mm | ea |  | 853 | 0
| RPZD 20mm | ea |  | 503 | 0
| RPZD 100mm | ea |  | 1809.63 | 0
| Office - Water & Rough IN | ea |  | 1650 | 0
| Ofice - NOGINS & Fixings | ea |  | 160 | 0
| Safety shr fittings | ea |  | 750 | 0
| In Grnd Fittings misc | ea |  | 450 | 0
| Abv Grnd Fittings misc | ea |  | 1250 | 0
| HWU quickie kit | ea |  | 190 | 0
| TMV | ea |  | 412.59 | 0
| TMV1 AQUABLEND 1000 (ATM710 | ea |  | 284.07 | 0
| TMV 2 AQUABLEND 1000 (ATMS710H-350) | ea |  | 502.1 | 0
| 25mm Isolavtive valve | ea | 1 | 70 | 70
| 20mm Isolavtive valve | ea |  | 50 | 0
| 450 SQ PIT | ea |  | 30 | 0
| Dock Office Water Mat | ea |  | 1850 | 0
| 25mm RPZD | ea |  | 1800 | 0
| misc. | ea |  | 3800 | 0
| 150mm isolation valve in valve pit (connect to authority watermain ) | ea |  | 371.37 | 0
| 100mm fire water meter assembly and 100mm cold water water assembly | ea | 1 | 5500 | 5500 | 0.5 | ADOPTED 1 EA - legend groups BOTH assemblies as one item; price as two assemblies under one item (Denis carried 0.5)
| 25mm DCW Isolation vlave in valve pit with path box cover | ea |  | 469.04 | 0
| 25mm water meter in tamper steel cage with isolative valves in both side | ea |  | 659.8 | 0
| TMV in Box | ea |  | 587.96 | 0
| 100 mm Water meter | ea |  | 641.58 | 0
| 32 valve in pit | ea |  | 50 | 0
| 32 mm water cap | ea | 2 | 15 | 30
| 25mm water cap | ea | 1 | 12 | 12
| 50mm control valve | ea |  | 31.71 | 0
| TLV under basin | ea |  | 146.09 | 0
| AUTOMATIC TRAP PRIMER | ea |  | 99.49 | 0
SEWER DRAINAGE -
Description
| PIPE DWV PVC S/WELD 150MM - In Grnd | m | 29.29 | 14.49 | 424.4121 | 30 | ADOPTED qty per QUANTITY_RECONCILIATION TPS_Site (vector-verified H003) - 150 DWV authority leg 29.29 m
| PIPE DWV SN8 PVC S/WELD 100MM | m | 178.24 | 9.5496 | 1702.1207 | 179 | ADOPTED qty per QUANTITY_RECONCILIATION TPS_Site (vector-verified H003) - 100 DWV gravity sewer 178.24 m
| 150MM * 45D PVC JUNCTION | ea |  | 9.66 | 0
| 100MM * 45D PVC JUNCTION | ea |  | 4.7886 | 0
| 150MM X 100MM 45D PVC JUNCTION | ea |  | 13.8 | 0
| 100*50 PVC DWV JUNCTION | ea |  | 6.5274 | 0
| 100MM * 65 PVC PVC JUNCTION | ea |  | 8.5974 | 0
| 150MM X 45 Deg Bend | ea |  | 6.9 | 0
| 150MM X 90 Deg Bend | ea |  | 6.9 | 0
| 100MM X 90Deg Bend | ea | 3 | 2.5668 | 7.7004
| 100MM X 45Deg Bend | ea | 6 | 2.3308 | 13.9849
| DWV PIPE REDUCER 150X100mm | ea |  | 5.52 | 0
| DWV PIPE REDUCER 100 X 50mm | ea |  | 2.6772 | 0
| PIPE DWV PVC S/WELD 100MM - In Grnd | m |  | 6.9 | 0
| PIPE DWV PVC S/WELD 65MM - In Grnd | m |  | 5.52 | 0
| 63 HDPE PN12.5 SDR11 - BLACK or CREAM - In Grnd | m |  | 8.7354 | 0
| PIPE DWV PVC S/WELD 50mm | m |  | 3.726 | 0
| PIPE DWV PVC S/WELD 40mm | m |  | 2.898 | 0
| DWV BEND 65X 90 DEG | ea |  | 2.3322 | 0
| DWV BEND 40 X 85 DEG | ea |  | 4.14 | 0
| DWV BEND 50 X 45 DEG | ea |  | 0.9384 | 0
| DWV BEND 50 X85 DEG | ea |  | 11.7162 | 0
| 50mm Condensate INSULATION | m |  | 14 | 0
| 100mm Condensate INSULATION | m |  | 6 | 0
0
| 150mm - Gas Tight H/D Cast Iron Clearout (Peepeye) | ea |  | 40 | 0
| 150mm Clear Out Cover - L/D - Brass | ea |  | 30 | 0
| 100mm - Gas Tight H/D Cast Iron Clearout (Peepeye) | ea |  | 33 | 0
| 100mm Clear Out Cover - L/D - Brass | ea |  | 23.26 | 0
| 100 mm Inspection Opening | ea |  | 50 | 0
| 100mm Trapped point - 100mm Gully Trap | ea |  | 7.65 | 0
| FWG - 100mm Gully Trap | ea |  | 7.65 | 0
| FWG - 100mm 4-way Riser | ea |  | 13.59 | 0
| FWG - Grate - Tile Insert 100*100 Chrome Plated | ea |  | 0 | 0
| In-Wall TD & View Panel - SS | ea |  | 75 | 0
0
| 100mm PVC 10mm nut hanging clip | ea |  | 2 | 0
| 50mm PVC 10mm nut hanging clip | ea |  | 1.5 | 0
| 10mm Zinc Threaded Rod | m |  | 0 | 0
0
| Glue - Blue - 4Ltr | ea |  | 26.4 | 0
| Primer - Red - 4Ltr | ea |  | 23 | 0
| Detectable SEWER Marker Tape - 250m | ea |  | 75 | 0
| 100mm AbleFlex Roll | ea |  | 22 | 0
| Concrete Mix bag | ea |  | 10 | 0
0
| External Sewer Mains fitting | ea |  | 520 | 0
| Vents Complete | ea |  | 230 | 0
| Office Drainage mat | ea |  | 2800 | 0
| Dock Office Drainage Mat | ea |  | 950 | 0
| misc. | ea |  | 1250 | 0
| Overflow Gully | ea |  | 200 | 0
| Tundish with HT | ea |  | 60 | 0
| COS | ea |  | 120 | 0
| Tundish | ea |  | 61.33 | 0
| SIVEL EXPANSION JOINT | ea |  | 100 | 0
| FWG-130x130 STAINLESS STEEL GRATE WITH 80Ø VERTICAL OUTLET. SPS MODEL Q130/80SR | ea |  | 250 | 0
| FWG/BT - 200x200 PUSH IN BASKET TRAP WITH 316 STAINLESS STEEL GRATE CLASS 'C' SPS MODEL Q200 SR6-BT WITH FIXED SECONDARY STRAINER | ea |  | 250 | 0
| Fire Collars & Misc | ea |  | 300 | 0
| plaster /slip trap | ea |  | 1200 | 0
| Material for 150mm sewer property connection | ea | 1 | 900 | 900
| sewer maintenance shaft | ea | 2 | 5250 | 10500
Trade Waste
Description
| Geberit Hdpe Pipe 110mm | m | 16.28 | 17 | 276.76 | 17 | ADOPTED qty per QUANTITY_RECONCILIATION TPS_Site (vector-verified H003) - 110 HDPE trade waste 16.28 m
STORMWATER DRAINAGE
Description
| PIPE 600MM - RIBBED | m |  | 165.6 | 0
| PIPE 450MM - RIBBED | m |  | 89.7 | 0
| PIPE 375MM - RIBBED BLACK MAX | m |  | 66.24 | 0
| PIPE 300MM - RIBBED BLACK MAX | m |  | 0 | 0
| PIPE DWV SN8 PVC S/WELD 375MM | m |  | 85.1046 | 0
| PIPE DWV SN8 PVC S/WELD 300MM | m |  | 84.18 | 0
| PIPE DWV SN4 PVC S/WELD 300MM | m |  | 68.77 | 0
| PIPE SW H/D PVC S/WELD 300MM | m |  | 55.2 | 0
| PIPE DWV SN8 PVC S/WELD 225MM | m | 6.91 | 55.2 | 381.432 | 7 | ADOPTED qty per QUANTITY_RECONCILIATION TPS_Site (vector-verified H003) - 225 DWV storm connection stubs 6.91 m (stubs only - runs are TCS line 81, interface L2)
| PIPE DWV SN4 PVC S/WELD 225MM | m |  | 42.78 | 0
| PIPE SW H/D PVC S/WELD 225MM | m |  | 32.66 | 0
| PIPE DWV SN8 PVC S/WELD 150MM | m |  | 19.55 | 0
| PIPE DWV SN4 PVC S/WELD 150MM | m |  | 16.1 | 0
| PIPE DWV SN8 PVC S/WELD 150MM - Suspended | m |  | 19.55 | 0
| PIPE DWV SN4 PVC S/WELD 150MM | m |  | 16.56 | 0
| PIPE DWV SN8 PVC S/WELD 100MM | m |  | 6.693 | 0
| PIPE DWV SN4 PVC S/WELD 100MM | m |  | 6.9 | 0
| PIPE DWV SN8 PVC S/WELD 50MM | m |  | 6.693 | 0
|  |  |  | 0 | 0
| DWV Grade Option |  |  | 0 | 0
|  | ea |  | 0 | 0
| 600*225 Ribbed Saddle | ea |  | 676.2 | 0
| 600*45Deg RIBBED Bend | ea |  | 897 | 0
| 600*450 Ribbed Reducer | ea |  | 1518 | 0
| 450*375 Ribbed*PVC Reducer | ea |  | 634.8 | 0
| 450 45 Deg ribbed Bend | ea |  | 800.4 | 0
| 450 * 225 Ribbed Saddle | ea |  | 441.6 | 0
| 375mm X 45Deg Junction | ea |  | 579.6 | 0
| 375X300X45D PVC JUNCTION | ea |  | 776.0982 | 0
| 375X225X45D PVC JUNCTION | ea |  | 777.4782 | 0
| 375MM X 300MM Reducer | ea |  | 524.4 | 0
| 375MM X 225MM Reducer | ea |  | 496.8 | 0
| 375MM X 90Deg Bend | ea |  | 745.2 | 0
| 375MM X 45Deg Bend | ea |  | 621 | 0
| 300MM * 45D PVC JUNCTION | ea |  | 496.8 | 0
| 300X225X45D PVC JUNCTION | ea |  | 441.6 | 0
| 300MM X 225MM Reducer | ea |  | 262.2 | 0
| 300MM X 90Deg Bend | ea |  | 345 | 0
| 300MM X 45Deg Bend | ea |  | 262.2 | 0
| 300MM X 150 Junction | ea |  | 455.4 | 0
| 225MM * 45D PVC JUNCTION | ea |  | 117.645 | 0
| 225X150X45D PVC JUNCTION | ea |  | 289.8 | 0
| 225MM X 90Deg Bend | ea | 10 | 85.56 | 855.6
| 225MM X 45Deg Bend | ea |  | 84.18 | 0
| 225MM X 150MM Reducer | ea |  | 62.1 | 0
| 150 PVC DWV 45Deg Junct | ea |  | 24.84 | 0
| 150MM X 90Deg Bend | ea |  | 22.08 | 0
| 150MM X 45Deg Bend | ea |  | 16.56 | 0
| 150X100X45D PVC JUNCTION | ea |  | 22.08 | 0
| PVC PIPE REDUCER 150X 100 mm | ea |  | 22.08 | 0
| 100MM * 45D PVC JUNCTION | ea |  | 6.486 | 0
| 100X50 X45D PVC JUNCTION | ea |  | 22.08 | 0
| PVC PIPE REDUCER 100X 50 mm | ea |  | 22.08 | 0
| 100MM X 90Deg Bend | ea |  | 16.56 | 0
| 100MM X 45Deg Bend | ea |  | 16.56 | 0
| 50 PVC X 45D PVC JUNCTION | ea |  | 19.32 | 0
| 50MM X 90Deg PVC Bend | ea |  | 0.897 | 0
| 50MM X 45Deg PVC Bend | ea |  | 0.897 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
| 150mm PVC 10mm nut hanging clip | ea |  | 2.622 | 0
| 10mm Zinc Threaded Rod | m |  | 2.76 | 0
| Glue - Blue - 4Ltr | ea |  | 36.432 | 0
| Primer - Red - 4Ltr | ea |  | 31.74 | 0
|  |  |  | 0 | 0
| SW_RRJ (RIBBED) Fittings |  |  | 0 | 0
|  |  |  | 0 | 0
| 375MM X 45Deg Bend | ea |  | 362.1396 | 0
| DN 375 X DN150 45 DEG BLACKMAX REDUCING JUNCTION (PVC FAB) | ea |  | 828 | 0
| DN375 x dn225 BlackMax® Reducing Adaptor FF RRJ x DWV SWJ (PVC Fab) | ea |  | 552 | 0
|  |  |  | 0 | 0
| DN 300 X DN150 45 DEG BLACKMAX REDUCING JUNCTION (PVC FAB) | ea |  | 690 | 0
| DN300 BLACK MAX 45 DEG BEND | ea |  | 414 | 0
| DN300 x dn225 BlackMax® Reducing Adaptor FF RRJ x DWV SWJ (PVC Fab) | ea |  | 414 | 0
| DN300 BLACK MAX 45 DEG BEND | ea |  | 414 | 0
|  | ea |  | 0 | 0
| 150mm Cap | ea |  | 20.7 | 0
| 150mm expansion coupler | ea |  | 110.4 | 0
| 450X450 GRATED SW GULLY | ea |  | 180 | 0
FITOFF
| Fit-Off Material; Ground & First Floor - | ea |  | 180 | 0
| Fit-Off Material; Ground & First Floor - | ea |  | 0 | 0
SUB TOTALS
379930.7656
|  |  |  | Contingency | 1.18
|  |  |  | Deliveries | 5000
TOTALS
453318.3034
Excavation/Quarry/Misc/ Takeoff.
|  | Qty | Unit
| Avrg Trench = .900D*.450W | 924.56 | m
| L/M Of Asphalt Reinstate | 0 | m
| M2 Of Asphalt Reinstate | 0 | m2
| L/M Of CBR Reinstate | 0 | m
| L/M of Inground Pipe (Average Depth) | 924.56 | m
| L/M of Inground Pipe (Deeper Than Average Depth) |  | m
| Avergage of trtenches 'Shared'…. Shared trench Factor | 0.1 | m
| SEWER / SW / TW - InGrnd |  | m | 0%
| WAT / FIRE - InGrnd |  | m | 0%
| SPK - InGrnd |  | m | 0%
|  | D | W | L | Spoil/Compact Factor; | Shared Trench Factor | Total m3 - EXCAVATED | Total M3 - Bed, Pipe, Cover reduction | Total M3 - Backfill Req (Less Bed&Pipe) | Total M3 - Spoil - REMOVE | TCS Load - Haulage & dump rate only
| L/M of Inground Pipe (Average Depth) | 0.95 | 0.6 | 924.56 | 1.3 | 0.1 | 632.399
| L/M of Inground Pipe (Deeper Than Average Depth) | 1.1 | 0.5 | 0 | 1.3 | 0 | 0
| L/M of Bed, Pipe, Cover material reduction (Average Depth) | 0.35 | 0.6 | 924.56 | 0 | 0.1 |  | 174.7418
| L/M of Bed, Pipe, Cover material reduction (Deeper Than Average Depth) | 0.2 | 0.5 | 0 | 0 | 0 |  | 0
| L/M of BACKFILL required (Average Depth) | 0.95 | 0.6 | 924.56 | 1.3 | 0.1 |  |  | 457.6572
| L/M of BACKFILL required (Deeper Than Average Depth) | 1.1 | 0.5 | 0 | 1.3 | 0 |  |  | 0
[10 empty] | QTY | Rate | Total
[7 empty] | 632.399 | 174.7418 | 457.6572 | 174.7418 | 15 | 2621.1276
| Thrust Block Concrete | m3/TB | Qty | Total m3 | Contingency | Total m3 | Total Cost
|  | 0.1 |  | 0 | 1.1 | 0 | 0
Quarry & Concrete Product
1.4
| Description | Unit/LM | Unit | Rate | Rate/LM |  |  | QTY | Shared Trench Factor | Total Req. | Total | Contingency | TOTAL | Drainage Use | Fire/WAT Use | SPK Use
| 5-7mm Stone | 0.203 | Ton | 62 | 12.586 |  |  | 187.6857 | 0.1 | 168.9171 | 10472.8609 | 4189.1444 | 14662.0053 | 0
| 5-7mm Stone | 0.14 | m3 | 62 | 16.926
| 10-12mm Stone | 0.45 | Ton | 62 | 27.9 |  |  | 0 |  |  | 0 |  | 0
| 80-110mm Stone | 0 | Ton | 25 | 0 |  |  | 0 |  |  | 0 |  | 0
| Medium River / Bed Sand | 0.225 | Ton | 62 | 13.95 |  |  | 208.026 | 0.1 | 187.2234 | 11607.8508 | 4643.1403 | 16250.9911 |  | 0 | 0
| Medium River / Bed Sand | 0.14 | m3 | 62 | 13.02
| CBR15 Road Base | 0.36 | Ton | 27 | 9.72 |  |  | 0 |  |  | 0 |  | 0
| CBR45 | 0.36 | Ton | 30 | 10.8 |  |  | 0 |  |  | 0 |  | 0
| LEANMIX | 0.3 | m3 | 0 | 0 |  |  | 0 |  |  | 0 |  | 0
|  |  |  | TCS | Q2
| Description |  | Unit | Rate | Rate
| 5-7mm Stone |  | T | 62 | 31
| 10-12mm Stone |  | T | 62 | 39
| 80-110mm Stone |  | T | 25 | 29
| Medium River / Bed Sand |  | T | 62 | 26
| CBR15 Road Base |  | T | 48 | 27
| CBR45 |  | T | 50 | 30
| LEANMIX_20mm-12:1 |  | M3 | 168 | 0
| Concrete_25/20/80 |  | M3 | 153 | 0

## LabourProject Rates_Master
Project:
Tricore -
Stage 1 Version 1
Item | [6 empty] | Source
BASED ON:
| Work ROSTER Example #3 - 6-Day Week, 10Hr Days, Stay @ Rocky for W/E, Return Every 2nd W/E. (FLY) | [5 empty] | frozen from [2] CQU ROK_Staff Costing.V1_Steph (2024 FIFO build) - link severed 26/07/26; re-based x1.08 below
| Working Days/Month | 21 |  |  |  |  | frozen from [2] CQU ROK_Staff Costing.V1_Steph (2024 FIFO build) - link severed 26/07/26; re-based x1.08 below
| No-Work Days/Month | 7 |  |  |  |  | frozen from [2] CQU ROK_Staff Costing.V1_Steph (2024 FIFO build) - link severed 26/07/26; re-based x1.08 below
| Avrg Hours / Month | 210 |  |  |  |  | frozen from [2] CQU ROK_Staff Costing.V1_Steph (2024 FIFO build) - link severed 26/07/26; re-based x1.08 below
STAFF
|  | Unit | REQ | Cost ex GST | Total ex GST
| TRADESMAN_LEADING HAND | HR | 1 | 132.9634 | 132.9634 |  | frozen from [2] CQU ROK_Staff Costing.V1_Steph (2024 FIFO build) - link severed 26/07/26; re-based x1.08 below
| ** for Roster Examples # 3 | DAY | 1 | 1329.6343 | 1329.6343
| TRADESMAN_LEADING HAND | WEEK | 1 | 6980.58 | 6980.58
|  | MONTH | 1 | 27922.32 | 27922.32 |  | LH monthly: $25,854 (frozen [2]) x 1.08 ROK uplift = $27,922.32 literal; hr/day/week formula-derived (/210, /21, /4) -> $132.9634/hr
| QTY Staff in Crew | 1
| TRADESMAN_PLUMBER_OPERATOR | HR | 1 | 101.6458 | 101.6458 |  | frozen from [2] CQU ROK_Staff Costing.V1_Steph (2024 FIFO build) - link severed 26/07/26; re-based x1.08 below
| ** for Roster Examples # 3 | DAY | 1 | 1016.4579 | 1016.4579
| TRADESMAN_PLUMBER_OPERATOR | WEEK | 1 | 5336.404 | 5336.404
|  | MONTH | 1 | 21345.616 | 21345.616 |  | Trades monthly: $19,764.4593 (frozen [2]) x 1.08 = $21,345.6160 literal -> $101.6458/hr
| QTY Staff in Crew | 1
| T/A & Apprentice | HR | 1 | 82.951 | 82.951 |  | frozen from [2] CQU ROK_Staff Costing.V1_Steph (2024 FIFO build) - link severed 26/07/26; re-based x1.08 below
| ** for Roster Examples # 3 | DAY | 1 | 829.5103 | 829.5103
| T/A & Apprentice | WEEK | 1 | 4354.929 | 4354.929
|  | MONTH | 1 | 17419.716 | 17419.716 |  | T/A monthly: $16,129.3667 (frozen [2]) x 1.08 = $17,419.7160 literal -> $82.9510/hr
| QTY Staff in Crew | 1
| Crew #1 - InGround Drainage | HR | 1 | 286.2426 | 286.2426
| ** for Roster Examples # 3 | DAY | 1 | 2862.4261 | 2862.4261
| TRADESMAN_PLUMBER_OPERATOR | WEEK | 1 | 15027.737 | 15027.737
| TRADESMAN_PLUMBER_OPERATOR | MONTH | 1 | 60110.9481 | 60110.9481
T/A & Apprentice
| QTY Staff in Crew | 3
| Crew #2 - InGround Water/Fire | HR | 1 | 286.2426 | 286.2426
| ** for Roster Examples # 3 | DAY | 1 | 2862.4261 | 2862.4261
| TRADESMAN_PLUMBER_OPERATOR | WEEK | 1 | 15027.737 | 15027.737
| TRADESMAN_PLUMBER_OPERATOR | MONTH | 1 | 60110.9481 | 60110.9481
T/A & Apprentice
| QTY Staff in Crew | 3
| Crew #3 - Above Ground Drainage | HR | 1 | 286.2426 | 286.2426
| ** for Roster Examples # 3 | DAY | 1 | 2862.4261 | 2862.4261
| TRADESMAN_PLUMBER_OPERATOR | WEEK | 1 | 15027.737 | 15027.737
| TRADESMAN_PLUMBER_OPERATOR | MONTH | 1 | 60110.9481 | 60110.9481
T/A & Apprentice
| QTY Staff in Crew | 3
| Crew #4 - Above Ground WATER/FIRE | HR | 1 | 286.2426 | 286.2426
| ** for Roster Examples # 3 | DAY | 1 | 2862.4261 | 2862.4261
| TRADESMAN_PLUMBER_OPERATOR | WEEK | 1 | 15027.737 | 15027.737
| TRADESMAN_PLUMBER_OPERATOR | MONTH | 1 | 60110.9481 | 60110.9481
T/A & Apprentice
| QTY Staff in Crew | 3
| Crew #5 - Above Ground FitOff / Misc | HR | 1 | 286.2426 | 286.2426
| ** for Roster Examples # 3 | DAY | 1 | 2862.4261 | 2862.4261
| TRADESMAN_PLUMBER_OPERATOR | WEEK | 1 | 15027.737 | 15027.737
| TRADESMAN_PLUMBER_OPERATOR | MONTH | 1 | 60110.9481 | 60110.9481
T/A & Apprentice
| QTY Staff in Crew | 3
| Crew #6 - DEMO | HR | 1 | 184.5968 | 184.5968
| ** for Roster Examples # 3 | DAY | 1 | 1845.9682 | 1845.9682
| TRADESMAN_PLUMBER_OPERATOR | WEEK | 1 | 9691.333 | 9691.333
| T/A & Apprentice | MONTH | 1 | 38765.332 | 38765.332
| QTY Staff in Crew | 2
`
| FULL team, FULL Duration, as per Program | HR | 0 | 705.4486 | 0
| ** for Roster Examples # 3 | DAY | 0 | 7054.4865 | 0
| Crew #1 - InGround Drainage | WEEK | 0 | 37036.054 | 0
| Crew #2 - InGround Water/Fire | MONTH | 4 | 148144.2162 | 592576.8647
TRADESMAN_LEADING HAND
| QTY Staff in Crew | 7
`
ACCOMODATION
|  | Unit | REQ | Cost | Total EX GST
| Full Apartment / TownHouse / Unit - VIA AGENT |  |  | *Changed to ex GST |  | 11
| ** for Roster Examples # 3 | NIGHT | 0 | 164.5022 | 0
|  | WEEK | 0 | 1151.5152 | 0
| TRADESMAN_PLUMBER_OPERATOR | MONTH | 0 | 4606.0606 | 0
TRADESMAN_PLUMBER_OPERATOR
T/A & Apprentice
| QTY Staff in Crew | 3
| Individual - PER PERSON |  |  | *Changed to ex GST |  | 11
| ** for Roster Examples # 3 | NIGHT | 0 | 103.2468 | 0
| TCS Cost Per Person - Private Unit - NO SHARE - Nightly Booking (average allowance) | WEEK | 0 | 722.7273 | 0
|  | MONTH | 0 | 2890.9091 | 0

## Material Rates_Master
FIRE SERVICES - IN GROUND
Description | Unit |  | Rate |  | Total |  |  | Qty |  |  |  | Source
200 HDPE PN16 SDR11 - REDLINE | m |  | 33.9208 |  | 16282 | COMPLETED don’t edit |  | 480 |  |  |  | frozen from [3] 240614 Pipe & Fittings Price Comparison (Jun-2024 cache) - link severed 26/07/26; >=2yr old at 2027 start - Phase 5 re-source pending
180 HDPE PN16 SDR11 - REDLINE | m |  | 25.4667 |  | 128657.6 |  |  | 5052 |  |  |  | frozen from [3] 240614 Pipe & Fittings Price Comparison (Jun-2024 cache) - link severed 26/07/26; >=2yr old at 2027 start - Phase 5 re-source pending
125 HDPE PN16 SDR11 - REDLINE | m |  | 12.3142 |  | 13151.53 |  |  | 1068 |  |  |  | frozen from [3] 240614 Pipe & Fittings Price Comparison (Jun-2024 cache) - link severed 26/07/26; >=2yr old at 2027 start - Phase 5 re-source pending
32 HDPE PN16 SDR11 - BLUELINE | m |  | 1.2159 |  | 121.59 |  |  | 100 |  |  |  | frozen from [3] 240614 Pipe & Fittings Price Comparison (Jun-2024 cache) - link severed 26/07/26; >=2yr old at 2027 start - Phase 5 re-source pending
200 EF Coupler | ea |  | 44.06 |  | 1321.8 | COMPLETED don’t edit |  | 30 |  |  |  | frozen from [3] 240614 Pipe & Fittings Price Comparison (Jun-2024 cache) - link severed 26/07/26; >=2yr old at 2027 start - Phase 5 re-source pending
180 EF Coupler | ea |  | 25.72 |  | 5144 |  |  | 200 |  |  |  | frozen from [3] 240614 Pipe & Fittings Price Comparison (Jun-2024 cache) - link severed 26/07/26; >=2yr old at 2027 start - Phase 5 re-source pending
125 EF Coupler | ea |  | 14.11 |  | 1411 |  |  | 100 |  |  |  | frozen from [3] 240614 Pipe & Fittings Price Comparison (Jun-2024 cache) - link severed 26/07/26; >=2yr old at 2027 start - Phase 5 re-source pending
200 EF 45DFeg Bend | ea |  | 109.16 |  | 218.32 |  |  | 2 |  |  |  | frozen from [3] 240614 Pipe & Fittings Price Comparison (Jun-2024 cache) - link severed 26/07/26; >=2yr old at 2027 start - Phase 5 re-source pending
180 EF 45DFeg Bend | ea |  | 97.97 |  | 12736.1 |  |  | 130 |  |  |  | frozen from [3] 240614 Pipe & Fittings Price Comparison (Jun-2024 cache) - link severed 26/07/26; >=2yr old at 2027 start - Phase 5 re-source pending
125 EF 45DFeg Bend | ea |  | 44.69 |  | 1117.25 | COMPLETED don’t edit |  | 25 |  |  |  | frozen from [3] 240614 Pipe & Fittings Price Comparison (Jun-2024 cache) - link severed 26/07/26; >=2yr old at 2027 start - Phase 5 re-source pending
200 EF 90DFeg Bend | ea |  | 109.16 |  | 654.96 |  |  | 6 |  |  |  | frozen from [3] 240614 Pipe & Fittings Price Comparison (Jun-2024 cache) - link severed 26/07/26; >=2yr old at 2027 start - Phase 5 re-source pending
180 EF 90DFeg Bend | ea |  | 97.81 |  | 7824.8 |  |  | 80 |  |  |  | frozen from [3] 240614 Pipe & Fittings Price Comparison (Jun-2024 cache) - link severed 26/07/26; >=2yr old at 2027 start - Phase 5 re-source pending
125 EF 90DFeg Bend | ea |  | 44.65 |  | 3572 |  |  | 80 |  |  |  | frozen from [3] 240614 Pipe & Fittings Price Comparison (Jun-2024 cache) - link severed 26/07/26; >=2yr old at 2027 start - Phase 5 re-source pending
200 EF TEE | ea |  | 109.75 |  | 329.25 |  |  | 3 |  |  |  | frozen from [3] 240614 Pipe & Fittings Price Comparison (Jun-2024 cache) - link severed 26/07/26; >=2yr old at 2027 start - Phase 5 re-source pending
180 EF TEE | ea |  | 114.28 |  | 4571.2 | COMPLETED don’t edit |  | 40 |  |  |  | frozen from [3] 240614 Pipe & Fittings Price Comparison (Jun-2024 cache) - link severed 26/07/26; >=2yr old at 2027 start - Phase 5 re-source pending
125 EF TEE | ea |  | 49.25 |  | 49.25 |  |  | 1 |  |  |  | frozen from [3] 240614 Pipe & Fittings Price Comparison (Jun-2024 cache) - link severed 26/07/26; >=2yr old at 2027 start - Phase 5 re-source pending
200*180 EF TEE | ea |  | 209.47 |  | 418.94 |  |  | 2 |  |  |  | frozen from [3] 240614 Pipe & Fittings Price Comparison (Jun-2024 cache) - link severed 26/07/26; >=2yr old at 2027 start - Phase 5 re-source pending
200*125 EF TEE | ea |  | 218.42 |  | 436.84 |  |  | 2 |  |  |  | frozen from [3] 240614 Pipe & Fittings Price Comparison (Jun-2024 cache) - link severed 26/07/26; >=2yr old at 2027 start - Phase 5 re-source pending
180*125 EF TEE | ea |  | 122.13 |  | 4885.2 |  |  | 40 |  |  |  | frozen from [3] 240614 Pipe & Fittings Price Comparison (Jun-2024 cache) - link severed 26/07/26; >=2yr old at 2027 start - Phase 5 re-source pending
200*180 EF Reducer | ea |  | 125.62 |  | 502.48 | COMPLETED don’t edit |  | 4 |  |  |  | frozen from [3] 240614 Pipe & Fittings Price Comparison (Jun-2024 cache) - link severed 26/07/26; >=2yr old at 2027 start - Phase 5 re-source pending
180*125 EF Reducer | ea |  | 60.1 |  | 1202 |  |  | 20 |  |  |  | frozen from [3] 240614 Pipe & Fittings Price Comparison (Jun-2024 cache) - link severed 26/07/26; >=2yr old at 2027 start - Phase 5 re-source pending
200PE*8"(200m) - MaxiStub W/Backing Ring | ea |  | 342.35 |  | 3423.5 |  |  | 10 |  |  |  | frozen from [3] 240614 Pipe & Fittings Price Comparison (Jun-2024 cache) - link severed 26/07/26; >=2yr old at 2027 start - Phase 5 re-source pending
180PE*6"(150mm) - MaxiStub W/Backing Ring | ea |  | 129.77 |  | 7786.2 |  |  | 60 |  |  |  | frozen from [3] 240614 Pipe & Fittings Price Comparison (Jun-2024 cache) - link severed 26/07/26; >=2yr old at 2027 start - Phase 5 re-source pending
125PE*4" (100mm) - MaxiStub W/Backing Ring | ea |  | 92.67 |  | 1853.4 |  |  | 20 |  |  |  | frozen from [3] 240614 Pipe & Fittings Price Comparison (Jun-2024 cache) - link severed 26/07/26; >=2yr old at 2027 start - Phase 5 re-source pending
180mm PE x 150mm GALV ADAPTER - PLASSON Brand | ea |  | 313.19 |  | 3131.9 | COMPLETED don’t edit |  | 10 |  |  |  | frozen from [3] 240614 Pipe & Fittings Price Comparison (Jun-2024 cache) - link severed 26/07/26; >=2yr old at 2027 start - Phase 5 re-source pending
125mm PE x 100mm GALV ADAPTER - PLASSON Brand | ea |  | 204.11 |  | 10205.5 |  |  | 50 |  |  |  | frozen from [3] 240614 Pipe & Fittings Price Comparison (Jun-2024 cache) - link severed 26/07/26; >=2yr old at 2027 start - Phase 5 re-source pending
180mm PE x 150mm GALV ADAPTER | ea |  | 315.71 |  | 3157.1 |  |  | 10 |  |  |  | frozen from [3] 240614 Pipe & Fittings Price Comparison (Jun-2024 cache) - link severed 26/07/26; >=2yr old at 2027 start - Phase 5 re-source pending
125mm PE x 100mm GALV ADAPTER | ea |  | 201.43 |  | 10071.5 |  |  | 50 |  |  |  | frozen from [3] 240614 Pipe & Fittings Price Comparison (Jun-2024 cache) - link severed 26/07/26; >=2yr old at 2027 start - Phase 5 re-source pending
200 Long SPIG 45DFeg Bend | ea |  | 68.54 |  | 137.08 | COMPLETED don’t edit |  | 2 |  |  |  | frozen from [3] 240614 Pipe & Fittings Price Comparison (Jun-2024 cache) - link severed 26/07/26; >=2yr old at 2027 start - Phase 5 re-source pending
180 Long SPIG 45DFeg Bend | ea |  | 64.46 |  | 8379.8 |  |  | 130 |  |  |  | frozen from [3] 240614 Pipe & Fittings Price Comparison (Jun-2024 cache) - link severed 26/07/26; >=2yr old at 2027 start - Phase 5 re-source pending
125 Long SPIG 45DFeg Bend | ea |  | 38.76 |  | 969 |  |  | 25 |  |  |  | frozen from [3] 240614 Pipe & Fittings Price Comparison (Jun-2024 cache) - link severed 26/07/26; >=2yr old at 2027 start - Phase 5 re-source pending
200 Long SPIG 90DFeg Bend | ea |  | 86.17 |  | 517.02 |  |  | 6 |  |  |  | frozen from [3] 240614 Pipe & Fittings Price Comparison (Jun-2024 cache) - link severed 26/07/26; >=2yr old at 2027 start - Phase 5 re-source pending
180 Long SPIG 90DFeg Bend | ea |  | 68.11 |  | 5448.8 |  |  | 80 |  |  |  | frozen from [3] 240614 Pipe & Fittings Price Comparison (Jun-2024 cache) - link severed 26/07/26; >=2yr old at 2027 start - Phase 5 re-source pending
125 Long SPIG 90DFeg Bend | ea |  | 31.65 |  | 2532 | COMPLETED don’t edit |  | 80 |  |  |  | frozen from [3] 240614 Pipe & Fittings Price Comparison (Jun-2024 cache) - link severed 26/07/26; >=2yr old at 2027 start - Phase 5 re-source pending
200 Long SPIG TEE | ea |  | 127.64 |  | 382.92 |  |  | 3 |  |  |  | frozen from [3] 240614 Pipe & Fittings Price Comparison (Jun-2024 cache) - link severed 26/07/26; >=2yr old at 2027 start - Phase 5 re-source pending
180 Long SPIG TEE | ea |  | 114.22 |  | 4568.8 |  |  | 40 |  |  |  | frozen from [3] 240614 Pipe & Fittings Price Comparison (Jun-2024 cache) - link severed 26/07/26; >=2yr old at 2027 start - Phase 5 re-source pending
125 Long SPIG TEE | ea |  | 38.26 |  | 38.26 |  |  | 1 |  |  |  | frozen from [3] 240614 Pipe & Fittings Price Comparison (Jun-2024 cache) - link severed 26/07/26; >=2yr old at 2027 start - Phase 5 re-source pending
200*180 Long SPIG TEE | ea |  | 183.48 |  | 366.96 |  |  | 2 |  |  |  | frozen from [3] 240614 Pipe & Fittings Price Comparison (Jun-2024 cache) - link severed 26/07/26; >=2yr old at 2027 start - Phase 5 re-source pending
200*125 Long SPIG TEE | ea |  | 192.43 |  | 384.86 | COMPLETED don’t edit |  | 2 |  |  |  | frozen from [3] 240614 Pipe & Fittings Price Comparison (Jun-2024 cache) - link severed 26/07/26; >=2yr old at 2027 start - Phase 5 re-source pending
180*125 Long SPIG TEE | ea |  | 185.71 |  | 7428.4 |  |  | 40 |  |  |  | frozen from [3] 240614 Pipe & Fittings Price Comparison (Jun-2024 cache) - link severed 26/07/26; >=2yr old at 2027 start - Phase 5 re-source pending
200*180 Long SPIG Reducer | ea |  | 55.84 |  | 223.36 |  |  | 4 |  |  |  | frozen from [3] 240614 Pipe & Fittings Price Comparison (Jun-2024 cache) - link severed 26/07/26; >=2yr old at 2027 start - Phase 5 re-source pending
180*125 Long SPIG Reducer | ea |  | 39.83 |  | 796.6 |  |  | 20 |  |  |  | frozen from [3] 240614 Pipe & Fittings Price Comparison (Jun-2024 cache) - link severed 26/07/26; >=2yr old at 2027 start - Phase 5 re-source pending
|  |  | 0 | [8 empty] | frozen from [3] 240614 Pipe & Fittings Price Comparison (Jun-2024 cache) - link severed 26/07/26; >=2yr old at 2027 start - Phase 5 re-source pending
200 FL DICL Sluice Valve | ea |  | 679.41 |  | 4076.46 | COMPLETED don’t edit |  | 6 |  |  |  | frozen from [3] 240614 Pipe & Fittings Price Comparison (Jun-2024 cache) - link severed 26/07/26; >=2yr old at 2027 start - Phase 5 re-source pending
150 FL DICL Sluice Valve | ea |  | 323.53 |  | 19411.8 |  |  | 60 |  |  |  | frozen from [3] 240614 Pipe & Fittings Price Comparison (Jun-2024 cache) - link severed 26/07/26; >=2yr old at 2027 start - Phase 5 re-source pending
100 FL DICL Sluice Valve | ea |  | 202.94 |  | 6088.2 |  |  | 30 |  |  |  | frozen from [3] 240614 Pipe & Fittings Price Comparison (Jun-2024 cache) - link severed 26/07/26; >=2yr old at 2027 start - Phase 5 re-source pending
Valve Spindle Riser - 600Long | ea |  | 136.94 |  | 13146.24 |  |  | 96 |  |  |  | frozen from [3] 240614 Pipe & Fittings Price Comparison (Jun-2024 cache) - link severed 26/07/26; >=2yr old at 2027 start - Phase 5 re-source pending
Valve Box - Cast Iron Trafficable - Rectangle Type "V" | ea |  | 123.53 |  | 8647.1 |  |  | 70 |  |  |  | frozen from [3] 240614 Pipe & Fittings Price Comparison (Jun-2024 cache) - link severed 26/07/26; >=2yr old at 2027 start - Phase 5 re-source pending
Valve Box - Non-Trafficable - Plastic Surround with CI Drop In "V" | ea |  | 98.82 |  | 2964.6 | COMPLETED don’t edit |  | 30 |  |  |  | frozen from [3] 240614 Pipe & Fittings Price Comparison (Jun-2024 cache) - link severed 26/07/26; >=2yr old at 2027 start - Phase 5 re-source pending
200*150mm DICL FL Reducer | ea |  | 291.18 |  | 582.36 |  |  | 2 |  |  |  | frozen from [3] 240614 Pipe & Fittings Price Comparison (Jun-2024 cache) - link severed 26/07/26; >=2yr old at 2027 start - Phase 5 re-source pending
200*100mm DICL FL Reducer | ea |  | 330 |  | 660 |  |  | 2 |  |  |  | frozen from [3] 240614 Pipe & Fittings Price Comparison (Jun-2024 cache) - link severed 26/07/26; >=2yr old at 2027 start - Phase 5 re-source pending
150*100mm DICL FL Reducer | ea |  | 156 |  | 936 |  |  | 6 |  |  |  | frozen from [3] 240614 Pipe & Fittings Price Comparison (Jun-2024 cache) - link severed 26/07/26; >=2yr old at 2027 start - Phase 5 re-source pending
150mm DICL FL * SP Adapter | ea |  | 106.24 |  | 1274.88 | COMPLETED don’t edit |  | 12 |  |  |  | frozen from [3] 240614 Pipe & Fittings Price Comparison (Jun-2024 cache) - link severed 26/07/26; >=2yr old at 2027 start - Phase 5 re-source pending
100mm DICL FL * SP Adapter | ea |  | 70.59 |  | 564.72 |  |  | 8 |  |  |  | frozen from [3] 240614 Pipe & Fittings Price Comparison (Jun-2024 cache) - link severed 26/07/26; >=2yr old at 2027 start - Phase 5 re-source pending
200mm DICL FL 90Deg Bend | ea |  | 516.35 |  | 1032.7 |  |  | 2 |  |  |  | frozen from [3] 240614 Pipe & Fittings Price Comparison (Jun-2024 cache) - link severed 26/07/26; >=2yr old at 2027 start - Phase 5 re-source pending
150mm DICL FL 90Deg Bend | ea |  | 198.88 |  | 1591.04 |  |  | 8 |  |  |  | frozen from [3] 240614 Pipe & Fittings Price Comparison (Jun-2024 cache) - link severed 26/07/26; >=2yr old at 2027 start - Phase 5 re-source pending
100mm DICL FL 90Deg Bend | ea |  | 108.71 |  | 434.84 |  |  | 4 |  |  |  | frozen from [3] 240614 Pipe & Fittings Price Comparison (Jun-2024 cache) - link severed 26/07/26; >=2yr old at 2027 start - Phase 5 re-source pending
200mm DICL FL TEE | ea |  | 672.65 |  | 1345.3 | COMPLETED don’t edit |  | 2 |  |  |  | frozen from [3] 240614 Pipe & Fittings Price Comparison (Jun-2024 cache) - link severed 26/07/26; >=2yr old at 2027 start - Phase 5 re-source pending
150mm DICL FL TEE | ea |  | 228.24 |  | 3423.6 |  |  | 15 |  |  |  | frozen from [3] 240614 Pipe & Fittings Price Comparison (Jun-2024 cache) - link severed 26/07/26; >=2yr old at 2027 start - Phase 5 re-source pending
100mm DICL FL TEE | ea |  | 128.24 |  | 256.48 |  |  | 2 |  |  |  | frozen from [3] 240614 Pipe & Fittings Price Comparison (Jun-2024 cache) - link severed 26/07/26; >=2yr old at 2027 start - Phase 5 re-source pending
200*150*200 DICL FL TEE | ea |  | 536.76 |  | 1073.52 |  |  | 2 |  |  |  | frozen from [3] 240614 Pipe & Fittings Price Comparison (Jun-2024 cache) - link severed 26/07/26; >=2yr old at 2027 start - Phase 5 re-source pending
200*100*200 DICL FL TEE | ea |  | 576.47 |  | 576.47 |  |  | 1 |  |  |  | frozen from [3] 240614 Pipe & Fittings Price Comparison (Jun-2024 cache) - link severed 26/07/26; >=2yr old at 2027 start - Phase 5 re-source pending
150-100-150 DICL FL TEE | ea |  | 198.82 |  | 1192.92 | COMPLETED don’t edit |  | 6 |  |  |  | frozen from [3] 240614 Pipe & Fittings Price Comparison (Jun-2024 cache) - link severed 26/07/26; >=2yr old at 2027 start - Phase 5 re-source pending
200mm DICL FL Pipe @ 1000 | ea |  | 898.82 |  | 898.82 |  |  | 1 |  |  |  | frozen from [3] 240614 Pipe & Fittings Price Comparison (Jun-2024 cache) - link severed 26/07/26; >=2yr old at 2027 start - Phase 5 re-source pending
200mm DICL FL Pipe @ 600 | ea |  | 640 |  | 640 |  |  | 1 |  |  |  | frozen from [3] 240614 Pipe & Fittings Price Comparison (Jun-2024 cache) - link severed 26/07/26; >=2yr old at 2027 start - Phase 5 re-source pending
200mm DICL FL Pipe @ 300 | ea |  | 355.29 |  | 355.29 |  |  | 1 |  |  |  | frozen from [3] 240614 Pipe & Fittings Price Comparison (Jun-2024 cache) - link severed 26/07/26; >=2yr old at 2027 start - Phase 5 re-source pending
150mm DICL FL Pipe @ 1000 | ea |  | 534.41 |  | 534.41 |  |  | 1 |  |  |  | frozen from [3] 240614 Pipe & Fittings Price Comparison (Jun-2024 cache) - link severed 26/07/26; >=2yr old at 2027 start - Phase 5 re-source pending
150mm DICL FL Pipe @ 600 | ea |  | 280 |  | 280 | COMPLETED don’t edit |  | 1 |  |  |  | frozen from [3] 240614 Pipe & Fittings Price Comparison (Jun-2024 cache) - link severed 26/07/26; >=2yr old at 2027 start - Phase 5 re-source pending
150mm DICL FL Pipe @ 450 | ea |  | 236.47 |  | 236.47 |  |  | 1 |  |  |  | frozen from [3] 240614 Pipe & Fittings Price Comparison (Jun-2024 cache) - link severed 26/07/26; >=2yr old at 2027 start - Phase 5 re-source pending
150mm DICL FL Pipe @ 300 | ea |  | 178.8 |  | 1430.4 |  |  | 8 |  |  |  | frozen from [3] 240614 Pipe & Fittings Price Comparison (Jun-2024 cache) - link severed 26/07/26; >=2yr old at 2027 start - Phase 5 re-source pending
100mm DICL FL Pipe @ 1000 | ea |  | 362.35 |  | 362.35 |  |  | 1 |  |  |  | frozen from [3] 240614 Pipe & Fittings Price Comparison (Jun-2024 cache) - link severed 26/07/26; >=2yr old at 2027 start - Phase 5 re-source pending
100mm DICL FL Pipe @ 600 | ea |  | 144.71 |  | 144.71 |  |  | 1 |  |  |  | frozen from [3] 240614 Pipe & Fittings Price Comparison (Jun-2024 cache) - link severed 26/07/26; >=2yr old at 2027 start - Phase 5 re-source pending
100mm DICL FL Pipe @ 450 | ea |  | 135.88 |  | 135.88 | COMPLETED don’t edit |  | 1 |  |  |  | frozen from [3] 240614 Pipe & Fittings Price Comparison (Jun-2024 cache) - link severed 26/07/26; >=2yr old at 2027 start - Phase 5 re-source pending
100mm DICL FL Pipe @ 300 | ea |  | 76.47 |  | 305.88 |  |  | 4 |  |  |  | frozen from [3] 240614 Pipe & Fittings Price Comparison (Jun-2024 cache) - link severed 26/07/26; >=2yr old at 2027 start - Phase 5 re-source pending
150mm DICL FL Deadplate | ea |  | 67.65 |  | 1691.25 |  |  | 25 |  |  |  | frozen from [3] 240614 Pipe & Fittings Price Comparison (Jun-2024 cache) - link severed 26/07/26; >=2yr old at 2027 start - Phase 5 re-source pending
100mm DICL FL Deadplate | ea |  | 43.53 |  | 1958.85 |  |  | 45 |  |  |  | frozen from [3] 240614 Pipe & Fittings Price Comparison (Jun-2024 cache) - link severed 26/07/26; >=2yr old at 2027 start - Phase 5 re-source pending
200mm PE*DI Gasket Kit Complete | ea |  | 67.06 |  | 804.72 | COMPLETED don’t edit |  | 12 |  |  |  | frozen from [3] 240614 Pipe & Fittings Price Comparison (Jun-2024 cache) - link severed 26/07/26; >=2yr old at 2027 start - Phase 5 re-source pending
200mm DI*DI Gasket Kit Complete | ea |  | 46.71 |  | 560.52 |  |  | 12 |  |  |  | frozen from [3] 240614 Pipe & Fittings Price Comparison (Jun-2024 cache) - link severed 26/07/26; >=2yr old at 2027 start - Phase 5 re-source pending
150mm PE*DI Gasket Kit Complete | ea |  | 60 |  | 3600 |  |  | 60 |  |  |  | frozen from [3] 240614 Pipe & Fittings Price Comparison (Jun-2024 cache) - link severed 26/07/26; >=2yr old at 2027 start - Phase 5 re-source pending
150mm DI*DI Gasket Kit Complete | ea |  | 42.35 |  | 2541 |  |  | 60 |  |  |  | frozen from [3] 240614 Pipe & Fittings Price Comparison (Jun-2024 cache) - link severed 26/07/26; >=2yr old at 2027 start - Phase 5 re-source pending
100mm PE*DI Gasket Kit Complete | ea |  | 24.71 |  | 741.3 |  |  | 30 |  |  |  | frozen from [3] 240614 Pipe & Fittings Price Comparison (Jun-2024 cache) - link severed 26/07/26; >=2yr old at 2027 start - Phase 5 re-source pending
100mm DI*DI Gasket Kit Complete | ea |  | 20 |  | 600 | COMPLETED don’t edit |  | 30 |  |  |  | frozen from [3] 240614 Pipe & Fittings Price Comparison (Jun-2024 cache) - link severed 26/07/26; >=2yr old at 2027 start - Phase 5 re-source pending
150mm SS Gibault Adapter Coupling | ea |  | 108.71 |  | 2174.2 |  |  | 20 |  |  |  | frozen from [3] 240614 Pipe & Fittings Price Comparison (Jun-2024 cache) - link severed 26/07/26; >=2yr old at 2027 start - Phase 5 re-source pending
100mm SS Gibault Adapter Coupling | ea |  | 87.06 |  | 1218.84 |  |  | 14 |  |  |  | frozen from [3] 240614 Pipe & Fittings Price Comparison (Jun-2024 cache) - link severed 26/07/26; >=2yr old at 2027 start - Phase 5 re-source pending
180mm PE GRIPPER Adapter Coupling | ea |  | 305.88 |  | 3670.56 |  |  | 12 |  |  |  | frozen from [3] 240614 Pipe & Fittings Price Comparison (Jun-2024 cache) - link severed 26/07/26; >=2yr old at 2027 start - Phase 5 re-source pending
125mm PE GRIPPER Adapter Coupling | ea |  | 182.35 |  | 1458.8 | COMPLETED don’t edit |  | 8 |  |  |  | frozen from [3] 240614 Pipe & Fittings Price Comparison (Jun-2024 cache) - link severed 26/07/26; >=2yr old at 2027 start - Phase 5 re-source pending
180mm PE GRIPPER * 150FL Adapter Coupling | ea |  | 229.41 |  | 917.64 |  |  | 4 |  |  |  | frozen from [3] 240614 Pipe & Fittings Price Comparison (Jun-2024 cache) - link severed 26/07/26; >=2yr old at 2027 start - Phase 5 re-source pending
125mm PE GRIPPER * 100FL Adapter Coupling | ea |  | 152.94 |  | 611.76 |  |  | 4 |  |  |  | frozen from [3] 240614 Pipe & Fittings Price Comparison (Jun-2024 cache) - link severed 26/07/26; >=2yr old at 2027 start - Phase 5 re-source pending
180mm PE GRIPPER Sluice Valve | ea |  | 690 |  | 13800 |  |  | 20 |  |  |  | frozen from [3] 240614 Pipe & Fittings Price Comparison (Jun-2024 cache) - link severed 26/07/26; >=2yr old at 2027 start - Phase 5 re-source pending
125mm PE GRIPPER Sluice Valve | ea |  | 408.47 |  | 8169.4 |  |  | 20 |  |  |  | frozen from [3] 240614 Pipe & Fittings Price Comparison (Jun-2024 cache) - link severed 26/07/26; >=2yr old at 2027 start - Phase 5 re-source pending
COMPLETED don’t edit
Detectable Tape - Fire x 250m | ea |  | 90 |  | 2520 |  |  | 28 |  |  |  | frozen from [3] 240614 Pipe & Fittings Price Comparison (Jun-2024 cache) - link severed 26/07/26; >=2yr old at 2027 start - Phase 5 re-source pending
Alcohol Weld Wipes | ea |  | 13.5 |  | 2025 |  |  | 150 |  |  |  | frozen from [3] 240614 Pipe & Fittings Price Comparison (Jun-2024 cache) - link severed 26/07/26; >=2yr old at 2027 start - Phase 5 re-source pending
Denzo Tape 100mm roll | ea |  | 27.14 |  | 4071 |  |  | 150 |  |  |  | frozen from [3] 240614 Pipe & Fittings Price Comparison (Jun-2024 cache) - link severed 26/07/26; >=2yr old at 2027 start - Phase 5 re-source pending
Black over-wrap tape - roll | ea |  | 27.14 |  | 4071 |  |  | 150 |  |  |  | frozen from [3] 240614 Pipe & Fittings Price Comparison (Jun-2024 cache) - link severed 26/07/26; >=2yr old at 2027 start - Phase 5 re-source pending
FIRE SERVICES - ABOVE GROUND
Description | Unit |  | Rate |  | Total | COMPLETED don’t edit |  | Qty
150mm MED DUTY Galv Pipe | m |  | 43.8462 |  | 3946.1538 |  |  | 90 |  |  |  | frozen from [3] 240614 Pipe & Fittings Price Comparison (Jun-2024 cache) - link severed 26/07/26; >=2yr old at 2027 start - Phase 5 re-source pending
100mm MED DUTY Galv Pipe w/RG Ends | m |  | 28.4615 |  | 341.5385 |  |  | 12 |  |  |  | frozen from [3] 240614 Pipe & Fittings Price Comparison (Jun-2024 cache) - link severed 26/07/26; >=2yr old at 2027 start - Phase 5 re-source pending
100mm Class B Copper Pipe | m |  | 106.2417 |  | 1274.9 |  |  | 12 |  |  |  | frozen from [3] 240614 Pipe & Fittings Price Comparison (Jun-2024 cache) - link severed 26/07/26; >=2yr old at 2027 start - Phase 5 re-source pending
25mm Class B Copper Pipe | m |  | 59.82 |  | 717.84 |  |  | 12 |  |  |  | frozen from [3] 240614 Pipe & Fittings Price Comparison (Jun-2024 cache) - link severed 26/07/26; >=2yr old at 2027 start - Phase 5 re-source pending
COMPLETED don’t edit
150mm Galv RG Coupling | ea |  | 12.83 |  | 384.9 |  |  | 30 |  |  |  | frozen from [3] 240614 Pipe & Fittings Price Comparison (Jun-2024 cache) - link severed 26/07/26; >=2yr old at 2027 start - Phase 5 re-source pending
100mm Galv RG Coupling | ea |  | 7.55 |  | 75.5 |  |  | 10 |  |  |  | frozen from [3] 240614 Pipe & Fittings Price Comparison (Jun-2024 cache) - link severed 26/07/26; >=2yr old at 2027 start - Phase 5 re-source pending
150mm Galv RG TEE | ea |  | 35.5 |  | 106.5 |  |  | 3 |  |  |  | frozen from [3] 240614 Pipe & Fittings Price Comparison (Jun-2024 cache) - link severed 26/07/26; >=2yr old at 2027 start - Phase 5 re-source pending
100mm Galv RG TEE | ea |  | 16.93 |  | 33.86 |  |  | 2 |  |  |  | frozen from [3] 240614 Pipe & Fittings Price Comparison (Jun-2024 cache) - link severed 26/07/26; >=2yr old at 2027 start - Phase 5 re-source pending
150mm Galv RG BEND 90Deg | ea |  | 22.85 |  | 457 | COMPLETED don’t edit |  | 20 |  |  |  | frozen from [3] 240614 Pipe & Fittings Price Comparison (Jun-2024 cache) - link severed 26/07/26; >=2yr old at 2027 start - Phase 5 re-source pending
100mm Galv RG BEND 90Deg | ea |  | 10.62 |  | 63.72 |  |  | 6 |  |  |  | frozen from [3] 240614 Pipe & Fittings Price Comparison (Jun-2024 cache) - link severed 26/07/26; >=2yr old at 2027 start - Phase 5 re-source pending
150mm Galv RG BEND 45Deg | ea |  | 23.5 |  | 188 |  |  | 8 |  |  |  | frozen from [3] 240614 Pipe & Fittings Price Comparison (Jun-2024 cache) - link severed 26/07/26; >=2yr old at 2027 start - Phase 5 re-source pending
100mm Galv RG BEND 45Deg | ea |  | 11.4 |  | 68.4 |  |  | 6 |  |  |  | frozen from [3] 240614 Pipe & Fittings Price Comparison (Jun-2024 cache) - link severed 26/07/26; >=2yr old at 2027 start - Phase 5 re-source pending
150mm Galv RG x 100mm FLANGE Adapt | ea |  | 30.75 |  | 307.5 |  |  | 10 |  |  |  | frozen from [3] 240614 Pipe & Fittings Price Comparison (Jun-2024 cache) - link severed 26/07/26; >=2yr old at 2027 start - Phase 5 re-source pending
100mm Galv RG x 100mm FLANGE Adapt | ea |  | 23.21 |  | 185.68 | COMPLETED don’t edit |  | 8 |  |  |  | frozen from [3] 240614 Pipe & Fittings Price Comparison (Jun-2024 cache) - link severed 26/07/26; >=2yr old at 2027 start - Phase 5 re-source pending
150mm RG Butterfly Valve Geared Wheel | ea |  | 217.8 |  | 1306.8 |  |  | 6 |  |  |  | frozen from [3] 240614 Pipe & Fittings Price Comparison (Jun-2024 cache) - link severed 26/07/26; >=2yr old at 2027 start - Phase 5 re-source pending
100mm RG Butterfly Valve Geared Wheel | ea |  | 169.4 |  | 1016.4 |  |  | 6 |  |  |  | frozen from [3] 240614 Pipe & Fittings Price Comparison (Jun-2024 cache) - link severed 26/07/26; >=2yr old at 2027 start - Phase 5 re-source pending
150mm H-Pattern Booster Assembly Complete | ea |  | 2350 |  | 2350 |  |  | 1 |  |  |  | frozen from [3] 240614 Pipe & Fittings Price Comparison (Jun-2024 cache) - link severed 26/07/26; >=2yr old at 2027 start - Phase 5 re-source pending
Booster Cabinet - Compl with doors and stickers | ea |  | 1155 |  | 1155 | COMPLETED don’t edit |  | 1 |  |  |  | frozen from [3] 240614 Pipe & Fittings Price Comparison (Jun-2024 cache) - link severed 26/07/26; >=2yr old at 2027 start - Phase 5 re-source pending
100mm Dual Pillar Hydrant Complete_ Flanged Base 1500 High w/landing Valves | ea |  | 365 |  | 19345 |  |  | 53 |  |  |  | frozen from [3] 240614 Pipe & Fittings Price Comparison (Jun-2024 cache) - link severed 26/07/26; >=2yr old at 2027 start - Phase 5 re-source pending
100mm Dual Pillar Hydrant Complete_ RG Base 1500 High w/landing Valves_OPTION | ea |  | 365 |  | 19345 |  |  | 53 |  |  |  | frozen from [3] 240614 Pipe & Fittings Price Comparison (Jun-2024 cache) - link severed 26/07/26; >=2yr old at 2027 start - Phase 5 re-source pending
65mm RG Landing Valve | ea |  | 90 |  | 540 |  |  | 6 |  |  |  | frozen from [3] 240614 Pipe & Fittings Price Comparison (Jun-2024 cache) - link severed 26/07/26; >=2yr old at 2027 start - Phase 5 re-source pending
Red caps and chain - suit 65mm QLD Landing valve | ea |  | 5 |  | 30 | COMPLETED don’t edit |  | 6 |  |  |  | frozen from [3] 240614 Pipe & Fittings Price Comparison (Jun-2024 cache) - link severed 26/07/26; >=2yr old at 2027 start - Phase 5 re-source pending
36m Fire Hose Reel w/25mm isolation valve | ea |  | 125 |  | 625 |  |  | 5 |  |  |  | frozen from [3] 240614 Pipe & Fittings Price Comparison (Jun-2024 cache) - link severed 26/07/26; >=2yr old at 2027 start - Phase 5 re-source pending
25mm Isolation Ball Valve (for fire hose reel) valve only, with hose nozzle latch | ea |  | 39 |  | 3315 |  |  | 85 |  |  |  | frozen from [3] 240614 Pipe & Fittings Price Comparison (Jun-2024 cache) - link severed 26/07/26; >=2yr old at 2027 start - Phase 5 re-source pending
150mm FL Testable Double Check Valve - Compl. w/Valves | ea |  | 3100.7 |  | 3100.7 |  |  | 1 |  |  |  | frozen from [3] 240614 Pipe & Fittings Price Comparison (Jun-2024 cache) - link severed 26/07/26; >=2yr old at 2027 start - Phase 5 re-source pending
150mm FL RPZD Valve - Compl. w/Valves | ea |  | 4237.09 |  | 8474.18 | COMPLETED don’t edit |  | 2 |  |  |  | frozen from [3] 240614 Pipe & Fittings Price Comparison (Jun-2024 cache) - link severed 26/07/26; >=2yr old at 2027 start - Phase 5 re-source pending
100mm FL Levered Butterfly Vlave | ea |  | 114.44 |  | 1144.4 |  |  | 10 |  |  |  | frozen from [3] 240614 Pipe & Fittings Price Comparison (Jun-2024 cache) - link severed 26/07/26; >=2yr old at 2027 start - Phase 5 re-source pending
100mm Copper Crimp - TEE | ea |  | 219.36 |  | 1535.52 |  |  | 7 |  |  |  | frozen from [3] 240614 Pipe & Fittings Price Comparison (Jun-2024 cache) - link severed 26/07/26; >=2yr old at 2027 start - Phase 5 re-source pending
100mm Copper Crimp - 90Deg Bend | ea |  | 135.09 |  | 1080.72 |  |  | 8 |  |  |  | frozen from [3] 240614 Pipe & Fittings Price Comparison (Jun-2024 cache) - link severed 26/07/26; >=2yr old at 2027 start - Phase 5 re-source pending
100mm Copper Crimp - 45Deg Bend | ea |  | 125.77 |  | 754.62 | COMPLETED don’t edit |  | 6 |  |  |  | frozen from [3] 240614 Pipe & Fittings Price Comparison (Jun-2024 cache) - link severed 26/07/26; >=2yr old at 2027 start - Phase 5 re-source pending
100mm Copper Crimp - Straight Socket | ea |  | 83.25 |  | 999 |  |  | 12 |  |  |  | frozen from [3] 240614 Pipe & Fittings Price Comparison (Jun-2024 cache) - link severed 26/07/26; >=2yr old at 2027 start - Phase 5 re-source pending
100mm Copper Crimp - 100mm FL Adapter | ea |  | 52.25 |  | 627 |  |  | 12 |  |  |  | frozen from [3] 240614 Pipe & Fittings Price Comparison (Jun-2024 cache) - link severed 26/07/26; >=2yr old at 2027 start - Phase 5 re-source pending
80mm Copper Crimp - TEE | ea |  | 175.66 |  | 702.64 |  |  | 4 |  |  |  | frozen from [3] 240614 Pipe & Fittings Price Comparison (Jun-2024 cache) - link severed 26/07/26; >=2yr old at 2027 start - Phase 5 re-source pending
100mm*80mm Copper Crimp - REDUCER | ea |  | 164.08 |  | 820.4 |  |  | 5 |  |  |  | frozen from [3] 240614 Pipe & Fittings Price Comparison (Jun-2024 cache) - link severed 26/07/26; >=2yr old at 2027 start - Phase 5 re-source pending
COMPLETED don’t edit
32mm Fi Lockable Ball Valve | ea |  | 77.95 |  | 311.8 |  |  | 4 |  |  |  | frozen from [3] 240614 Pipe & Fittings Price Comparison (Jun-2024 cache) - link severed 26/07/26; >=2yr old at 2027 start - Phase 5 re-source pending
32mm Cu Crimp * 32mi Adapt | ea |  | 17.16 |  | 137.28 |  |  | 8 |  |  |  | frozen from [3] 240614 Pipe & Fittings Price Comparison (Jun-2024 cache) - link severed 26/07/26; >=2yr old at 2027 start - Phase 5 re-source pending
32mm Cu Crimp Coupling Straight | ea |  | 7.23 |  | 86.76 |  |  | 12 |  |  |  | frozen from [3] 240614 Pipe & Fittings Price Comparison (Jun-2024 cache) - link severed 26/07/26; >=2yr old at 2027 start - Phase 5 re-source pending
32mm Cu Crimp 90Deg Bend | ea |  | 14.31 |  | 85.86 |  |  | 6 |  |  |  | frozen from [3] 240614 Pipe & Fittings Price Comparison (Jun-2024 cache) - link severed 26/07/26; >=2yr old at 2027 start - Phase 5 re-source pending
32mm Cu Crimp 45Deg Bend | ea |  | 16.24 |  | 64.96 | COMPLETED don’t edit |  | 4 |  |  |  | frozen from [3] 240614 Pipe & Fittings Price Comparison (Jun-2024 cache) - link severed 26/07/26; >=2yr old at 2027 start - Phase 5 re-source pending
32mm*25mm Cu Crimp Reducer | ea |  | 14.36 |  | 57.44 |  |  | 4 |  |  |  | frozen from [3] 240614 Pipe & Fittings Price Comparison (Jun-2024 cache) - link severed 26/07/26; >=2yr old at 2027 start - Phase 5 re-source pending
25mm Fi Lockable Ball Valve | ea |  | 46.94 |  | 3989.9 |  |  | 85 |  |  |  | frozen from [3] 240614 Pipe & Fittings Price Comparison (Jun-2024 cache) - link severed 26/07/26; >=2yr old at 2027 start - Phase 5 re-source pending
25mm Cu Crimp * 25mi Adapt | ea |  | 8.46 |  | 1438.2 |  |  | 170 |  |  |  | frozen from [3] 240614 Pipe & Fittings Price Comparison (Jun-2024 cache) - link severed 26/07/26; >=2yr old at 2027 start - Phase 5 re-source pending
25mm Cu Crimp Coupling Straight | ea |  | 5.74 |  | 975.8 |  |  | 170 |  |  |  | frozen from [3] 240614 Pipe & Fittings Price Comparison (Jun-2024 cache) - link severed 26/07/26; >=2yr old at 2027 start - Phase 5 re-source pending
25mm Cu Crimp 90Deg Bend | ea |  | 7.7 |  | 1309 | COMPLETED don’t edit |  | 170
25mm Cu Crimp 45Deg Bend | ea |  | 10.19 |  | 254.75 |  |  | 25 |  |  |  | frozen from [3] 240614 Pipe & Fittings Price Comparison (Jun-2024 cache) - link severed 26/07/26; >=2yr old at 2027 start - Phase 5 re-source pending
150mm Galv 2 Piece Weld-nut Bracket M12 | ea |  | 5.86 |  | 468.8 |  |  | 80 |  |  |  | frozen from [3] 240614 Pipe & Fittings Price Comparison (Jun-2024 cache) - link severed 26/07/26; >=2yr old at 2027 start - Phase 5 re-source pending
100mm Galv 2 Piece Weld-nut Bracket M12 | ea |  | 4.41 |  | 44.1 |  |  | 10 |  |  |  | frozen from [3] 240614 Pipe & Fittings Price Comparison (Jun-2024 cache) - link severed 26/07/26; >=2yr old at 2027 start - Phase 5 re-source pending
150 Galv 2 Piece Channel Clip | ea |  | 5.36 |  | 53.6 | COMPLETED don’t edit |  | 10 |  |  |  | frozen from [3] 240614 Pipe & Fittings Price Comparison (Jun-2024 cache) - link severed 26/07/26; >=2yr old at 2027 start - Phase 5 re-source pending
100 Galv 2 Piece Channel Clip | ea |  | 4.4 |  | 44 |  |  | 10 |  |  |  | frozen from [3] 240614 Pipe & Fittings Price Comparison (Jun-2024 cache) - link severed 26/07/26; >=2yr old at 2027 start - Phase 5 re-source pending
12mm Galv Threaded Rod | ea |  | 10.64 |  | 127.68 |  |  | 12 |  |  |  | frozen from [3] 240614 Pipe & Fittings Price Comparison (Jun-2024 cache) - link severed 26/07/26; >=2yr old at 2027 start - Phase 5 re-source pending
Galv Braced Counter Lever Bracket - 450Long | ea |  | 20 |  | 120 |  |  | 6 |  |  |  | frozen from [3] 240614 Pipe & Fittings Price Comparison (Jun-2024 cache) - link severed 26/07/26; >=2yr old at 2027 start - Phase 5 re-source pending
003 Padlock | ea |  | 19.5 |  | 390 |  |  | 20 |  |  |  | frozen from [3] 240614 Pipe & Fittings Price Comparison (Jun-2024 cache) - link severed 26/07/26; >=2yr old at 2027 start - Phase 5 re-source pending
100mm DI*DI Gasket Kit Complete | ea |  | 20 |  | 480 |  |  | 24
FIRE SERVICES - Misc.
Description | Unit |  | Rate |  | Total |  |  | Qty
PE Pipe Scraper/Peeler - 125-250mmPE.Please detail Spec | ea |  | 0 |  | 0 |  |  | 1
Electrofusion PE Welder 25-250mmPE. Please detail Spec | ea |  | 0 |  | 0 |  |  | 1
PE Butt Welder. Automatic. 125-250mmPE. Please detail Spec | ea |  | 0 |  | 0 |  |  | 1
Hand Roll Groover. 65-150mm. | ea |  | 0 |  | 0 |  |  | 1
Delivery - To Rockhampton PIPE LENGTHS as quoted | ea |  | 2178.48 |  | 2178.48 |  |  | 1 |  |  |  | frozen from [3] 240614 Pipe & Fittings Price Comparison (Jun-2024 cache) - link severed 26/07/26; >=2yr old at 2027 start - Phase 5 re-source pending
Delivery - To Rockhampton Standard/Palletised items | ea |  | 2178.48 |  | 2178.48 |  |  | 1 |  |  |  | frozen from [3] 240614 Pipe & Fittings Price Comparison (Jun-2024 cache) - link severed 26/07/26; >=2yr old at 2027 start - Phase 5 re-source pending
Quarry / Gravels / Landscape
Description | Unit |  | Rate |  | Total | COMPLETED don’t edit |  | Qty
Bedding / Fill Sand | m3 |  | 39.75 |  | 32697.5383 |  |  | 822.5796 |  |  |  | frozen from [4] 240614 Suppliers Subbies Price Comparison (Jun-2024 cache) - link severed 26/07/26; Phase 5 re-source pending
CBR 45/2.5 Roadbase | m3 |  | 41.9 |  | 419 |  |  | 10 |  |  |  | frozen from [4] 240614 Suppliers Subbies Price Comparison (Jun-2024 cache) - link severed 26/07/26; Phase 5 re-source pending
Turf Underlay/Topsoil | m3 |  | 45.25 |  | 6912.0506 |  |  | 152.7525 |  |  |  | frozen from [4] 240614 Suppliers Subbies Price Comparison (Jun-2024 cache) - link severed 26/07/26; Phase 5 re-source pending
Standard Garden Woodchip | m3 |  | 87 |  | 353.046 |  |  | 4.058 |  |  |  | frozen from [4] 240614 Suppliers Subbies Price Comparison (Jun-2024 cache) - link severed 26/07/26; Phase 5 re-source pending
Turf - Standard Couch or Similar | Slab (.5m2) |  | 6.48 |  | 22436.2872 |  |  | 3462.39 |  |  |  | frozen from [4] 240614 Suppliers Subbies Price Comparison (Jun-2024 cache) - link severed 26/07/26; Phase 5 re-source pending
Concrete Product
Description | Unit |  | Rate |  | Total | COMPLETED don’t edit |  | Qty
Cement Stabalized Sand (3-5%) | m3 |  | 169 |  | 87150.5368 |  |  | 515.6836 |  |  |  | frozen from [4] 240614 Suppliers Subbies Price Comparison (Jun-2024 cache) - link severed 26/07/26; Phase 5 re-source pending
Exposed Agg Concrete - Standard/Cheapest Exposed Agg Stone | m3 |  | 252 |  | 23250.528 |  |  | 92.264 |  |  |  | frozen from [4] 240614 Suppliers Subbies Price Comparison (Jun-2024 cache) - link severed 26/07/26; Phase 5 re-source pending
N25 20mm 80 Slump Concrete | m3 |  | 263 |  | 3971.5104 |  |  | 15.1008 |  |  |  | frozen from [4] 240614 Suppliers Subbies Price Comparison (Jun-2024 cache) - link severed 26/07/26; Phase 5 re-source pending
Asphalt
Description | Unit |  | Rate |  | Total |  |  | Qty
50mm Thick Roadway | m2 |  | 0 |  | 0 |  |  | 1516.88
Excavation/Quarry/Misc/ Takeoff.
| Unit | Rate |  | Rate |  |  |  | Qty
Avrg Trench = .900D*.500W | m | [6 empty] | 1250
L/M Of Asphalt Reinstate | m | [6 empty] | 120
M2 Of Asphalt Reinstate | m2 | [6 empty] | 96
L/M Of CBR Reinstate | m | [6 empty] | 968
L/M of Inground Pipe | m | [6 empty] | 1250
L/M of Tunnel Bore | m | [6 empty] | 75
Spoil Removal | W | L | Spoil Factor; | L | Total m3 |  |  | D
Average Trench Dimensions | 0.5 | 1250 | 1.3 | 1250 | 731.25 |  |  | 0.9
Thrust Block Concrete | Qty | Total m3 | Contingency | Total m3 | Total m3 | Total Cost |  | m3/TB
| 12 | 0.42 | 1.02 | 0 | 0.17993 | 47.3211 |  | 0.035
Bollard Concrete | Qty | Total m3 | Contingency | Total m3 | Total m3 | Total Cost |  | m3/B
Set | 40 | 3.2 | 1.02 | 0 | 10.4448 | 2746.9824 |  | 0.08
Fill | 40 | 3.6 | 1.02 | 0 | 13.2192 | 263 |  | 0.09
Base Slab Concrete | Qty | Total m3 | Contingency | Total m3 | Total m3 | Total Cost |  | m3/Base
| 10 | 7.5 | 1.025 | 0 | 57.6562 | 263 |  | 0.75
Above Grnd Pole-Bracket Concrete | Qty | Total m3 | Contingency | Total m3 | Total m3 | Total Cost |  | m3/B
| 80 | 5.2 | 1.015 | 0 | 27.4456 | 263 |  | 0.065
Quarry & Concrete Product
Description | Unit | Rate | Rate/LM | Rate |  |  | QTY | Unit/LM | Total | Contingency | 1.05
5-7mm Stone | Ton | 1 | 0.203 | 1 |  |  | 253.75 | 0.203 | 253.75 | 266.4375
5-7mm Stone | m3 | 1 | 0.14 | 1 |  |  |  | 0.14
10-12mm Stone | Ton | 1 | 0.45 | 1 |  |  | 40 | 0.45 | 40 | 42
Medium River / Bed Sand | Ton | 1 | 0.225 | 1 |  |  | 281.25 | 0.225 | 281.25 | 295.3125
Medium River / Bed Sand | m3 | 1 | 0.14 | 1 |  |  |  | 0.14
CBR15 Road Base | Ton | 1 | 0.36 | 1 |  |  | 348.48 | 0.36 | 348.48 | 365.904
CBR45 | Ton | 1 | 0.36 | 1 |  |  | 348.48 | 0.36 | 348.48 | 365.904
LEANMIX | m3 | 1 | 0.3 | 1 |  |  | 36 | 0.3 | 36 | 37.8

## Equip&HIRE_Master
| TCS PROJECT USE |  |  | COMPLETED don’t edit
DESCRIPTION | Unit | Qty | WEEKLY (5 day)
Skid Steer Loader_Tracked (CAT249+) | Day |  | 225.4333 |  | Source
Skid Steer Loader_Wheeled (CAT226+) | Day |  | 163.9667 |  | frozen from [4] 240614 Suppliers Subbies Price Comparison (Jun-2024 cache) - link severed 26/07/26; Phase 5 re-source pending
Mini Loader, Stand-on Type | Day |  | 180 |  | frozen from [4] 240614 Suppliers Subbies Price Comparison (Jun-2024 cache) - link severed 26/07/26; Phase 5 re-source pending
COMPLETED don’t edit
1.5-1.8 Ton_Excavator | Day |  | 137.1429 |  | frozen from [4] 240614 Suppliers Subbies Price Comparison (Jun-2024 cache) - link severed 26/07/26; Phase 5 re-source pending
1.7-2Ton_Excavator | Day
3-5Ton_Excavator | Day |  | 238.6667 |  | frozen from [4] 240614 Suppliers Subbies Price Comparison (Jun-2024 cache) - link severed 26/07/26; Phase 5 re-source pending
8Ton_Excavator | Day |  | 261.1667 |  | frozen from [4] 240614 Suppliers Subbies Price Comparison (Jun-2024 cache) - link severed 26/07/26; Phase 5 re-source pending
10-12Ton_Excavator | Day |  |  | COMPLETED don’t edit
13-16Ton_Excavator | Day |  | 317.2 |  | frozen from [4] 240614 Suppliers Subbies Price Comparison (Jun-2024 cache) - link severed 26/07/26; Phase 5 re-source pending
20-24Ton_Excavator | Day |  | 314.2857 |  | frozen from [4] 240614 Suppliers Subbies Price Comparison (Jun-2024 cache) - link severed 26/07/26; Phase 5 re-source pending
Ripper_1.7-2T | Day
Ripper_1.5-4T | Day |  | 32.74 | COMPLETED don’t edit | frozen from [4] 240614 Suppliers Subbies Price Comparison (Jun-2024 cache) - link severed 26/07/26; Phase 5 re-source pending
Ripper_3-5T | Day
Ripper_8T | Day |  | 40.38 |  | frozen from [4] 240614 Suppliers Subbies Price Comparison (Jun-2024 cache) - link severed 26/07/26; Phase 5 re-source pending
Breaker_1.7-2T | Day |  | 123.33 |  | frozen from [4] 240614 Suppliers Subbies Price Comparison (Jun-2024 cache) - link severed 26/07/26; Phase 5 re-source pending
Breaker_3-5T | Day |  | 165.89 |  | frozen from [4] 240614 Suppliers Subbies Price Comparison (Jun-2024 cache) - link severed 26/07/26; Phase 5 re-source pending
Breaker_8T | Day |  | 165.89 | COMPLETED don’t edit | frozen from [4] 240614 Suppliers Subbies Price Comparison (Jun-2024 cache) - link severed 26/07/26; Phase 5 re-source pending
Breaker_10-12T | Day
Breaker_13-15T | Day |  | 203 |  | frozen from [4] 240614 Suppliers Subbies Price Comparison (Jun-2024 cache) - link severed 26/07/26; Phase 5 re-source pending
Auger Drive_10-12T
300Dia Auger Drill
COMPLETED don’t edit
1.25T_Tipper Truck | Day |  | 205 |  | frozen from [4] 240614 Suppliers Subbies Price Comparison (Jun-2024 cache) - link severed 26/07/26; Phase 5 re-source pending
2-4T_Tipper Truck | Day |  | 166.98 |  | frozen from [4] 240614 Suppliers Subbies Price Comparison (Jun-2024 cache) - link severed 26/07/26; Phase 5 re-source pending
<6T_Tipper Truck | Day |  | 171.4286 |  | frozen from [4] 240614 Suppliers Subbies Price Comparison (Jun-2024 cache) - link severed 26/07/26; Phase 5 re-source pending
<10T_Articulated Site Tipper | Day |  |  | COMPLETED don’t edit
Upright Rammer_Wacker | Day |  | 34.2857 |  | frozen from [4] 240614 Suppliers Subbies Price Comparison (Jun-2024 cache) - link severed 26/07/26; Phase 5 re-source pending
Trench Roller_Dbl Drum_Remote | Day |  | 165 |  | frozen from [4] 240614 Suppliers Subbies Price Comparison (Jun-2024 cache) - link severed 26/07/26; Phase 5 re-source pending
<26Ft_Scissor Lift - Diesel | Day
<26Ft_Scissor Lift - Elec | Day
<34Ft_Boom Lift - Diesel | Day |  |  | COMPLETED don’t edit
<34Ft_Boom Lift - Elec | Day
Porta Loo_No Tank | Day |  | 5.46 |  | frozen from [4] 240614 Suppliers Subbies Price Comparison (Jun-2024 cache) - link severed 26/07/26; Phase 5 re-source pending
6*3m Demantable Lunchroom - COMPLETE | Day |  | 23 |  | frozen from [4] 240614 Suppliers Subbies Price Comparison (Jun-2024 cache) - link severed 26/07/26; Phase 5 re-source pending
6*3m Demantable Office - COMPLETE | Day |  | 23 | COMPLETED don’t edit | frozen from [4] 240614 Suppliers Subbies Price Comparison (Jun-2024 cache) - link severed 26/07/26; Phase 5 re-source pending
20Ft Shipping Container | Day
Quick Cut Demo Saw | Day
Sngl Ph_6KVA Genset | Day
Diesel Air Compressor_Trailer | Day
Air Breaker - Heavy | Day |  |  | COMPLETED don’t edit
Air Hose <10m | Day
Elec Breaker/Jachammer | Day
Flexdrive Motor Unit | Day
Flexdrive_Pump Shaft | Day
Temporary Power Board | Day |  |  | COMPLETED don’t edit
Dual CabUte | Day
3m3 Skip Bbin | per serive |  | 230 |  | frozen from [4] 240614 Suppliers Subbies Price Comparison (Jun-2024 cache) - link severed 26/07/26; Phase 5 re-source pending
plus disposal | Tonne |  | 309 |  | frozen from [4] 240614 Suppliers Subbies Price Comparison (Jun-2024 cache) - link severed 26/07/26; Phase 5 re-source pending
site fee | Week |  | 35 | COMPLETED don’t edit | frozen from [4] 240614 Suppliers Subbies Price Comparison (Jun-2024 cache) - link severed 26/07/26; Phase 5 re-source pending
~4m3_Skip Bin | per change over |  | 229.9 |  | frozen from [4] 240614 Suppliers Subbies Price Comparison (Jun-2024 cache) - link severed 26/07/26; Phase 5 re-source pending
~6m3_Skip Bin | per change over |  | 239.8 |  | frozen from [4] 240614 Suppliers Subbies Price Comparison (Jun-2024 cache) - link severed 26/07/26; Phase 5 re-source pending
Plus disposal | Tonne |  | 309 |  | frozen from [4] 240614 Suppliers Subbies Price Comparison (Jun-2024 cache) - link severed 26/07/26; Phase 5 re-source pending
Site fee | Week |  | 35 |  | frozen from [4] 240614 Suppliers Subbies Price Comparison (Jun-2024 cache) - link severed 26/07/26; Phase 5 re-source pending
Vacuum Excavator - Vermeer VT250D | Day |  | 295.77 | COMPLETED don’t edit | frozen from [4] 240614 Suppliers Subbies Price Comparison (Jun-2024 cache) - link severed 26/07/26; Phase 5 re-source pending
Vac Trailer – Dry Hire | Day |  | 355 |  | frozen from [4] 240614 Suppliers Subbies Price Comparison (Jun-2024 cache) - link severed 26/07/26; Phase 5 re-source pending
TRANSPORT_Ex BRIS - Return | Day
TRANSPORT_Ex ROK - Return | Hour |  | 180 |  | frozen from [4] 240614 Suppliers Subbies Price Comparison (Jun-2024 cache) - link severed 26/07/26; Phase 5 re-source pending
0-4T Per Hour Delivery Rate | Hour |  | 125 | COMPLETED don’t edit | frozen from [4] 240614 Suppliers Subbies Price Comparison (Jun-2024 cache) - link severed 26/07/26; Phase 5 re-source pending
5 - 9t Transport Hourly Rate | Hour |  | 160 |  | frozen from [4] 240614 Suppliers Subbies Price Comparison (Jun-2024 cache) - link severed 26/07/26; Phase 5 re-source pending
10 - 19t Low Loader Hourly rate - Minimum 2 Hour Charge | Hour |  | 200 |  | frozen from [4] 240614 Suppliers Subbies Price Comparison (Jun-2024 cache) - link severed 26/07/26; Phase 5 re-source pending

## Misc Subbie Rates_Master
DENIS - Cells highlighted GREEN are complete (By Me). | [6 empty] | Source
PLANT HIRE - WET |  |  | TCS PROJECT USE |  |  | COMPLETED don’t edit
DESCRIPTION | Unit |  | Hr Rate | Total
1.8T Excavator | Hr |  | 100 |  |  |  | frozen from [4] 240614 Suppliers Subbies Price Comparison (Jun-2024 cache) - link severed 26/07/26; Phase 5 re-source pending
3-5 ton Excavator | Hr |  | 115 |  |  |  | frozen from [4] 240614 Suppliers Subbies Price Comparison (Jun-2024 cache) - link severed 26/07/26; Phase 5 re-source pending
3-5T Combo | Hr |  | 154 |  |  |  | frozen from [4] 240614 Suppliers Subbies Price Comparison (Jun-2024 cache) - link severed 26/07/26; Phase 5 re-source pending
Hammer attachment 3.5-4T | Hr |  | 21 |  |  | COMPLETED don’t edit | frozen from [4] 240614 Suppliers Subbies Price Comparison (Jun-2024 cache) - link severed 26/07/26; Phase 5 re-source pending
Ripper 3.5-4T | Hr |  | 10 |  |  |  | frozen from [4] 240614 Suppliers Subbies Price Comparison (Jun-2024 cache) - link severed 26/07/26; Phase 5 re-source pending
5t Excavator | Hr |  | 150 |  |  |  | frozen from [4] 240614 Suppliers Subbies Price Comparison (Jun-2024 cache) - link severed 26/07/26; Phase 5 re-source pending
Hammer attachment 5T | Hr |  | 50 |  |  |  | frozen from [4] 240614 Suppliers Subbies Price Comparison (Jun-2024 cache) - link severed 26/07/26; Phase 5 re-source pending
Skid steer | Hr |  | 140 |  |  |  | frozen from [4] 240614 Suppliers Subbies Price Comparison (Jun-2024 cache) - link severed 26/07/26; Phase 5 re-source pending
8T Excavator | Hr |  | 128 |  |  | COMPLETED don’t edit | frozen from [4] 240614 Suppliers Subbies Price Comparison (Jun-2024 cache) - link severed 26/07/26; Phase 5 re-source pending
Hammer attachment 8T | Hr |  | 26 |  |  |  | frozen from [4] 240614 Suppliers Subbies Price Comparison (Jun-2024 cache) - link severed 26/07/26; Phase 5 re-source pending
Ripper 8T | Hr |  | 10 |  |  |  | frozen from [4] 240614 Suppliers Subbies Price Comparison (Jun-2024 cache) - link severed 26/07/26; Phase 5 re-source pending
13-15T Excavator | Hr |  | 153 |  |  |  | frozen from [4] 240614 Suppliers Subbies Price Comparison (Jun-2024 cache) - link severed 26/07/26; Phase 5 re-source pending
Hammer attachment 14T | Hr |  | 36 |  |  |  | frozen from [4] 240614 Suppliers Subbies Price Comparison (Jun-2024 cache) - link severed 26/07/26; Phase 5 re-source pending
Ripper 14T | Hr |  | 10 |  |  | COMPLETED don’t edit | frozen from [4] 240614 Suppliers Subbies Price Comparison (Jun-2024 cache) - link severed 26/07/26; Phase 5 re-source pending
3000L Hydro Excavation Truck | Hr |  | 190 |  |  |  | frozen from [4] 240614 Suppliers Subbies Price Comparison (Jun-2024 cache) - link severed 26/07/26; Phase 5 re-source pending
4500L Hydro Excavation Truck | Hr |  | 220 |  |  |  | frozen from [4] 240614 Suppliers Subbies Price Comparison (Jun-2024 cache) - link severed 26/07/26; Phase 5 re-source pending
6300L Hydro Excavation Truck | Hr |  | 250 |  |  |  | frozen from [4] 240614 Suppliers Subbies Price Comparison (Jun-2024 cache) - link severed 26/07/26; Phase 5 re-source pending
Water Truck allow for water at cost | Hr |  | 110 |  |  |  | frozen from [4] 240614 Suppliers Subbies Price Comparison (Jun-2024 cache) - link severed 26/07/26; Phase 5 re-source pending
12t Body Truck Tipper | Hr |  | 110 |  |  | COMPLETED don’t edit | frozen from [4] 240614 Suppliers Subbies Price Comparison (Jun-2024 cache) - link severed 26/07/26; Phase 5 re-source pending
SURVEYOR |  |  | TCS PROJECT USE |  |  | COMPLETED don’t edit
DESCRIPTION | QTY |  | Hr Rate? | Total
Site Field Surveyor for all works preformed | 0 |  | 180 | 0 |  |  | frozen from [4] 240614 Suppliers Subbies Price Comparison (Jun-2024 cache) - link severed 26/07/26; Phase 5 re-source pending
| 0 |  | 0 | 0
| 0 |  | 0 | 0
SERVICES LOCATOR |  |  | TCS PROJECT USE |  |  | COMPLETED don’t edit
DESCRIPTION | QTY |  | Hr Rate? | Total
Standard Rate (includes wand, GPR) | 0 |  | 130 | 0 |  |  | frozen from [4] 240614 Suppliers Subbies Price Comparison (Jun-2024 cache) - link severed 26/07/26; Phase 5 re-source pending
| 0 |  | 0 | 0
| 0 |  | 0 | 0
CONCRETE CUTTER |  |  | TCS PROJECT USE |  |  | COMPLETED don’t edit
DESCRIPTION | QTY |  | Lm Rate | Total
Asphalt Cutting | 0 |  | 13.5 | 0 |  |  | frozen from [4] 240614 Suppliers Subbies Price Comparison (Jun-2024 cache) - link severed 26/07/26; Phase 5 re-source pending
Concrete Cutting | 0 |  | 16 | 0 |  |  | frozen from [4] 240614 Suppliers Subbies Price Comparison (Jun-2024 cache) - link severed 26/07/26; Phase 5 re-source pending
Site Establishment Fee (2 per stage) | 0 |  | 80 | 0 |  |  | frozen from [4] 240614 Suppliers Subbies Price Comparison (Jun-2024 cache) - link severed 26/07/26; Phase 5 re-source pending
CONCRETING SERVICES |  |  | TCS PROJECT USE |  |  | COMPLETED don’t edit
DESCRIPTION | QTY |  | Rate | Total
Road/Drveway Reinstate; 1mW x 150 Thck, N25/20/80, Incl Reinforcement | 0 |  | 145 | 0 |  |  | frozen from [4] 240614 Suppliers Subbies Price Comparison (Jun-2024 cache) - link severed 26/07/26; Phase 5 re-source pending
Kerb & Channel - 1m Wide | 0 |  | 155 | 0 |  |  | frozen from [4] 240614 Suppliers Subbies Price Comparison (Jun-2024 cache) - link severed 26/07/26; Phase 5 re-source pending
Footpath - 1.5mW, N25/20/80, Incl Reinforcement | 0 |  | 180 | 0 |  |  | frozen from [4] 240614 Suppliers Subbies Price Comparison (Jun-2024 cache) - link severed 26/07/26; Phase 5 re-source pending
Footpath - 1.5mW, EXPOSED AGG, N25/20/80, Incl Reinforcement | 0 |  | 185 | 0 |  |  | frozen from [4] 240614 Suppliers Subbies Price Comparison (Jun-2024 cache) - link severed 26/07/26; Phase 5 re-source pending
ASPHALT SERVICES |  |  | TCS PROJECT USE |  |  | COMPLETED don’t edit
DESCRIPTION | QTY |  | m2 | Total
50mm Thck - Trench Reinstatement Through Road/Driveway | 0 |  | 97 | 0 |  |  | frozen from [4] 240614 Suppliers Subbies Price Comparison (Jun-2024 cache) - link severed 26/07/26; Phase 5 re-source pending
50mm Thck - 1.5-2m Wide Footpath reinstatements | 0 |  | 97 | 0 |  |  | frozen from [4] 240614 Suppliers Subbies Price Comparison (Jun-2024 cache) - link severed 26/07/26; Phase 5 re-source pending
Establishment Fee (1 per stage) | 0 |  | 5500 | 0
SOIL TESTING & GEO |  |  | TCS PROJECT USE |  |  | COMPLETED don’t edit
DESCRIPTION | QTY |  | Rate | Total
Compaction Testing | 0 |  | 115 | 0 |  |  | frozen from [4] 240614 Suppliers Subbies Price Comparison (Jun-2024 cache) - link severed 26/07/26; Phase 5 re-source pending
Site Establishment (3 per stage) | 0 |  | 90 | 0
| 0 |  | 0 | 0 |  |  | frozen from [4] 240614 Suppliers Subbies Price Comparison (Jun-2024 cache) - link severed 26/07/26; Phase 5 re-source pending
FIRE TESTING / CERTIFICATION |  |  | TCS PROJECT USE |  |  | COMPLETED don’t edit
DESCRIPTION | QTY |  | Rate | Total
Sprinkler Fitter | 0 |  | 130 | 0 |  |  | frozen from [4] 240614 Suppliers Subbies Price Comparison (Jun-2024 cache) - link severed 26/07/26; Phase 5 re-source pending
Sprinkler Apprentice | 0 |  | 100 | 0 |  |  | frozen from [4] 240614 Suppliers Subbies Price Comparison (Jun-2024 cache) - link severed 26/07/26; Phase 5 re-source pending
Hydrostatic Test Equip | 0 |  | 450 | 0 |  |  | frozen from [4] 240614 Suppliers Subbies Price Comparison (Jun-2024 cache) - link severed 26/07/26; Phase 5 re-source pending
Booster Pump Appliance | 0 |  | 800 | 0 |  | COMPLETED don’t edit | frozen from [4] 240614 Suppliers Subbies Price Comparison (Jun-2024 cache) - link severed 26/07/26; Phase 5 re-source pending
FULL Hydro Test - Per Test (6.5Hr 1 x fitter, 1 x apprentice, 1 day Test gear) | 0 |  | 1945 | 0 |  |  | frozen from [4] 240614 Suppliers Subbies Price Comparison (Jun-2024 cache) - link severed 26/07/26; Phase 5 re-source pending
FULL Boost Test - Per Test (8.5Hr - 2 x fitter, 1 x apprentice, 1 day Pump) | 0 |  | 3560 | 0 |  |  | frozen from [4] 240614 Suppliers Subbies Price Comparison (Jun-2024 cache) - link severed 26/07/26; Phase 5 re-source pending
Provision of Form 72 | 0 |  | 350 | 0 |  |  | frozen from [4] 240614 Suppliers Subbies Price Comparison (Jun-2024 cache) - link severed 26/07/26; Phase 5 re-source pending
Misc. Project Rates (ROCHAMPTON) - Master
| Unit | REQ | All EX GST | Total EX GST
Flight Costs; Qantas, 1-Way, No Check in Luggage | Ea. | 1 | 220 | 220 | Average $220 Incl GST per flight
Hire Car; Budget, Airport Pick/Drop, NOT UTE, No Fuel | Day | 1 | 190 | 190
Transport (TCS Cost); Airport-Site/Accom, Cab/Staff Pickup | Ea. | 1 | 65 | 65 | Avg | HD
TCS Fuel; $/Km | Km | 1 | 0.2 | 0.2 |  | 0.16
TCS Vehicle Running Costs; $/Km ($3,800/Yr, 35,000Kms/Yr) | Km | 1 | 0.18 | 0.18 |  | 0.11
| Ea. | 1 | 0 | 0
Bris -> Rok - Courier - UTE | Ea. | 1 | 0 | 0
Bris -> Rok - Courier - Std Truck | Ea. | 1 | 0 | 0
Bris -> Rok - Courier - Flat Bed (Container/Machine) | Ea. | 1 | 2500 | 2500

## Accomodation_Master
INCLUDING GST (UNLESS NOTED OTHERWISE)
TCS Accomodation Rates & Costs
| Hotel / Motel | Sngl Night | Week | Month | Qtr
| 1 x Unit, 1 x Room | Motel Unit | Private Unit
Hidden | No. of persons stayng; | 1
| Furnished | YES
| *Serviced | YES
| Individual/Private BATHROOM | YES
| Individual/Private KITCHEN (Cooking) Faciliities Available - Microwave min. | YES
| Individual/Private LAUNDRY Facilities Available | YES
| Individual/Private LOUNGE ROOM Facilities Available | YES
|  | Sngl Night | Week | Month | Qtr
| Total Booking Cost | 112.8571 | 790 | 3160 | 9480
| TCS Housing Consumables; ….. | 0 | 0 | 0 | 0
| TCS Laundry Allowance..? | 0 | 0 | 0 | 0
| TCS Additional Meals Allowance (If no cooking Facilities?) | 0 | 0 | 0 | 0
| TCS Furnishings? | 0 | 0 | 0 | 0
| TCS Cleaning/Servincing Allowance? | 0 | 0 | 0 | 0
| Total TCS Cost | 112.8571 | 790 | 3160 | 9480
| Total Cost Per Person | 112.8571 | 790 | 3160 | 9480
| 1 x Unit, 1 x Room | Motel Unit | Share Rooms
Hidden | No. of persons stayng; | 2
| Furnished | YES
| *Serviced | YES
| Individual/Private BATHROOM | NO | Share with Unit
| Individual/Private KITCHEN (Cooking) Faciliities Available - Microwave min. | NO | Share with Unit
| Individual/Private LAUNDRY Facilities Available | YES
| Individual/Private LOUNGE ROOM Facilities Available | YES
|  | Sngl Night | Week | Month | Qtr
| Total Booking Cost | 101.4286 | 710 | 2840 | 8520
| TCS Housing Consumables; ….. | 0 | 0 | 0 | 0
| TCS Laundry Allowance..? | 0 | 0 | 0 | 0
| TCS Additional Meals Allowance (If no cooking Facilities?) | 0 | 0 | 0 | 0
| TCS Furnishings? | 0 | 0 | 0 | 0
| TCS Cleaning/Servincing Allowance? | 0 | 0 | 0 | 0
| Total TCS Cost | 101.4286 | 710 | 2840 | 8520
| Total Cost Per Person | 50.7143 | 355 | 1420 | 4260
| 1 x Unit, 1 x Room | Motel Unit | Share Rooms
Hidden | No. of persons stayng; | 3
| Furnished | YES
| *Serviced | YES
| Individual/Private BATHROOM | NO | Share with Unit
| Individual/Private KITCHEN (Cooking) Faciliities Available - Microwave min. | NO | Share with Unit
| Individual/Private LAUNDRY Facilities Available | YES
| Individual/Private LOUNGE ROOM Facilities Available | YES
|  | Sngl Night | Week | Month | Qtr
| Total Booking Cost | 130.7143 | 915 | 3660 | 10980
| TCS Housing Consumables; ….. | 0 | 0 | 0 | 0
| TCS Laundry Allowance..? | 0 | 0 | 0 | 0
| TCS Additional Meals Allowance (If no cooking Facilities?) | 0 | 0 | 0 | 0
| TCS Furnishings? | 0 | 0 | 0 | 0
| TCS Cleaning/Servincing Allowance? | 0 | 0 | 0 | 0
| Total TCS Cost | 130.7143 | 915 | 3660 | 10980
| Total Cost Per Person | 43.5714 | 305 | 1220 | 3660
| 1 x Unit, 2 x Room | Motel Unit | Share House'
Hidden | No. of persons stayng; | 2
| Furnished | YES
| *Serviced | YES
| Individual/Private BATHROOM | NO | Share with Unit
| Individual/Private KITCHEN (Cooking) Faciliities Available - Microwave min. | NO | Share with Unit
| Individual/Private LAUNDRY Facilities Available | YES
| Individual/Private LOUNGE ROOM Facilities Available | YES
|  | Sngl Night | Week | Month | Qtr
| Total Booking Cost | 254.2857 | 1780 | 7120 | 21360
| TCS Housing Consumables; ….. | 0 | 0 | 0 | 0
| TCS Laundry Allowance..? | 0 | 0 | 0 | 0
| TCS Additional Meals Allowance (If no cooking Facilities?) | 0 | 0 | 0 | 0
| TCS Furnishings? | 0 | 0 | 0 | 0
| TCS Cleaning/Servincing Allowance? | 0 | 0 | 0 | 0
| Total TCS Cost | 254.2857 | 1780 | 7120 | 21360
| Total Cost Per Person | 127.1429 | 890 | 3560 | 10680
| Full Apartment / Cabin / Villa (Tourist/Caravan Park) | Sngl Night | Week | Month | Qtr
| 1 x Unit, 1 x Room | *CABIN | Private Unit
Hidden | No. of persons stayng; | 1
| Furnished | YES
| *Serviced | YES
| Individual/Private BATHROOM | YES
| Individual/Private KITCHEN (Cooking) Faciliities Available - Microwave min. | YES
| Individual/Private LAUNDRY Facilities Available | YES
| Individual/Private LOUNGE ROOM Facilities Available | YES
** Pool, BBQ, Games etc etc?
|  | Sngl Night | Week | Month | Qtr
| Total Booking Cost | 114.2857 | 800 | 3200 | 9600
| TCS Housing Consumables; ….. | 0 | 0 | 0 | 0
| TCS Laundry Allowance..? | 0 | 0 | 0 | 0
| TCS Additional Meals Allowance (If no cooking Facilities?) | 0 | 0 | 0 | 0
| TCS Furnishings? | 0 | 0 | 0 | 0
| TCS Cleaning/Servincing Allowance? | 0 | 0 | 0 | 0
| Total TCS Cost | 114.2857 | 800 | 3200 | 9600
| Total Cost Per Person | 114.2857 | 800 | 3200 | 9600
Hidden | 1 x Unit, 1 x Room | *UNIT/VILLA | Share Rooms
| No. of persons stayng; | 2
| Furnished | YES
| *Serviced | YES
| Individual/Private BATHROOM | NO | Share with Unit
| Individual/Private KITCHEN (Cooking) Faciliities Available - Microwave min. | NO | Share with Unit
| Individual/Private LAUNDRY Facilities Available | YES
| Individual/Private LOUNGE ROOM Facilities Available | YES
** Pool, BBQ, Games etc etc?
|  | Sngl Night | Week | Month | Qtr
| Total Booking Cost | 142.8571 | 1000 | 4000 | 12000
| TCS Housing Consumables; ….. | 0 | 0 | 0 | 0
| TCS Laundry Allowance..? | 0 | 0 | 0 | 0
| TCS Additional Meals Allowance (If no cooking Facilities?) | 0 | 0 | 0 | 0
| TCS Furnishings? | 0 | 0 | 0 | 0
| TCS Cleaning/Servincing Allowance? | 0 | 0 | 0 | 0
| Total TCS Cost | 142.8571 | 1000 | 4000 | 12000
| Total Cost Per Person | 71.4286 | 500 | 2000 | 6000
Hidden | 1 x Unit, 1 x Room | *UNIT/VILLA | Share Rooms
| No. of persons stayng; | 3
| Furnished | YES
| *Serviced | YES
| Individual/Private BATHROOM | YES
| Individual/Private KITCHEN (Cooking) Faciliities Available - Microwave min. | YES
| Individual/Private LAUNDRY Facilities Available | YES
| Individual/Private LOUNGE ROOM Facilities Available | YES
** Pool, BBQ, Games etc etc?
|  | Sngl Night | Week | Month | Qtr
| Total Booking Cost | 178.5714 | 1250 | 5000 | 15000
| TCS Housing Consumables; ….. | 0 | 0 | 0 | 0
| TCS Laundry Allowance..? | 0 | 0 | 0 | 0
| TCS Additional Meals Allowance (If no cooking Facilities?) | 0 | 0 | 0 | 0
| TCS Furnishings? | 0 | 0 | 0 | 0
| TCS Cleaning/Servincing Allowance? | 0 | 0 | 0 | 0
| Total TCS Cost | 178.5714 | 1250 | 5000 | 15000
| Total Cost Per Person | 59.5238 | 416.6667 | 1666.6667 | 5000
| 1 x Unit, 2 x Room | *UNIT/VILLA | Share House'
Hidden | No. of persons stayng; | 2
| Furnished | YES
| *Serviced | YES
| Individual/Private BATHROOM | YES
| Individual/Private KITCHEN (Cooking) Faciliities Available - Microwave min. | YES
| Individual/Private LAUNDRY Facilities Available | YES
| Individual/Private LOUNGE ROOM Facilities Available | YES
** Pool, BBQ, Games etc etc?
|  | Sngl Night | Week | Month | Qtr
| Total Booking Cost | 185.7143 | 1300 | 5200 | 15600
| TCS Housing Consumables; ….. | 0 | 0 | 0 | 0
| TCS Laundry Allowance..? | 0 | 0 | 0 | 0
| TCS Additional Meals Allowance (If no cooking Facilities?) | 0 | 0 | 0 | 0
| TCS Furnishings? | 0 | 0 | 0 | 0
| TCS Cleaning/Servincing Allowance? | 0 | 0 | 0 | 0
| Total TCS Cost | 185.7143 | 1300 | 5200 | 15600
| Total Cost Per Person | 92.8571 | 650 | 2600 | 7800
Hidden | 1 x Unit, 2 x Room | *UNIT/VILLA | Share Rooms
| No. of persons stayng; | 4
| Furnished | YES
| *Serviced | YES
| Individual/Private BATHROOM | YES
| Individual/Private KITCHEN (Cooking) Faciliities Available - Microwave min. | YES
| Individual/Private LAUNDRY Facilities Available | YES
| Individual/Private LOUNGE ROOM Facilities Available | YES
** Pool, BBQ, Games etc etc?
|  | Sngl Night | Week | Month | Qtr
| Total Booking Cost | 240 | 1680 | 6720 | 20160
| TCS Housing Consumables; ….. | 0 | 0 | 0 | 0
| TCS Laundry Allowance..? | 0 | 0 | 0 | 0
| TCS Additional Meals Allowance (If no cooking Facilities?) | 0 | 0 | 0 | 0
| TCS Furnishings? | 0 | 0 | 0 | 0
| TCS Cleaning/Servincing Allowance? | 0 | 0 | 0 | 0
| Total TCS Cost | 240 | 1680 | 6720 | 20160
| Total Cost Per Person | 60 | 420 | 1680 | 5040
| 1 x Unit, 3 x Room | *UNIT/VILLA | Share House'
Hidden | No. of persons stayng; | 3
| Furnished | YES
| *Serviced | YES
| Individual/Private BATHROOM | YES
| Individual/Private KITCHEN (Cooking) Faciliities Available - Microwave min. | YES
| Individual/Private LAUNDRY Facilities Available | YES
| Individual/Private LOUNGE ROOM Facilities Available | YES
** Pool, BBQ, Games etc etc?
|  | Sngl Night | Week | Month | Qtr
| Total Booking Cost | 328.5714 | 2300 | 9200 | 27600
| TCS Housing Consumables; ….. | 0 | 0 | 0 | 0
| TCS Laundry Allowance..? | 0 | 0 | 0 | 0
| TCS Additional Meals Allowance (If no cooking Facilities?) | 0 | 0 | 0 | 0
| TCS Furnishings? | 0 | 0 | 0 | 0
| TCS Cleaning/Servincing Allowance? | 0 | 0 | 0 | 0
| Total TCS Cost | 328.5714 | 2300 | 9200 | 27600
| Total Cost Per Person | 109.5238 | 766.6667 | 3066.6667 | 9200
Hidden | 1 x Unit, 3 x Room | *UNIT/VILLA | Share Rooms
| No. of persons stayng; | 6
| Furnished | YES
| *Serviced | YES
| Individual/Private BATHROOM | YES
| Individual/Private KITCHEN (Cooking) Faciliities Available - Microwave min. | YES
| Individual/Private LAUNDRY Facilities Available | YES
| Individual/Private LOUNGE ROOM Facilities Available | YES
** Pool, BBQ, Games etc etc?
|  | Sngl Night | Week | Month | Qtr
| Total Booking Cost | 378.5714 | 2650 | 10600 | 31800
| TCS Housing Consumables; ….. | 0 | 0 | 0 | 0
| TCS Laundry Allowance..? | 0 | 0 | 0 | 0
| TCS Additional Meals Allowance (If no cooking Facilities?) | 0 | 0 | 0 | 0
| TCS Furnishings? | 0 | 0 | 0 | 0
| TCS Cleaning/Servincing Allowance? | 0 | 0 | 0 | 0
| Total TCS Cost | 378.5714 | 2650 | 10600 | 31800
| Total Cost Per Person | 63.0952 | 441.6667 | 1766.6667 | 5300
Full Apartment / TownHouse (Private/AirBnB)
| 1 x Unit, 3 x Room | T'House | Share House'
| No. of persons stayng; | 3
| Furnished | YES
| *Serviced | YES | Fortnightly
| Individual/Private BATHROOM | YES | 2 of
| Individual/Private KITCHEN (Cooking) Faciliities Available - Microwave min. | YES
| Individual/Private LAUNDRY Facilities Available | YES
| Individual/Private LOUNGE ROOM Facilities Available | YES
|  | Sngl Night | Week | Month | Qtr
| Total Booking Cost | 144.4444 | 1083.3333 | 4333.3333 | 13000
| TCS Housing Consumables; ….. | 4.4444 | 33.3333 | 133.3333 | 400
| TCS Laundry Allowance..? | 0 | 0 | 0 | 0
| TCS Additional Meals Allowance (If no cooking Facilities?) | 0 | 0 | 0 | 0
| TCS Furnishings? | 0 | 0 | 0 | 0
| TCS Cleaning/Servincing Allowance? | 3.3333 | 25 | 100 | 300
| Total TCS Cost | 152.2222 | 1141.6667 | 4566.6667 | 13700
| Total Cost Per Person | 54.3651 | 380.5556 | 1522.2222 | 4566.6667
Full Apartment / TownHouse / Unit - VIA AGENT
| 1 x Unit, 3 x Room | House | Share House'
| No. of persons stayng; | 3
| Furnished | NO
| *Serviced | NO
| Individual/Private BATHROOM | YES
| Individual/Private KITCHEN (Cooking) Faciliities Available - Microwave min. | YES
| Individual/Private LAUNDRY Facilities Available | YES
| Individual/Private LOUNGE ROOM Facilities Available | YES
|  | Sngl Night | Week | Month | Qtr
| Total Booking Cost | 77.7778 | 583.3333 | 2333.3333 | 7000
| TCS Housing Consumables; ….. | 4.4444 | 33.3333 | 133.3333 | 400
| TCS Laundry Allowance..? | 0 | 0 | 0 | 0
| TCS Additional Meals Allowance (If no cooking Facilities?) | 0 | 0 | 0 | 0
| TCS Furnishings? | 31.1111 | 233.3333 | 933.3333 | 2800
| TCS Cleaning/Servincing Allowance? | 16.6667 | 125 | 500 | 1500
| TCS Cost - Labour to set up, Fitout etc? | 11.1111 | 83.3333 | 333.3333 | 1000
| Total TCS Cost | 141.1111 | 1058.3333 | 4233.3333 | 12700
| Total Cost Per Person | 50.3968 | 352.7778 | 1411.1111 | 4233.3333
| 1 x Unit, 4 x Room | House
HIDDEN | No. of persons stayng; | 4
| Furnished | NO
| *Serviced | NO
| Individual/Private BATHROOM | YES
| Individual/Private KITCHEN (Cooking) Faciliities Available - Microwave min. | YES
| Individual/Private LAUNDRY Facilities Available | YES
| Individual/Private LOUNGE ROOM Facilities Available | YES
|  | Sngl Night | Week | Month | Qtr
| Total Booking Cost | 87.2222 | 654.1667 | 2616.6667 | 7850
| TCS Housing Consumables; ….. | 4.4444 | 33.3333 | 133.3333 | 400
| TCS Laundry Allowance..? | 0 | 0 | 0 | 0
| TCS Additional Meals Allowance (If no cooking Facilities?) | 0 | 0 | 0 | 0
| TCS Furnishings? | 38.8889 | 291.6667 | 1166.6667 | 3500
| TCS Cleaning/Servincing Allowance? | 20.5556 | 154.1667 | 616.6667 | 1850
| TCS Cost - Labour to set up, Fitout etc? | 17.7778 | 133.3333 | 533.3333 | 1600
| Total TCS Cost | 168.8889 | 1266.6667 | 5066.6667 | 15200
| Total Cost Per Person | 45.2381 | 316.6667 | 1266.6667 | 3800
OPTION AVERAGES - Per Person, Per MONTH (No Project Roster Imapct)
| Single Hotel/Motel, Single Room - NO SHARE |  |  |  | 3160
| Single Hotel/Motel, Individual Rooms - SHARE HOUSE |  |  |  | 3560
| Single Hotel/Motel, ANY ROOM - SHARE ROOM |  |  |  | 1320
| Cabin/Flat/Unit_Tourist Park Type, Single Room - NO SHARE |  |  |  | 3200
| Cabin/Flat/Unit_Tourist Park Type, Individual Rooms - SHARE HOUSE |  |  |  | 2833.3333
| Cabin/Flat/Unit_Tourist Park Type, ANY ROOM - SHARE ROOM |  |  |  | 1778.3333
| Unit / T'House / House_Serviced / Air BnB, Individual Rooms - SHARE HOUSE |  |  |  | 1522.2222
| Unit / T'House / House_Private / TCS Rental, Individual Rooms - SHARE HOUSE |  |  |  | 1338.8889
BASED ON:
Work ROSTER Example #3 - 6-Day Week, 10Hr Days, Stay @ Rocky for W/E, Return Every 2nd W/E. (FLY)
| Working Days/Month | 21 | (Add 2.5 days for non-work days spent in accom)
| No-Work Days/Month | 7
| Avrg Hours / Month | 210
OPTION AVERAGES - Per Person, Per NIGHT (As Per Project Roster)
| Single Hotel/Motel, Private Unit - NO SHARE |  |  |  | 112.8571 | Nightly Book
| Single Hotel/Motel, Individual Rooms - SHARE HOUSE |  |  |  | 127.1429 | Nightly Book
| Single Hotel/Motel, ANY ROOM - SHARE ROOM |  |  |  | 62.8571
| Cabin/Flat/Unit_Tourist Park Type, Private Unit - NO SHARE |  |  |  | 114.2857 | Nightly Book
| Cabin/Flat/Unit_Tourist Park Type, Individual Rooms - SHARE HOUSE |  |  |  | 134.9206 | Long-stay Book
| Cabin/Flat/Unit_Tourist Park Type, ANY ROOM - SHARE ROOM |  |  |  | 84.6825
| Unit / T'House / House_Serviced / Air BnB, Individual Rooms - SHARE HOUSE |  |  |  | 72.4868 | Long-stay Book
| Unit / T'House / House_Private / TCS Rental, Individual Rooms - SHARE HOUSE |  |  |  | 63.7566 | Long-stay Book
Roster Averages
| TCS Cost Per Person - Private Unit - NO SHARE - Nightly Booking (average allowance) |  |  |  | 113.5714
| TCS Cost Per Person - Individual Room - SHARE HOUSE - Nightly Booking (average allowance) |  |  |  | 68.1217

## EBC_Alternates
TPS - EBC REGISTER & ALTERNATES - TEN16699 (all ex GST)
NOTHING on this sheet feeds the base roll-up on 'TCS $ Sched'. Every figure is either an EXCLUDED-BUT-COSTED add-price held ready for reinstatement, or a labelled ALTERNATE to a base-offer item. The markup factor is referenced live from 'TCS $ Sched' Q51 (41.5% = 5.5% prelims + 18% O/H + 18% profit, each applied to total cost per SS5.4).
SECTION A - EXCLUDED-BUT-COSTED (EBC) add-prices - formula-ready for reinstatement
EBC-1 Sewer rising main O100/DN110, pumpwell to discharge - 110 m (SCOPE_MATRIX 2.1-x2; NewItems #1; RFI CL C4 discharge undefined)
PE100 DN110 PN16 pressure pipe - benchmark (Reece Q-459014437 PE100 125 @ $31.1083/m x (110/125)^2 weight ratio x 1.38 escalation) | m | 110 | 33.2446 | 3656.9026
EF couplers / fittings allowance (15% of pipe value) | item | 1 | 548.5354 | 548.5354
Labour - Crew 1 in-ground, 2 crew-days (Phase 7 T1-06) | day | 2 | 2862.4261 | 5724.8522
Plant - 5T excavator 2 d + butt welder 2 d @ $350/d allowance | item | 1 | 1177.3333 | 1177.3333
EBC-1 cost subtotal |  |  |  | 11107.6235
EBC-1 ADD-PRICE (cost x 1.415) |  |  |  | 15717.2873
Wording control: the exclusion must be worded so the builder cannot deem the rising main included inside 2.1-b gravity sewer. Ownership is ambiguous once Council installs the station (interface L6) - the reinstatement price is HELD, not offered.
EBC-2 Trade waste application (grease arrestor) - excluded per locked SS5.3 / cross-cutting X3; add-price held (CL A2)
Trade waste application / consultant fee allowance | item | 1 | 1500 | 1500
Attendance + documentation - 0.5 crew-day | day | 0.5 | 2862.4261 | 1431.213
EBC-2 cost subtotal |  |  |  | 2931.213
EBC-2 ADD-PRICE (cost x 1.415) |  |  |  | 4147.6665
H002 n.25 makes the trade waste application TPS's; VOL 21 never mentions trade waste despite the canteen. Excluded per locked decision + RFI. The arrestor HARDWARE is priced in the NBC base (1500 L Viking GIT; size conflict 1500/2000/550-5000 L per CL B6).
EBC-3 Fire extinguisher SUPPLY - NBC x8 + PAM x1 (drawn with no trade allocation - CL B8; matrix 4.11-d / 3.11-d)
FE 2.5 kg ABE + bracket + location sign | ea | 9 | 120 | 1080
Install / mount labour - 0.25 crew-day | day | 0.25 | 2862.4261 | 715.6065
EBC-3 cost subtotal |  |  |  | 1795.6065
EBC-3 ADD-PRICE (cost x 1.415) |  |  |  | 2540.7832
VOL38 s14.1 says the plumber prices extinguishers; the drawing note says the builder generally provides them. Carried EBC + RFI so the position is stated either way. AS1851 12-month maintenance of the fire services IS priced in the NBC base (r309).
EBC-4 Sewer pump station - EXCLUDED, NO PRICE CARRIED (Addendum 2, 10 Jul 2026: 'Sewage Pump Station will be getting installed by Council')
Interface per ledger L6: TPS carries the gravity sewer to and terminating at the station's inlet DICL pipe piece ('LIMIT OF Q-MAX WORKS'). Station supply, installation, excavation and slab by Council/others; electrical supply, controls and commissioning cabling by the electrical trade; the rising main is EBC-1 above. TPS states this interface list verbatim in its submission so 'pump station excluded' cannot be read as excluding the connecting works.
Add-price EVIDENCE held (not offered): APS Quote 14065 as-specified QMax Fortis 3200 O x 6700 deep = $468,000 supply + install + commissioning - the basis to quote from if an add-price is requested (no validity stated - flag). Cross-references for the same station: Tradelink 1066334 pack ~$416,000 (incl. $115,000 M&E install labour) and Reece Q-459014431 $523,170.73 S+I. Spread of $107k across the three offers.
REMOVED FROM THE MODEL 26/07/26: the prior workbook carried an orphaned block W37 $468,000 -> W43 = 468,000 x 1.15 + $2,500 freight + $5,000 install = $545,700 'sell'. That block fed NO roll-up cell - it was never inside the old $273,056.54 sub-total, so its deletion moves no headline number. D6 FLAG: any prior quote circulated off the old N68 grand total never included the pump station.
SECTION B - ALTERNATES (clearly labelled; EXCLUDED from the base roll-up)
ALT-1 O200 buried main - COPPER Type B alternate. BASE OFFER = HDPE PE100 SDR11 DN250 (locked SS5.5: no buried copper alternate is OFFERED)
Kembla copper Type B DN200 - Tradelink 6595064, $2,015 per 6 m length (Jul-26; escalation not embedded) | m | 134.63 | 335.8333 | 45213.2417
Base HDPE line as carried in the model ('Siteworks ' F349) |  |  |  | 23118.3881
Material delta if copper were adopted (alternate less base) |  |  |  | 22094.8535
Sell delta if adopted (delta x 1.18 site contingency x 1.415 markup) |  |  |  | 36891.7769
The copper build-up is retained here as a cost record only. The base offer sits inside the spec's own equivalence table (VOL38 s10.1, Cromford PN16 250 = O200 ID) so it is a CONFORMING offer, not a departure. The copper tapping-cluster FITTINGS (tees, bends, full-faced stubs, gasket kits, sluice valves) remain in the base at adopted counts - only the 134.63 m pipe run changes material.
ALT-2 Building water >DN22 - COPPER alternate. BASE = 316 SS press-fit per WS2 (priced both ways per locked SS5.5 / CL C9)
NBC copper Type B 32 mm (CQU 1057751 curve basis) | m | 17.86 | 32 | 571.52
NBC copper Type B 25 mm | m | 112.72 | 21.5 | 2423.48
PAM copper Type B 32 mm | m | 9.56 | 19.98 | 191.0088
PAM copper Type B 25 mm | m | 26.9 | 17.52 | 471.288
Copper pipe alternate - total |  |  |  | 3657.2968
316 SS press-fit pipe as carried in the base (NBC F420+F423, PAM F405+F407) |  |  |  | 2479.6372
Base SS press FITTINGS total (these carry a +50% benchmark uplift over copper press) |  |  |  | 1319.655
Copper fitting reversion (base/1.5 less base = -base/3) |  |  |  | -439.885
Material delta if copper adopted (copper pipe less SS pipe plus fitting reversion) |  |  |  | 737.7746
Sell delta if adopted (delta x 1.12 NBC contingency x 1.415 markup) |  |  |  | 1169.2252
Gap #2: Tradelink refused a 316 SS press-fit rate; Reece Q-459014431 priced 22/28/35 mm only - which covers every size needed here (NBC/PAM carry nothing above 35 mm), so the PIPE rate is a project quote, not a benchmark. The FITTING rates are benchmark-derived at copper press x1.5 (SS press fittings run 1.4-1.6x copper on supplier curves) and are tagged PENDING RFQ on every affected row. 316 SS long-lead 10-14 weeks is flagged in the programme.
SUMMARY - held add-prices (EBC) and alternate deltas are STATED in the submission but are NOT in the tendered sum. Base-offer positions: O200 main = HDPE PE100 SDR11 DN250; building water >DN22 = 316 SS press-fit; <=DN22 = PEX / copper per WS2.
TOTAL EBC add-prices held (EBC-1 + EBC-2 + EBC-3) |  |  |  | 22405.737

## Sched3_Extract
TPS (Hydraulic) - Paynters Schedule 3 price extract - TEN16699 - ALL EX GST
Maps the TPS cost model to the exact Schedule 3 line structure (schedule3_transcript.md / 01_SCOPE_MATRIX). Physical lump-sum lines are carried inside the stage lump sums; PC Sums, provisional fees and schedule-of-rates lines are separately identified as the schedule requires. Every Schedule 3 line allocated to TPS appears exactly once.
Stage | Sch ref | Schedule 3 line | TPS treatment | Amount ex GST | Basis / qualification
1A | 1.1-1.7 | Preliminaries & Documentation (TPS share of the Split lines) | In 1A lump sum |  | Own establishment/TC/ESC/plans/set-out/QC+ADAC/PM per SS5.2 - priced via Phase 7 activities T1-01, T1-02, T5-07 plus the Prelim & OH tab; no shared compound (L5)
1A | 2.1-b | Sewerage mains (incl. mains through 1B land serving 1A) | In 1A lump sum |  | Gravity sewer 207.53 m (29.29 O150 + 178.24 O100) + SMS x2 + O150 property connection. Terminates at the Council station inlet DICL piece (L6). FRW lodgement = Principal Contractor (X2)
1A | 2.1-x1 | -- Sewer pump station | EXCLUDED (Addendum 2) |  | Council-installed; interface list stated verbatim (L6); add-price evidence held on EBC_Alternates EBC-4 (APS 14065 basis)
1A | 2.1-x2 | -- Sewer rising main O100/DN110 | EBC - add-price held | 15717.2873 | 110 m allowance, formula-ready reinstatement; RFI CL C4 (discharge location undefined); wording prevents it being deemed inside 2.1-b
1A | 2.1-c | Water mains - O200 tapping to meter slab (mains through 1B) | In 1A lump sum |  | BASE = O200 ID HDPE PE100 SDR11 DN250 per locked SS5.5 (VOL38 s10.1 equivalence); rate benchmark-derived PENDING RFQ (Gap #5). Copper alternate ALT-1. H002 n.26 diameter blank - RFI CL C3
1A | 2.2-b | Temporary site services (TPS own, in full) | In 1A lump sum |  | Own toilets/wash/genset/potable water storage + distribution (ITT S17.3 - no site power or water). Priced bottom-up on the Prelim & OH tab
1A | 2.4-b | Hydraulic services - site reticulation within 1A | In 1A lump sum |  | 125 PE CW spine 236.88 m + 6 take-off sets + 32/25 branches 111.51 m + capped future services + irrigation take-off capped at the E-type flange (L13)
1A | 2.4-c | Fire services - site | In 1A lump sum |  | 125 HDPE REDLINE 217.73 m + H-pattern booster + cabinet + 100 dual pillar hydrant. Extent qualified (CL C1/F3); AS2419.1 coverage + missing H004 = RFI
1A | 3.5 | Hydraulic - grated trench drains and pits | EXCLUDED - TCS scope |  | Locked SS5.1: priced by TCS despite the 'Hydraulic' heading (drawn on the civil sheets). TPS expressly excludes and cross-refers the TCS tender (L1)
1A | 4.3 | -- Roofing / roof plumbing / gutters / downpipes | EXCLUDED (SS5.3) |  | TPS scope starts at the DP 'CONNECT TO CIVIL' point in ground; the roofer owns everything above (L14). DP stub count adopted 19 EA, RFI on count (Opens #23)
1A | 4.11-c | NBC hydraulic services | In 1A lump sum |  | Sanitary 268.4 m + trade waste 54.78 m + 1500 L GIT (size RFI CL B6) + water (316 SS press-fit >DN22 conforming, PEX <=DN22; copper ALT-2) + 2x Rheem 315L HWU + RPZD/backflow + articulation + seismic (install + layout only, CL C7) + DP stubs to CONNECT TO CIVIL only (L2)
1A | 4.11-d | NBC fire compliance | In 1A lump sum |  | FHR x1 + FB x1 + AS1851 12-month maintenance & tagging. FE x8 supply = EBC-3 + RFI (CL B8)
1A | 4.12-c | NBC plumbing fixtures - SUPPLY | PC SUM | 207268.8355 | Tradelink 1066143 adjusted for adopted counts + 15% (build-up on 'TCS $ Sched' R70:S78). Install labour is in Base. Validity 13/08/26 vs 2027 start + header defects qualified (CL F4)
1A | 4.12-e | NBC drinking fountain (chilled) | PC SUM (calculated) | 25415 | 2x CF400 chilled @ $11,050 + 15%; chilled/non-chilled same-SKU RFI (CL C10); signage explicitly extra on the quote. Rough-in connections in Base
1A | 5.0 | Provisional - plumbing, water & sewer connection fees | PROVISIONAL as directed | 20000 | $20,000 actual-cost reimbursement carried exactly as directed, NO markup (SS5.4). Schedule entry mechanics RFI (CL A3)
1A | 7.0-a | Rock removal rate - TPS trenches AND pits, soft AND hard | SCHEDULE OF RATES | see build-up below | Four rates tendered per H002 n.24. Extra-over, payable on Superintendent written direction (ITT s18.2). TPS rates apply only to water/sewer/fire excavations - no overlap with TCS. Three-regime inconsistency RFI'd (CL B5/A5)
1A | 7.0-b | Unsuitable ground removal & reinstatement rate | SCHEDULE OF RATES | see build-up below | Extra-over, Superintendent written direction only (ITT s18.1); same own-excavations boundary
1A |  | STAGE 1A TOTAL ex GST (lump sum + PC sums + provisional) |  | 1751720.1063 | 1A base sell + 1A PC sums. Section 6.0 (electrical) is Not Ours; 1A 2.3 / 2.5 drainage is TCS
1B | 1.1-1.7 | Preliminaries & Documentation (TPS share) | In 1B lump sum |  | Standalone-viable 1B per SS5.2 - no reliance on any 1A establishment
1B | 2.1-a | Temporary site services (TPS own) | In 1B lump sum |  | As 1A 2.2-b, sized for a standalone 1B award
1B | 2.2-b | Hydraulic services - 1B's own connections and reticulation | In 1B lump sum |  | Branch take-offs from the 1A-priced mains; the branch fitting/valve IS the line (L9). PAM O25/O32 entries, O100 PAM sewer leg, bubbler/DF supplies + wastes, hose taps (Phase 7 T2-09, 4 crew-days carried on the PAM sheet)
1B | 2.2-c | Fire services - 1B extent | In 1B lump sum |  | Same extent-verification qualification as 1A 2.4-c (CL C1)
1B | 3.11-c | PAM hydraulic services | In 1B lump sum |  | Sanitary 68.09 m @1:60 + ORG + FWG x4 + Rheem 50L HWU + TMV in SS lockable cabinet + O32 check-meter (no PRV vs NBC 500 kPa - RFI CL C8) + 316 SS/PEX water + articulation + seismic. DP stubs only - PAM sheets carry NO 'connect to civil' note (RFI)
1B | 3.11-d | PAM fire compliance | In 1B lump sum |  | FE x1 supply = EBC-3 + RFI (CL B8)
1B | 3.12-a | PAM plumbing fixtures - SUPPLY | PC SUM | 17250 | PAM extension of the Tradelink 1066143 basis + 15%. The PAM fixture set was never counted by the take-off - adopted counts (8 s/s WC + in-wall cisterns, 1800 trough, PWD basin, CSK, timed taps, 2x TR) extended at the quote-rate family; delta stated
1B | 3.12-b | PAM drinking fountain (non-chilled) | PC SUM (calculated) | 16560 | 2x CF400 non-chilled benchmark $7,200 ea + 15% - the non-chilled variant is unpriced by anyone (Gap #6), re-quote pending; same SKU RFI (CL C10)
1B | 4.5-c | Water bubbler stations (recreational park) | PC SUM (calculated) | 33120 | 4x site DF/BT positions per H003 at the same benchmark + 15%; unit type undefined in the legend (RFI CL C10). Supply/waste connections priced in 1B 2.2-b Base; slabs/surrounds by others
1B | 4.6 | Provisional - connection fees | PROVISIONAL as directed | 20000 | $20,000 as directed, no markup - mirror of 1A 5.0. Carried in BOTH stages per the schedule and SS5.4
1B | 5.0-a | Rock removal rate - TPS trenches AND pits, soft AND hard | SCHEDULE OF RATES | see build-up below | Identical rates and regime to 1A 7.0-a
1B | 5.0-b | Unsuitable ground removal & reinstatement rate | SCHEDULE OF RATES | see build-up below | Identical to 1A 7.0-b
1B | 2.3 / 4.x | Stormwater drainage, landscaping, play equipment, park furniture | Not Ours / TCS |  | 1B 2.3-a stormwater = TCS; landscape/irrigation/play/furniture = other trades. Listed so no 1B line is silent
1B |  | STAGE 1B TOTAL ex GST (lump sum + PC sums + provisional) |  | 267215.6783 | 1B base sell + 1B PC sums
|  | TPS GRAND TOTAL ex GST (1A + 1B) |  | 2018935.7846 | Tie check on 'TCS $ Sched' N88 must read 0
SCHEDULE-OF-RATES BUILD-UP (1A 7.0 / 1B 5.0) - extra-over rates, TPS excavations only
Extra-over $/m3 = (crew day rate + plant day rate) x (1/rock production - 1/normal production) + disposal or import premium. The crew rate is the re-based FIFO Crew 1 day rate; plant is 8T excavator + breaker. Productions are estimator judgement for Rockhampton siltstone/sandstone per geotech NQL2024-0320 s5.3.3 refusal depths.
Rate line | Rock prod (m3/d) | Normal prod (m3/d) | Crew+plant $/day | Disposal/import $/m3 | TENDERED RATE $/m3
Soft rock - TRENCH (extra over) | 18 | 45 | 3289.4828 | 25 | 134.6494
Hard rock - TRENCH (extra over) | 7 | 45 | 3289.4828 | 25 | 421.8265
Soft rock - PIT / structure (extra over) | 12 | 45 | 3289.4828 | 25 | 226.0239
Hard rock - PIT / structure (extra over) | 4.5 | 45 | 3289.4828 | 25 | 682.8966
Unsuitable ground - removal & reinstatement (extra over) | 25 | 45 | 3123.5928 | 54.75 | 110.2805 | Disposal $15/m3 (helper haulage rate) + imported select fill at the bedding-sand rate; compaction sits inside the crew production
Rock 'reasonably anticipated' extent: the rates apply BELOW the bore-log rock horizons in NQL2024-0320; rock encountered above those horizons is deemed included. Three inconsistent regimes exist (ITT s18.2 written direction vs H002 n.24 four-way schedule vs VOL38 s7.7 deemed-included) - the priced regime is stated and the inconsistency RFI'd (CL B5/A5) so H002 n.15 cannot bite.
Exclusions & qualifications carried per 01_SCOPE_MATRIX: roofing/DPs above ground (4.3 / 3.3), landscape irrigation (demarcation = the capped E-type flange, L13), plumbing approval lodgement (X2 - RRC plumbing applications; the FRW Private Works lodgement is Principal Contractor as written in ITT s16), trade waste application (X3 = EBC-2), shop drawings (X1 - EBC in the tender control register), court trench drains (TCS, L1), sewer pump station (Addendum 2, L6), design liability (construct-only; seismic = layout drafting only, CL C7).